## Schedule
Eastsound WWTP Upgrade Phase I — Schedule by CWP (proof of concept)
Dates from 00 31 13 via the Project Wiki and Ledger (Verified) with Inferred windows where the documents give none. Owner's planning schedule: "for planning only and does not dictate means and methods" (00 31 13 p.21). Bars: package color; black = milestone.
[12 empty] | Feb 23 |  |  |  | Mar 23 |  |  |  | Apr 23 |  |  |  | May 23 |  |  |  |  | Jun 23 |  |  |  | Jul 23 |  |  |  |  | Aug 23 |  |  |  | Sep 23 |  |  |  | Oct 23 |  |  |  |  | Nov 23 |  |  |  | Dec 23 |  |  |  | Jan 24 |  |  |  |  | Feb 24 |  |  |  | Mar 24 |  |  |  | Apr 24 |  |  |  |  | May 24 |  |  |  | Jun 24 |  |  |  | Jul 24 |  |  |  |  | Aug 24 |  |  |  | Sep 24 |  |  |  |  | Oct 24
ID | Type | CWP | Activity | Start | Finish | Days | Date basis | Tag level | Predecessors (Inferred) | Ledger rows | Ledger tags | time axis 2023-02-06 to 2024-10-21
Project milestones
MS01 | Milestone | Milestone | Bids opened | 2023-02-08 | 2023-02-08 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS02 | Milestone | Milestone | Contract award | 2023-02-15 | 2023-02-15 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS03 | Milestone | Milestone | CPM schedule due (10 days after award) | 2023-02-25 | 2023-02-25 | 0 | 01 31 00 ¶1.05.A / Appendix F §3.0 — 10 days after award (date Inferred from award) | Inferred
MS04 | Milestone | Milestone | Preconstruction meeting and Notice to Proceed | 2023-03-15 | 2023-03-15 | 0 | Pre-con Mar 15, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); NTP Mar 15, 2023 (Appendix F Table 3-1) | Verified
MS05 | Milestone | Milestone | 480V service, MCC and PLC panel complete | 2023-10-04 | 2023-10-04 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.12 | Verified
MS06 | Milestone | Milestone | UV system complete | 2023-10-07 | 2023-10-07 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS07 | Milestone | Milestone | UV on line; effluent switched to new 8-in piping | 2023-10-11 | 2023-10-11 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS08 | Milestone | Milestone | 2W air gap water system complete | 2023-10-18 | 2023-10-18 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS09 | Milestone | Milestone | Influent pump station, flow splitter and sampler on line | 2023-10-25 | 2023-10-25 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS10 | Milestone | Milestone | Major piping complete; aerobic digester complete | 2023-11-01 | 2023-11-01 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.18 | Verified
MS11 | Milestone | Milestone | Dewatering system complete | 2024-02-09 | 2024-02-09 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS12 | Milestone | Milestone | Permanent generator on line; rental removed | 2024-04-30 | 2024-04-30 | 0 | April 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.21); plotted at month end | Verified (month)
MS13 | Milestone | Milestone | Train 3 complete | 2024-07-08 | 2024-07-08 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows | Verified
MS14 | Milestone | Milestone | Substantial Completion | 2024-07-26 | 2024-07-26 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows; SC 19 lists what must be on line | Verified
MS15 | Milestone | Milestone | Final Completion | 2024-10-16 | 2024-10-16 | 0 | 00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.27; 00 73 00 SC 15 | Verified
01-SUM | CWP summary | CWP 01 | CWP 01 General Requirements & Temporary Works | 2023-02-15 | 2024-10-16 | 610 | Earliest start / latest finish of the package (formula) | —
01-P01 | Submittals & procurement | CWP 01 | General Requirements & Temporary Works — submittals and procurement (20 register lines) | 2023-02-15 | 2023-03-14 | 28 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
01-C02 | Construction | CWP 01 | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-15 | 2024-10-16 | 582 | NTP Mar 15, 2023 to Final Completion Oct 16, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 01-P01 | 8 | PROPOSED-Off-site staging area; PROPOSED-Temporary construction sign; PROPOSED-Funding-Recognition-Sign; PROPOSED-Temporary-Barriers; PROPOSED-Temporary-Pump-and-Process-Equipment; PROPOSED-Contractor-Field-Office; PROPOSED-Temporary-Construction-Water-Connection; PROPOSED-Temporary-Sanitary-Facilities
01-C01 | Construction | CWP 01 | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-04-01 | 2023-10-11 | 194 | Set up April 2023; switched to new 8-in effluent when UV goes on line Oct 11, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 01-P01 | 4 | PROPOSED-Temporary bypass pumping system; PROPOSED-Temporary-Bypass-Pipe; PROPOSED-Bypass-Pumping-System; PROPOSED-Temporary-Bypass-Alarm-Monitoring
01-T01 | Inspection & test | CWP 01 | General Requirements & Temporary Works — inspections and tests during the work (11 ITP lines) | 2023-03-15 | 2024-10-16 | 582 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 01-C01, 01-C02
02-SUM | CWP summary | CWP 02 | CWP 02 Demolition & Existing Conditions | 2023-02-15 | 2024-05-31 | 472 | Earliest start / latest finish of the package (formula) | —
02-P01 | Submittals & procurement | CWP 02 | Demolition & Existing Conditions — submittals and procurement (0 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
02-C02 | Construction | CWP 02 | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-04-01 | 2023-05-31 | 61 | Ahead of the April 2023 work starts (Inferred window) | Inferred | 02-P01 | 18 | PROPOSED-Existing 8in effluent outfall pipe; PROPOSED-Existing 4in roof drain pipe; SSMH 1286; SSMH 1285; PROPOSED-Existing 10in effluent outfall pipe; PROPOSED-Existing storm drain and catch basin 87 LF; PROPOSED-Existing 6in drain pipe to sump station; PROPOSED-Existing 1.5in sump force main; PROPOSED-Existing chain link fence 149 LF; PROPOSED-Existing storm drain at roof drain 7 ft; PROPOSED-Existing retaining wall 61 LF; PROPOSED-Existing chain link fence 119 LF; PROPOSED-Existing 4in storm drain 8 LF; PROPOSED-Existing 8in influent pipe; PROPOSED-Asphalt pavement sawcut and removal; PROPOSED-Existing 8in slab over pre-aeration basin; PROPOSED-Existing basin internal piping; PROPOSED-EXISTING-INFLUENT-PIPING-REMOVAL
02-C03 | Construction | CWP 02 | Demolition & Existing Conditions — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 02-P01 | 2 | PROPOSED-Existing holding tanks; PROPOSED-Existing Train 1 influent pipe
02-C01 | Construction | CWP 02 | Demolition & Existing Conditions — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31 | 31 | After the Owner has full use of the new generator (Appendix F §5.3.1; generator on line April 2024) — Inferred window | Inferred | 02-P01 | 1 | PROPOSED-Existing generator fuel tank and spill basin
02-T01 | Inspection & test | CWP 02 | Demolition & Existing Conditions — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2024-05-31 | 427 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 02-C01, 02-C02, 02-C03
03-SUM | CWP summary | CWP 03 | CWP 03 Concrete (Cast-in-Place & Precast) | 2023-02-15 | 2024-07-08 | 510 | Earliest start / latest finish of the package (formula) | —
03-P01 | Submittals & procurement | CWP 03 | Concrete (Cast-in-Place & Precast) — submittals and procurement (8 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
03-C02 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 03-P01 | 2 | PROPOSED-Blower-Building-Slab-and-Grade-Beams; PROPOSED-Blower-Pad
03-C05 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Sludge pumps and valving | 2023-04-01 | 2023-11-01 | 215 | Start April 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = digester complete Nov 1, 2023 (Inferred) | Inferred | 03-P01 | 1 | PROPOSED-Existing-Slab-Trench-Infill
03-C07 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 03-P01 | 6 | PROPOSED-EFFLUENT-SAMPLE-SUMP; PROPOSED-UV-DIGESTER-STRUCTURE; PROPOSED-UV-Disinfection-Chamber-Basin; PROPOSED-Digester-Concrete-Tank; PROPOSED-Aerobic-Digester; PROPOSED-UV-Disinfection-Chamber
03-C08 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 03-P01 | 5 | PROPOSED-Existing slab coring and repair; PROPOSED-Influent-Flow-Meter-Valve-Vault; PROPOSED-Effluent-Flow-Meter-Valve-Vault; PROPOSED-Plants-2-and-3-Flow-Meter-Vault; PROPOSED-Yard-Piping-Vaults
03-C01 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — 2W air gap water system | 2023-05-01 | 2023-10-18 | 171 | Start May 2023; complete Oct 18, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 03-P01 | 1 | PROPOSED-2W-Pump-Station-Precast-Wet-Well
03-C04 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 03-P01 | 13 | PROPOSED-FLOW-SPLITTER-SUPPORT; PROPOSED-INFLUENT-FLOW-METER-VAULT; PROPOSED-TRAIN-2-FLOW-METER-VAULT; PROPOSED-TRAIN-3-FLOW-METER-VAULT; PROPOSED-IPS-HATCHES; PROPOSED-Drain-Pump-Station-Lid; PROPOSED-Drain-Pump-Station-Precast-Wet-Well; PROPOSED-Drain-Pump-Station-Hatches; PROPOSED-Flow-Splitter-Pad; PROPOSED-Influent-Pump-Station-Precast-Wet-Well; PROPOSED-Influent-Pump-Station-Top-Slab; PROPOSED-Influent-Pump-Station-Meter-Vaults; PROPOSED-Influent-Pump-Station
03-C06 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 03-P01 | 1 | PROPOSED-Train-3-Concrete-Tank
03-C03 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Permanent standby generator | 2024-03-01 | 2024-04-30 | 61 | Installed, tested and on line April 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.21); start Inferred | Inferred | 03-P01 | 1 | PROPOSED-Generator-Slab
03-T01 | Inspection & test | CWP 03 | Concrete (Cast-in-Place & Precast) — inspections and tests during the work (4 ITP lines) | 2023-04-01 | 2024-07-08 | 465 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 03-C01, 03-C02, 03-C03
03-S01 | Test / start-up | CWP 03 | Clean-water leakage test — UV chamber | 2023-09-27 | 2023-10-10 | 14 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 03-C01, 03-C02, 03-C04, 03-C05, 03-C06, 03-C07, 03-C08
03-S02 | Test / start-up | CWP 03 | Clean-water leakage test — 2W wet well | 2023-10-04 | 2023-10-17 | 14 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 03-C01, 03-C02, 03-C04, 03-C05, 03-C06, 03-C07, 03-C08
03-S03 | Test / start-up | CWP 03 | Clean-water leakage test — influent pump station wet well and flow splitter | 2023-10-11 | 2023-10-24 | 14 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 03-C01, 03-C02, 03-C04, 03-C05, 03-C06, 03-C07, 03-C08
03-S04 | Test / start-up | CWP 03 | Clean-water leakage test — aerobic digester | 2023-10-18 | 2023-10-31 | 14 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 03-C01, 03-C02, 03-C04, 03-C05, 03-C06, 03-C07, 03-C08
03-S05 | Test / start-up | CWP 03 | Clean-water leakage test — Train 3 aeration and anoxic basins and clarifier | 2024-06-24 | 2024-07-07 | 14 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 03-C01, 03-C02, 03-C03, 03-C04, 03-C05, 03-C06, 03-C07, 03-C
05-SUM | CWP summary | CWP 05 | CWP 05 Metals (Grating, Railings, Ladders, Stairs) | 2023-02-15 | 2024-07-08 | 510 | Earliest start / latest finish of the package (formula) | —
05-P01 | Submittals & procurement | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — submittals and procurement (7 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
05-C02 | Construction | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 05-P01 | 4 | PROPOSED-UV-DIGESTER-GRATING-GUARDRAIL; PROPOSED-Digester-Grating-Beam; PROPOSED-UV-Digester-Grating; PROPOSED-UV-Digester-Guardrail-and-Ladders
05-C01 | Construction | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 05-P01 | 2 | PROPOSED-Train-3-Guardrail-and-Ladders; PROPOSED-Steel-Stairs-Ladders-Platforms
05-T01 | Inspection & test | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — inspections and tests during the work (1 ITP lines) | 2023-04-01 | 2024-07-08 | 465 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 05-C01, 05-C02
08-SUM | CWP summary | CWP 08 | CWP 08 Doors, Frames & Hardware | 2023-02-15 | 2023-07-31 | 167 | Earliest start / latest finish of the package (formula) | —
08-P01 | Submittals & procurement | CWP 08 | Doors, Frames & Hardware — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
08-C01 | Construction | CWP 08 | Doors, Frames & Hardware — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 08-P01 | 4 | 101A; 101B; 101C; PROPOSED-Boot-Brush-and-Pad
08-T01 | Inspection & test | CWP 08 | Doors, Frames & Hardware — inspections and tests during the work (2 ITP lines) | 2023-04-01 | 2023-07-31 | 122 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 08-C01
09-SUM | CWP summary | CWP 09 | CWP 09 Painting & Coatings | 2023-02-15 | 2023-10-25 | 253 | Earliest start / latest finish of the package (formula) | —
09-P01 | Submittals & procurement | CWP 09 | Painting & Coatings — submittals and procurement (4 register lines) | 2023-02-15 | 2023-05-31 | 106 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
09-C01 | Construction | CWP 09 | Painting & Coatings — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 09-P01 | 1 | PROPOSED-Influent-Pump-Station-Interior-Coating
09-T01 | Inspection & test | CWP 09 | Painting & Coatings — inspections and tests during the work (3 ITP lines) | 2023-06-01 | 2023-10-25 | 147 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 09-C01
10-SUM | CWP summary | CWP 10 | CWP 10 Specialties | 2023-02-15 | 2024-07-08 | 510 | Earliest start / latest finish of the package (formula) | —
10-P01 | Submittals & procurement | CWP 10 | Specialties — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
10-C01 | Construction | CWP 10 | Specialties — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 10-P01 | 1 | PROPOSED-Fire-Extinguishers-Blower-Building
10-C03 | Construction | CWP 10 | Specialties — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 10-P01 | 1 | PROPOSED-WWTP tank and building signs
10-C02 | Construction | CWP 10 | Specialties — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 10-P01 | 1 | PROPOSED-TRAIN-3-FRP-LAUNDER-COVER
10-T01 | Inspection & test | CWP 10 | Specialties — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-07-08 | 465 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 10-C01, 10-C02, 10-C03
13-SUM | CWP summary | CWP 13 | CWP 13 Pre-Engineered Metal Building | 2023-02-15 | 2024-05-31 | 472 | Earliest start / latest finish of the package (formula) | —
13-P01 | Submittals & procurement | CWP 13 | Pre-Engineered Metal Building — submittals and procurement (5 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
13-C01 | Construction | CWP 13 | Pre-Engineered Metal Building — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 13-P01 | 1 | PROPOSED-BLOWER-BUILDING; PROPOSED-Blower-Building
13-C03 | Construction | CWP 13 | Pre-Engineered Metal Building — Site demolition ahead of new work | 2023-04-01 | 2023-05-31 | 61 | Ahead of the April 2023 work starts (Inferred window) | Inferred | 13-P01 | 2 | PROPOSED-Existing-Office-Louver-4x4; PROPOSED-Existing-Office-Louver-2x3
13-C04 | Construction | CWP 13 | Pre-Engineered Metal Building — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09 | 315 | Sludge pumps start April 2023 through dewatering complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 13-P01 | 2 | PROPOSED-WWTP-Building-Louver-3x7; PROPOSED-WWTP-Building-Exhaust-Fan-24x24
13-C02 | Construction | CWP 13 | Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31 | 31 | After the Owner has full use of the new generator (Appendix F §5.3.1; generator on line April 2024) — Inferred window | Inferred | 13-P01 | 2 | PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers; PROPOSED-Existing-Generator-Exhaust-Assembly
13-T01 | Inspection & test | CWP 13 | Pre-Engineered Metal Building — inspections and tests during the work (1 ITP lines) | 2023-04-01 | 2024-05-31 | 427 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 13-C01, 13-C02, 13-C03
22-SUM | CWP summary | CWP 22 | CWP 22 Plumbing & Process Pumps | 2023-02-15 | 2024-02-09 | 360 | Earliest start / latest finish of the package (formula) | —
22-P01 | Submittals & procurement | CWP 22 | Plumbing & Process Pumps — submittals and procurement (6 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
22-C02 | Construction | CWP 22 | Plumbing & Process Pumps — Sludge pumps and valving | 2023-04-01 | 2023-11-01 | 215 | Start April 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = digester complete Nov 1, 2023 (Inferred) | Inferred | 22-P01 | 5 | PROPOSED-WAS-PUMP; PROPOSED-SWING-SLUDGE-PUMP; PROPOSED-DIGESTED-SLUDGE-PUMP; PROPOSED-SLUDGE-PUMP-LOCAL-PANELS; PROPOSED-Sludge-Pumps
22-C03 | Construction | CWP 22 | Plumbing & Process Pumps — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09 | 315 | Sludge pumps start April 2023 through dewatering complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 22-P01 | 3 | WP-1; WP-2; SD-1
22-C04 | Construction | CWP 22 | Plumbing & Process Pumps — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 22-P01 | 3 | PROPOSED-YARD-HYDRANTS; PROPOSED-POST-HYDRANTS; PROPOSED-EXTERIOR-SANITARY-DRAINS
22-C01 | Construction | CWP 22 | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 22-P01 | 14 | PROPOSED-IPS-DISCHARGE-TO-SPLITTER; PROPOSED-INFLUENT-PUMP-STATION-WET-WELL; PROPOSED-INFLUENT-PUMPS-SMALL; PROPOSED-INFLUENT-PUMPS-LARGE; PROPOSED-IPS-LEVEL-TRANSDUCER; F1–F4 [Influent Pump Station]; PROPOSED-IPS-VALVE-VAULTS; PROPOSED-IPS-MOTOR-SAVER-RELAYS; IP-1; IP-2; IP-3; IP-4; PROPOSED-Influent-Pump-Seal-Fail-Overtemp-Relays; PROPOSED-Submersible-Pump-Equipment
22-T01 | Inspection & test | CWP 22 | Plumbing & Process Pumps — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-02-09 | 315 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 22-C01, 22-C02, 22-C03
22-S12 | Test / start-up | CWP 22 | Influent pumps and flow splitter start-up | 2023-10-18 | 2023-10-25 | 8 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 22-C01, 22-C02, 22-C03, 22-C04
23-SUM | CWP summary | CWP 23 | CWP 23 HVAC & Ventilation | 2023-02-15 | 2024-02-09 | 360 | Earliest start / latest finish of the package (formula) | —
23-P01 | Submittals & procurement | CWP 23 | HVAC & Ventilation — submittals and procurement (1 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
23-C01 | Construction | CWP 23 | HVAC & Ventilation — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 23-P01 | 10 | PROPOSED-BLOWER-BLDG-WALL-FANS; PROPOSED-BLOWER-BLDG-MOTORIZED-LOUVER; PROPOSED-BLOWER-BLDG-MANUAL-LOUVER; EF-1; EF-2; ML-1; PROPOSED-Blower-Building-Manual-Louver; PROPOSED-Louver-36x84-Motorized; PROPOSED-Louver-24x24-Manual; PROPOSED-Exhaust-Fans-Blower-Building
23-C02 | Construction | CWP 23 | HVAC & Ventilation — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09 | 315 | Sludge pumps start April 2023 through dewatering complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 23-P01 | 5 | PROPOSED-EXISTING-BLDG-WALL-FANS; PROPOSED-EXISTING-BLDG-LOUVERS; EF-3; EF-4; EF-5
23-T01 | Inspection & test | CWP 23 | HVAC & Ventilation — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2024-02-09 | 315 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 23-C01, 23-C02
26-SUM | CWP summary | CWP 26 | CWP 26 Electrical, Instrumentation & Controls | 2023-02-15 | 2024-10-16 | 610 | Earliest start / latest finish of the package (formula) | —
26-P01 | Submittals & procurement | CWP 26 | Electrical, Instrumentation & Controls — submittals and procurement (26 register lines) | 2023-02-15 | 2023-03-14 | 28 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
26-C12 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Temporary facilities and controls | 2023-03-15 | 2024-10-16 | 582 | NTP Mar 15, 2023 to Final Completion Oct 16, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 26-P01 | 2 | PROPOSED-Construction-Power-Service; PROPOSED-Temporary-Construction-Power
26-C02 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 26-P01 | 19 | MCC; MCP; LP-1; PROPOSED-Blower-Building-Power-Handholes; PROPOSED-Blower-Building-Control-Signal-Handholes; PROPOSED-Blower-Building-Smoke-Heat-Detector; PROPOSED-Blower-Building-Door-Intrusion-Switch; PROPOSED-2W-Pressure-Transducer; PROPOSED-Blower-High-Temperature-Switches; PROPOSED-Blower-Building-Grounding-Electrode-System; L1 (Blower Building); L2 (Blower Building); X1 (Blower Building); PROPOSED-Blower-Building-Ventilation-Control-Panel; T2; PROPOSED-VFDs-in-MCC; PROPOSED-Blower-PTC-Relay-Modules; PROPOSED-Electrical-Equipment-Housekeeping-Pads; PROPOSED-Motor-Control-Center
26-C05 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Aerobic digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 2 | PROPOSED-DB-Local-Disconnect; PROPOSED-Digester-Level-Transducer
26-C10 | Construction | CWP 26 | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-04-01 | 2023-10-04 | 187 | Electrical starts April 2023; complete Oct 4, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 15 | PROPOSED-Hot Box #1 flow meter; PROPOSED-EFFLUENT-FLOW-METER; PROPOSED-Utility-Transformer-480V; P-SEC; PROPOSED-CT-Enclosure-and-Meter-Base; ATS; MDP; TS; PROPOSED-Existing-Grounding-Electrode-System; PROPOSED-Conduit-and-Conductor-Runs; PROPOSED-8in-Effluent-Flow-Meter; PROPOSED-Automatic-Transfer-Switch; PROPOSED-480V-Electrical-Service; PROPOSED-PLC-Control-Panel; PROPOSED-Magnetic-Flow-Meters
26-C11 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Sludge pumps and valving | 2023-04-01 | 2023-11-01 | 215 | Start April 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = digester complete Nov 1, 2023 (Inferred) | Inferred | 26-P01 | 1 | PROPOSED-WAS-FLOW-METER
26-C15 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09 | 315 | Sludge pumps start April 2023 through dewatering complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 26-P01 | 12 | P-TPS; TPS; PROPOSED-Existing-208V-400A-Distribution-Panel; PROPOSED-Treatment-Building-Power-Handhole; PROPOSED-Treatment-Building-Control-Signal-Handhole; PROPOSED-WAS-Dewatering-Flow-Meter; PROPOSED-WAS-and-Sludge-Pump-Local-Disconnects; PROPOSED-Treatment-Building-Ventilation-Control-Panel; PROPOSED-Methane-Sensor; PROPOSED-H2S-Sensor; PROPOSED-Gas-Alarm-Light-and-Horn; L2 (Treatment Building)
26-C16 | Construction | CWP 26 | Electrical, Instrumentation & Controls — UV chamber | 2023-04-01 | 2023-10-11 | 194 | Start April 2023; UV channels in service Oct 11, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 7 | PROPOSED-Effluent-Flow-Meter; PROPOSED-Effluent-Flow-Meter-Transmitter-Panel; PROPOSED-UV-Control-Panel-1; PROPOSED-UV-Control-Panel-2; PROPOSED-UV-Power-Distribution-1; PROPOSED-UV-Power-Distribution-2; PROPOSED-UV-Area-Pole-Light
26-C17 | Construction | CWP 26 | Electrical, Instrumentation & Controls — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 1 | S1–S2 [Aerobic Digester]
26-C01 | Construction | CWP 26 | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-05-01 | 2023-10-18 | 171 | Start May 2023; complete Oct 18, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 7 | PROPOSED-2W-Flow-Meter; LSH-111; F2 (2W Pump Station); F3 (2W Pump Station); LSL-111; PROPOSED-2W-Pump-Local-Disconnects; PROPOSED-Hot-Box-Heat-Trace
26-C08 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 19 | PROPOSED-Train 2 flow meter; PROPOSED-INFLUENT-FLOW-METER; PROPOSED-TRAIN-2-FLOW-METER; PROPOSED-TRAIN-3-FLOW-METER; PROPOSED-PLANT-DRAIN-FLOW-METER; PROPOSED-Plant-Drain-Flow-Meter; F1 (Influent Pump Station); F2 (Influent Pump Station); F3 (Influent Pump Station); F4 (Influent Pump Station); LT (Influent Pump Station); IPS; T3; LP2; PROPOSED-Influent-Pump-Local-Disconnects; PROPOSED-Influent-Wet-Well-Power-Handhole; PROPOSED-Influent-Wet-Well-Instrument-Handhole; PROPOSED-Influent-Flow-Meter; PROPOSED-Plant-2-Flow-Meter; PROPOSED-Plant-3-Flow-Meter
26-C14 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 26-P01 | 3 | PROPOSED-Train 3 flow meter; PROPOSED-Train-3-Local-Disconnects; PROPOSED-Train-3-Pole-Light
26-C13 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | 2023-09-25 | 2024-04-30 | 219 | Rent Sept 25, 2023 until the permanent generator is on line, April 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; Add. 4 Clarification 5) | Verified (finish to month) | 26-P01 | 3 | PROPOSED-Temporary power generator; PROPOSED-Temporary-Backup-Generator; PROPOSED-Temporary-Back-Up-Generator
26-C09 | Construction | CWP 26 | Electrical, Instrumentation & Controls — SCADA / PLC programming | 2023-10-04 | 2024-07-26 | 297 | After the PLC panel is complete Oct 4, 2023 through Substantial Completion July 26, 2024 (SC 19 lists SCADA/PLC programming) — span Inferred | Inferred | 26-P01 | 1 | PROPOSED-SCADA-Computer-System
26-C04 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-10-05 | 2023-10-31 | 27 | After the new 480V service is complete Oct 4, 2023 (Inferred window) | Inferred | 26-P01 | 4 | PROPOSED-Existing-Utility-Transformer-208V; PROPOSED-Existing-CT-Enclosure-and-Meter; PROPOSED-Existing-Meter-Base-and-Wall-Raceway; PROPOSED-Existing-200A-Feeder-to-Panel-TPS
26-C07 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Permanent standby generator | 2024-03-01 | 2024-04-30 | 61 | Installed, tested and on line April 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows, ¶A.21); start Inferred | Inferred | 26-P01 | 4 | GEN; PROPOSED-Service-Area-Grounding-Electrode-System; PROPOSED-Generator-on-S2.4; PROPOSED-Permanent-Standby-Generator
26-C03 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31 | 31 | After the Owner has full use of the new generator (Appendix F §5.3.1; generator on line April 2024) — Inferred window | Inferred | 26-P01 | 3 | GEN (E); SES (E); ATS (E)
26-T01 | Inspection & test | CWP 26 | Electrical, Instrumentation & Controls — inspections and tests during the work (23 ITP lines) | 2023-03-15 | 2024-10-16 | 582 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 26-C01, 26-C02, 26-C03
26-S08 | Test / start-up | CWP 26 | 480V service, MCC and PLC testing and energization | 2023-09-20 | 2023-10-04 | 15 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 26-C01, 26-C02, 26-C05, 26-C08, 26-C10, 26-C11, 26-C12, 26-C
26-S07 | Test / start-up | CWP 26 | Temporary generator connection and automatic load transfer test (Add. 4 Clarification 5) | 2023-09-25 | 2023-10-04 | 10 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 26-C01, 26-C02, 26-C05, 26-C08, 26-C10, 26-C11, 26-C12, 26-C
26-S09 | Test / start-up | CWP 26 | Permanent generator load bank test, 2 hours at full load (26 32 13) | 2024-04-15 | 2024-04-30 | 16 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 26-C01, 26-C02, 26-C04, 26-C05, 26-C07, 26-C08, 26-C09, 26-C
26-C06 | Not scheduled | CWP 26 | Electrical, Instrumentation & Controls — Future provisions — not scheduled |  |  |  | Marked FUTURE on the drawings; not Phase I work | Verified |  | 3 | PROPOSED-Train-1-Flow-Meter; TCP-1; TCP-2
31-SUM | CWP summary | CWP 31 | CWP 31 Earthwork, Dewatering & Erosion Control | 2023-02-15 | 2024-10-16 | 610 | Earliest start / latest finish of the package (formula) | —
31-P01 | Submittals & procurement | CWP 31 | Earthwork, Dewatering & Erosion Control — submittals and procurement (11 register lines) | 2023-02-15 | 2023-03-14 | 28 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
31-C02 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-15 | 2024-10-16 | 582 | NTP Mar 15, 2023 to Final Completion Oct 16, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 31-P01 | 14 | PROPOSED-Plastic covering for slopes and stockpiles; PROPOSED-Catch basin inserts; PROPOSED-Filter fabric fence; PROPOSED-Stabilized construction entrance; PROPOSED-Geotextile encased check dams; PROPOSED-Dewatering system; PROPOSED-Compost berm; PROPOSED-Orange barrier fence; PROPOSED-Temporary shoring and trench safety systems; PROPOSED-Emergency access areas; PROPOSED-Trench-Safety-System; PROPOSED-Erosion-and-Sediment-Control-Measures; PROPOSED-Temporary-Construction-Dewatering; PROPOSED-Temporary-Excavation-Support
31-C04 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 31-P01 | 2 | PROPOSED-Tracer wire and locater boxes; PROPOSED-Influent sample sump
31-C01 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 31-P01 | 2 | PROPOSED-Train 2 flow meter vault; PROPOSED-INFLUENT-SAMPLE-SUMP
31-C03 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 31-P01 | 1 | PROPOSED-Train 3 flow meter vault
31-T01 | Inspection & test | CWP 31 | Earthwork, Dewatering & Erosion Control — inspections and tests during the work (9 ITP lines) | 2023-03-15 | 2024-10-16 | 582 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 31-C01, 31-C02, 31-C03
32-SUM | CWP summary | CWP 32 | CWP 32 Paving, Fencing, Walls & Landscaping | 2023-02-15 | 2024-10-16 | 610 | Earliest start / latest finish of the package (formula) | —
32-P01 | Submittals & procurement | CWP 32 | Paving, Fencing, Walls & Landscaping — submittals and procurement (6 register lines) | 2023-02-15 | 2023-03-14 | 28 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
32-C03 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Temporary facilities and controls | 2023-03-15 | 2024-10-16 | 582 | NTP Mar 15, 2023 to Final Completion Oct 16, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 32-P01 | 1 | PROPOSED-Temporary cold-mix patches
32-C01 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2024-08-01 | 2024-08-31 | 31 | Entire site, August 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 32-P01 | 6 | PROPOSED-Parking stall striping; PROPOSED-Concrete walkway; PROPOSED-HMA pavement; PROPOSED-Gravel surfacing; PROPOSED-Asphalt wedge curb; PROPOSED-Site-Final-Surfacing-and-Pavement
32-C02 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2024-08-01 | 2024-09-30 | 61 | With final surfacing, August 2024, before Final Completion Oct 16, 2024 (Inferred window) | Inferred | 32-P01 | 5 | PROPOSED-Block retaining wall; PROPOSED-Chain link fence 126 LF; PROPOSED-Hydroseeded restoration areas; PROPOSED-Retaining wall footing drain; PROPOSED-Bollards
32-T01 | Inspection & test | CWP 32 | Paving, Fencing, Walls & Landscaping — inspections and tests during the work (2 ITP lines) | 2023-03-15 | 2024-10-16 | 582 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 32-C01, 32-C02, 32-C03
33-SUM | CWP summary | CWP 33 | CWP 33 Yard Piping & Utilities | 2023-02-15 | 2024-07-08 | 510 | Earliest start / latest finish of the package (formula) | —
33-P01 | Submittals & procurement | CWP 33 | Yard Piping & Utilities — submittals and procurement (14 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
33-C01 | Construction | CWP 33 | Yard Piping & Utilities — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 33-P01 | 5 | PROPOSED-AERATION-AIR-HEADER; PROPOSED-AIR-TO-TRAIN-3; PROPOSED-AIR-TO-TRAIN-1-STUB; PROPOSED-AIR-TO-TRAIN-2-STUB; PROPOSED-Blower-Building-Foundation-Drains
33-C02 | Construction | CWP 33 | Yard Piping & Utilities — Temporary bypass and interim effluent piping | 2023-04-01 | 2023-10-11 | 194 | Set up April 2023; switched to new 8-in effluent when UV goes on line Oct 11, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 33-P01 | 2 | PROPOSED-Interim 8in HDPE effluent pipe; PROPOSED-Temporary-8in-Effluent-Piping
33-C05 | Construction | CWP 33 | Yard Piping & Utilities — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 33-P01 | 5 | PROPOSED-EFFLUENT-HEADER-TO-UV; PROPOSED-UV-CHAMBER-DRAIN; PROPOSED-DIGESTER-AIR-LINES; PROPOSED-DIGESTED-SLUDGE-LINE; PROPOSED-WAS-PUMP-DISCHARGE-TO-DIGESTER
33-C06 | Construction | CWP 33 | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 33-P01 | 70 | PROPOSED-Water line relocation at storm drain; Pipe ID 1; Pipe ID 2; Pipe ID 3; Pipe ID 4; Pipe ID 5; Pipe ID 6; Pipe ID 7; Pipe ID 8; Pipe ID 9; Pipe ID 10; Pipe ID 11; Pipe ID 12; Pipe ID 13; Pipe ID 14; Pipe ID 15; Pipe ID 16; Pipe ID 17; Pipe ID 18; Pipe ID 19 (+50 more)
33-C03 | Construction | CWP 33 | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 33-P01 | 4 | INF1; INF2; INF3; PROPOSED-STEP-INFLUENT-CONNECTION
33-C04 | Construction | CWP 33 | Yard Piping & Utilities — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 33-P01 | 2 | PROPOSED-Floor drains; SE3
33-T01 | Inspection & test | CWP 33 | Yard Piping & Utilities — inspections and tests during the work (21 ITP lines) | 2023-04-01 | 2024-07-08 | 465 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 33-C01, 33-C02, 33-C03
33-S06 | Test / start-up | CWP 33 | Pipe pressure testing, witnessed (48-hour notice) | 2023-10-01 | 2023-10-31 | 31 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 33-C01, 33-C02, 33-C03, 33-C04, 33-C05, 33-C06
40-SUM | CWP summary | CWP 40 | CWP 40 Process Interconnections | 2023-02-15 | 2023-11-01 | 260 | Earliest start / latest finish of the package (formula) | —
40-P01 | Submittals & procurement | CWP 40 | Process Interconnections — submittals and procurement (1 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
40-C01 | Construction | CWP 40 | Process Interconnections — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 40-P01 | 1 | PROPOSED-DIGESTER-TELESCOPING-VALVE
40-T01 | Inspection & test | CWP 40 | Process Interconnections — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2023-11-01 | 215 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 40-C01
41-SUM | CWP summary | CWP 41 | CWP 41 Material Handling (Screw Conveyors) | 2023-02-15 | 2024-02-09 | 360 | Earliest start / latest finish of the package (formula) | —
41-P01 | Submittals & procurement | CWP 41 | Material Handling (Screw Conveyors) — submittals and procurement (1 register lines) | 2023-02-15 | 2023-10-31 | 259 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
41-C01 | Construction | CWP 41 | Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09 | 101 | Complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); start = digester complete (Inferred) | Inferred | 41-P01 | 2 | Receiving Conveyor; Inclined Conveyor
41-T01 | Inspection & test | CWP 41 | Material Handling (Screw Conveyors) — inspections and tests during the work (1 ITP lines) | 2023-11-01 | 2024-02-09 | 101 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 41-C01
43-SUM | CWP summary | CWP 43 | CWP 43 Blowers & 2W Plant Water System | 2023-02-15 | 2024-02-09 | 360 | Earliest start / latest finish of the package (formula) | —
43-P01 | Submittals & procurement | CWP 43 | Blowers & 2W Plant Water System — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
43-C02 | Construction | CWP 43 | Blowers & 2W Plant Water System — Blower Building | 2023-04-01 | 2023-07-31 | 122 | Start April 2023; complete July 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (month) | 43-P01 | 10 | ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3); PROPOSED-EYE-WASH-STATIONS; BL-1; BL-2; BL-3; BL-4; DB; PROPOSED-Blowers-Blower-Building; PROPOSED-2W-Bladder-Tank-Assembly; PROPOSED-Blowers
43-C04 | Construction | CWP 43 | Blowers & 2W Plant Water System — Aerobic digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 43-P01 | 1 | ESWD WWTP – Aerobic Digester Blower
43-C05 | Construction | CWP 43 | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 43-P01 | 4 | Hot Box #1; Hot Box #2; PROPOSED-Hot Box #1 solenoid valve; PROPOSED-2W-AIR-GAP-ENCLOSURE
43-C01 | Construction | CWP 43 | Blowers & 2W Plant Water System — 2W air gap water system | 2023-05-01 | 2023-10-18 | 171 | Start May 2023; complete Oct 18, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 43-P01 | 15 | PROPOSED-2W-FLOW-METER; PROPOSED-2W-PUMP-STATION-WET-WELL; PROPOSED-2W-Pump-Station-Wet-Well; PROPOSED-2W-PUMPS; F1–F4 [2W Pump Station]; PROPOSED-2W-DIAPHRAGM-TANKS; PIT-620; PROPOSED-2W-DISCHARGE-LINE; PROPOSED-2W-FILL-LINE; PROPOSED-2W-BLADDER-TANK-SUPPLY; 2W-P1; 2W-P2; PROPOSED-Hot-Box-1; PROPOSED-Hot-Box-2; PROPOSED-2W-Isolation-Valve-Solenoid; PROPOSED-2W-Air-Gap-Water-System
43-C03 | Construction | CWP 43 | Blowers & 2W Plant Water System — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09 | 101 | Complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); start = digester complete (Inferred) | Inferred | 43-P01 | 1 | PROPOSED-2W-SUPPLY-TO-PRESS
43-T01 | Inspection & test | CWP 43 | Blowers & 2W Plant Water System — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-02-09 | 315 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 43-C01, 43-C02, 43-C03
43-S11 | Test / start-up | CWP 43 | 2W system start-up (01 91 00 ¶1.10: hold 60–90 psi, 0–50 gpm) | 2023-10-11 | 2023-10-18 | 8 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 43-C01, 43-C02, 43-C04, 43-C05
43-S13 | Test / start-up | CWP 43 | Blower start-up (01 91 00) | 2023-10-18 | 2023-11-01 | 15 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 43-C01, 43-C02, 43-C04, 43-C05
45-SUM | CWP summary | CWP 45 | CWP 45 Process Valves | 2023-02-15 | 2023-11-01 | 260 | Earliest start / latest finish of the package (formula) | —
45-P01 | Submittals & procurement | CWP 45 | Process Valves — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
45-C01 | Construction | CWP 45 | Process Valves — Aerobic digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 45-P01 | 1 | PROPOSED-AIR-BUTTERFLY-VALVES
45-C03 | Construction | CWP 45 | Process Valves — Sludge pumps and valving | 2023-04-01 | 2023-11-01 | 215 | Start April 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = digester complete Nov 1, 2023 (Inferred) | Inferred | 45-P01 | 1 | PROPOSED-SLUDGE-MANIFOLD-PIPING
45-C02 | Construction | CWP 45 | Process Valves — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 45-P01 | 2 | PROPOSED-IPS-CHECK-VALVES; PROPOSED-IPS-GATE-VALVES
45-T01 | Inspection & test | CWP 45 | Process Valves — inspections and tests during the work (2 ITP lines) | 2023-04-01 | 2023-11-01 | 215 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 45-C01, 45-C02, 45-C03
46-SUM | CWP summary | CWP 46 | CWP 46 Treatment Equipment | 2023-02-15 | 2024-07-12 | 514 | Earliest start / latest finish of the package (formula) | —
46-P01 | Submittals & procurement | CWP 46 | Treatment Equipment — submittals and procurement (19 register lines) | 2023-02-15 | 2023-03-31 | 45 | Submittals start after award, long-lead items first (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = day before the package's first work (Inferred). Vendor lead times not stated in the documents. | Inferred
46-C03 | Construction | CWP 46 | Treatment Equipment — Sludge pumps and valving | 2023-04-01 | 2023-11-01 | 215 | Start April 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); finish = digester complete Nov 1, 2023 (Inferred) | Inferred | 46-P01 | 1 | PROPOSED-WAS-SOLENOID-VALVES
46-C05 | Construction | CWP 46 | Treatment Equipment — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09 | 315 | Sludge pumps start April 2023 through dewatering complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows; span Inferred) | Inferred | 46-P01 | 3 | DW-1; PROPOSED-WAS-Solenoid-Valves; PROPOSED-Polymer-Feed-Pump
46-C06 | Construction | CWP 46 | Treatment Equipment — UV chamber | 2023-04-01 | 2023-10-11 | 194 | Start April 2023; UV channels in service Oct 11, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 46-P01 | 3 | PROPOSED-UV-TRANSMISSIVITY-ANALYZER; UV1; UV2
46-C07 | Construction | CWP 46 | Treatment Equipment — UV chamber and digester | 2023-04-01 | 2023-11-01 | 215 | Start April 2023; UV on line Oct 11, 2023; digester complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 46-P01 | 5 | PROPOSED-UV-SYSTEM; PROPOSED-UV-CONTROL-PANELS; PROPOSED-DIGESTER-DIFFUSERS; PROPOSED-UV-INTENSITY-SENSORS; PROPOSED-UV-Disinfection-System
46-C08 | Construction | CWP 46 | Treatment Equipment — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01 | 215 | Yard piping and vaults start April 2023; major piping complete Nov 1, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 46-P01 | 1 | PROPOSED-PLANT-DRAIN-LINE
46-C02 | Construction | CWP 46 | Treatment Equipment — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25 | 147 | Start June 2023; on line Oct 25, 2023 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 46-P01 | 5 | PROPOSED-FLOW-SPLITTER-BOX; PROPOSED-Influent-Sampler; PROPOSED-Flow-Splitter; PROPOSED-Influent-Flow-Splitter
46-C04 | Construction | CWP 46 | Treatment Equipment — Train 3 | 2023-08-01 | 2024-07-08 | 343 | Start Aug 2023; complete July 8, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified (start to month) | 46-P01 | 29 | WAS3; DO #1; DO-1; DO #2; DO-2; PROPOSED-TRAIN-3-TANK; PROPOSED-TRAIN-3-TREATMENT-SYSTEM; PROPOSED-TRAIN-3-INNER-WALLS; PROPOSED-TRAIN-3-CLARIFIER-MECHANISM; PROPOSED-TRAIN-3-WALKWAYS-AND-LADDER; PROPOSED-TRAIN-3-AERATION-DIFFUSERS; PROPOSED-TRAIN-3-ANOXIC-MIXERS; PROPOSED-TRAIN-3-DAVIT-CRANES; PROPOSED-TRAIN-3-RAS-AIRLIFT; PROPOSED-TRAIN-3-MLR-AIRLIFT; PROPOSED-CARBON-FEED-PUMPS; PROPOSED-TRAIN-3-CONTROL-PANEL; TCP-3; PROPOSED-Train-3-Clarifier-Drive-Motor; PROPOSED-Train-3-Submersible-Mixer-A (+11 more)
46-C01 | Construction | CWP 46 | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09 | 101 | Complete Feb 9, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows); start = digester complete (Inferred) | Inferred | 46-P01 | 13 | PROPOSED-DIGESTED-SLUDGE-FLOW-METER; PROPOSED-ROTARY-FAN-PRESS; PROPOSED-RFP-FLOCCULATOR; PROPOSED-RFP-SLUDGE-MANIFOLD; PROPOSED-RFP-CAKE-CHUTE; PROPOSED-RFP-AIR-COMPRESSOR; PROPOSED-RFP-CONTROL-PANEL; PROPOSED-POLYMER-SYSTEM; PROPOSED-SCREW-CONVEYOR; PROPOSED-DIGESTED-SLUDGE-FEED-TO-PRESS; PROPOSED-RFP-POLYMER-FLOWMETER; PROPOSED-RFP-INLET-PRESSURE-TRANSMITTER; PROPOSED-Dewatering-System
46-T01 | Inspection & test | CWP 46 | Treatment Equipment — inspections and tests during the work (13 ITP lines) | 2023-04-01 | 2024-07-08 | 465 | Window = the package's construction span (Inferred); requirements per the Inspection & Test Plan | Inferred | 46-C01, 46-C02, 46-C03
46-S10 | Test / start-up | CWP 46 | UV system start-up and field testing (46 66 00: 2 days start-up, 1 day training) | 2023-10-07 | 2023-10-11 | 5 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 46-C02, 46-C03, 46-C04, 46-C05, 46-C06, 46-C07, 46-C08
46-S14 | Test / start-up | CWP 46 | Dewatering system start-up (01 91 00 ¶1.07.A) | 2024-02-01 | 2024-02-09 | 9 | Requirement per the cited section; window = the two weeks (or stated gap) before the on-line / completion milestone (Inferred) | Inferred | 46-C01, 46-C02, 46-C03, 46-C04, 46-C05, 46-C06, 46-C07, 46-C
46-S15 | Test / start-up | CWP 46 | Train 3 start-up and seeding, 10,000 gal activated sludge | 2024-07-08 | 2024-07-12 | 5 | Seeding July 8–12, 2024 (00 31 13 pp.21–22 via the Contract & General Wiki note and rows) | Verified | 46-C01, 46-C02, 46-C03, 46-C04, 46-C05, 46-C06, 46-C07, 46-C

## Schedule Basis
Item | Value | Basis
Planning schedule source | 00 31 13 Preliminary Project Phase, pp.21–22 | Read through the Contract & General Wiki note and Ledger rows (Verified); 00 31 13 is "for planning only and does not dictate means and methods" (p.21)
Notice to Proceed | 2023-03-15 | Pre-con Mar 15, 2023 (00 31 13); NTP Mar 15, 2023 (Appendix F Table 3-1)
Substantial Completion | 2024-07-26 | 00 31 13
Final Completion | 2024-10-16 | 00 31 13; 00 73 00 SC 15
Working days NTP → Substantial Completion (formula) | 358 | Mon–Fri, no holidays
Working days NTP → end of final paving, Aug 31, 2024 (formula) | 383 | Final surfacing and pavement August 2024 (00 31 13)
Working days NTP → Final Completion (formula) | 416
On-site work limit (SC 15) | 360 | 00 73 00 SC 15 p.91: on-site work limited to 360 working days (72 weeks) — per Contract & General Issues
Month-only dates | Start → first of month; finish → last of month | e.g. "Blower Building complete July 2023" plotted Jul 31, 2023
Inferred windows | Procurement, inspection spans, tests and start-ups, demolition, site finish, dewatering start, generator start | No dates in the documents; each activity states its basis
Ledger rows → activities | Each Ledger row sits in one activity: its CWP × the 00 31 13 work item for its Area/Building (or status: Temporary / Demolished) | Mapping Inferred; see "Row placement" sheet
Import | Schedule_by_CWP.csv has ID, dates and predecessors for P6 or MS Project import | Predecessor logic is Inferred (procurement → work → tests → milestone)

## Row placement
Ledger tag | CWP | Schedule activity | Window | Placed by
PROPOSED-Temporary bypass pumping system | CWP 01 | 01-C01 General Requirements & Temporary Works — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-Temporary power generator | CWP 26 | 26-C13 Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | Temporary back-up generator (rental) | temporary generator
PROPOSED-Plastic covering for slopes and stockpiles | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Catch basin inserts | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Filter fabric fence | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Stabilized construction entrance | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Geotextile encased check dams | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Existing 8in effluent outfall pipe | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Interim 8in HDPE effluent pipe | CWP 33 | 33-C02 Yard Piping & Utilities — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-Existing 4in roof drain pipe | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
SSMH 1286 | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
SSMH 1285 | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing 10in effluent outfall pipe | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing storm drain and catch basin 87 LF | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing 6in drain pipe to sump station | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing 1.5in sump force main | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing holding tanks | CWP 02 | 02-C03 Demolition & Existing Conditions — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Existing chain link fence 149 LF | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing storm drain at roof drain 7 ft | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing retaining wall 61 LF | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing generator fuel tank and spill basin | CWP 02 | 02-C01 Demolition & Existing Conditions — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
PROPOSED-Existing chain link fence 119 LF | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing 4in storm drain 8 LF | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Water line relocation at storm drain | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Existing 8in influent pipe | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Asphalt pavement sawcut and removal | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing 8in slab over pre-aeration basin | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing basin internal piping | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Off-site staging area | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
Pipe ID 1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 3 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 4 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 5 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 6 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 7 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 8 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 9 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 10 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 11 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 12 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 13 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 14 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 15 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 16 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 17 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 18 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 19 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 20 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 21 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 22 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 23 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 24 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Pipe ID 25 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
Pipe ID 26 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Existing Train 1 influent pipe | CWP 02 | 02-C03 Demolition & Existing Conditions — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Hot Box #1 | CWP 43 | 43-C05 Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Hot Box #2 | CWP 43 | 43-C05 Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 3 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 4 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 5 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 6 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 7 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 8 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 9 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 10 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 11 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 12 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
Buried Valve ID 13 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Existing slab coring and repair | CWP 03 | 03-C08 Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | area
SD-1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-4in roof drain at SD-1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #5 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #8 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #9 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #7 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #10 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #3 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #4 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB #6 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SDCB 1076 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-East trench drains | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-West trench drain | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Block retaining wall | CWP 32 | 32-C02 Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | Site finish work (fencing, walls, landscaping, bollards) | site finish
PROPOSED-Chain link fence 126 LF | CWP 32 | 32-C02 Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | Site finish work (fencing, walls, landscaping, bollards) | site finish
PROPOSED-New septic tank | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Floor drains | CWP 33 | 33-C04 Yard Piping & Utilities — Train 3 | Train 3 | area
PROPOSED-Parking stall striping | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-Gravity sewer cleanouts | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Tracer wire and locater boxes | CWP 31 | 31-C04 Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Concrete walkway | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-WWTP tank and building signs | CWP 10 | 10-C03 Specialties — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Buried valve label markers | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-HMA pavement | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-Gravel surfacing | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-Post hydrant | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Composite manholes, double manhole condition | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | CWP default (area not stated)
PROPOSED-Influent sample sump | CWP 31 | 31-C04 Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Hot Box #1 flow meter | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | site-wide electrical
PROPOSED-Hot Box #1 solenoid valve | CWP 43 | 43-C05 Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Train 2 flow meter vault | CWP 31 | 31-C01 Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Train 3 flow meter vault | CWP 31 | 31-C03 Earthwork, Dewatering & Erosion Control — Train 3 | Train 3 | area
PROPOSED-Train 2 flow meter | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Train 3 flow meter | CWP 26 | 26-C14 Electrical, Instrumentation & Controls — Train 3 | Train 3 | area
PROPOSED-Hydroseeded restoration areas | CWP 32 | 32-C02 Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | Site finish work (fencing, walls, landscaping, bollards) | site finish
PROPOSED-Temporary construction sign | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Dewatering system | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Compost berm | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Orange barrier fence | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary shoring and trench safety systems | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary cold-mix patches | CWP 32 | 32-C03 Paving, Fencing, Walls & Landscaping — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Retaining wall footing drain | CWP 32 | 32-C02 Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | Site finish work (fencing, walls, landscaping, bollards) | site finish
SDCB #1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SD-2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SD-3 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Asphalt wedge curb | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-Emergency access areas | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-4in roof drain connections (SD-2, SD-3) | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
INF1 | CWP 33 | 33-C03 Yard Piping & Utilities — Influent pump station and flow splitter | Influent pump station and flow splitter | area
INF2 | CWP 33 | 33-C03 Yard Piping & Utilities — Influent pump station and flow splitter | Influent pump station and flow splitter | area
INF3 | CWP 33 | 33-C03 Yard Piping & Utilities — Influent pump station and flow splitter | Influent pump station and flow splitter | area
SE1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SE2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
SE3 | CWP 33 | 33-C04 Yard Piping & Utilities — Train 3 | Train 3 | area
WAS1 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
WAS2 | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
WAS3 | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-IPS-DISCHARGE-TO-SPLITTER | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-EXISTING-INFLUENT-PIPING-REMOVAL | CWP 02 | 02-C02 Demolition & Existing Conditions — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-INFLUENT-FLOW-METER | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-TRAIN-2-FLOW-METER | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-TRAIN-3-FLOW-METER | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-EFFLUENT-FLOW-METER | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | site-wide electrical
PROPOSED-PLANT-DRAIN-FLOW-METER ¦ PROPOSED-Plant-Drain-Flow-Meter | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-2W-FLOW-METER | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-DIGESTED-SLUDGE-FLOW-METER | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
DO #1 ¦ DO-1 | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
DO #2 ¦ DO-2 | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-FLOW-SPLITTER-BOX | CWP 46 | 46-C02 Treatment Equipment — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-FLOW-SPLITTER-SUPPORT | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-INFLUENT-FLOW-METER-VAULT | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-TRAIN-2-FLOW-METER-VAULT | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-TRAIN-3-FLOW-METER-VAULT | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-TRAIN-3-TANK | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-INFLUENT-SAMPLE-SUMP | CWP 31 | 31-C01 Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-EFFLUENT-SAMPLE-SUMP | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-TRAIN-3-TREATMENT-SYSTEM | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-INNER-WALLS | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-CLARIFIER-MECHANISM | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-WALKWAYS-AND-LADDER | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-AERATION-DIFFUSERS | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-ANOXIC-MIXERS | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-DAVIT-CRANES | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-RAS-AIRLIFT | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-MLR-AIRLIFT | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-CARBON-FEED-PUMPS | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-CONTROL-PANEL | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-TRAIN-3-FRP-LAUNDER-COVER | CWP 10 | 10-C02 Specialties — Train 3 | Train 3 | area
PROPOSED-INFLUENT-PUMP-STATION-WET-WELL | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-INFLUENT-PUMPS-SMALL | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-INFLUENT-PUMPS-LARGE | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-IPS-LEVEL-TRANSDUCER | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
F1–F4 [Influent Pump Station] | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-IPS-VALVE-VAULTS | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-IPS-HATCHES | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-PLANT-DRAIN-LINE | CWP 46 | 46-C08 Treatment Equipment — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-STEP-INFLUENT-CONNECTION | CWP 33 | 33-C03 Yard Piping & Utilities — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-2W-PUMP-STATION-WET-WELL ¦ PROPOSED-2W-Pump-Station-Wet-Well | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-PUMPS | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
F1–F4 [2W Pump Station] | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-DIAPHRAGM-TANKS | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | keyword (area not stated)
PIT-620 | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-DISCHARGE-LINE | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-FILL-LINE | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-UV-DIGESTER-STRUCTURE | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-SYSTEM | CWP 46 | 46-C07 Treatment Equipment — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-CONTROL-PANELS | CWP 46 | 46-C07 Treatment Equipment — UV chamber and digester | UV chamber and digester | area
PROPOSED-EFFLUENT-HEADER-TO-UV | CWP 33 | 33-C05 Yard Piping & Utilities — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-CHAMBER-DRAIN | CWP 33 | 33-C05 Yard Piping & Utilities — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-DIGESTER-GRATING-GUARDRAIL | CWP 05 | 05-C02 Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | UV chamber and digester | area
PROPOSED-DIGESTER-TELESCOPING-VALVE | CWP 40 | 40-C01 Process Interconnections — UV chamber and digester | UV chamber and digester | area
PROPOSED-DIGESTER-DIFFUSERS | CWP 46 | 46-C07 Treatment Equipment — UV chamber and digester | UV chamber and digester | area
PROPOSED-DIGESTER-AIR-LINES | CWP 33 | 33-C05 Yard Piping & Utilities — UV chamber and digester | UV chamber and digester | area
PROPOSED-DIGESTED-SLUDGE-LINE | CWP 33 | 33-C05 Yard Piping & Utilities — UV chamber and digester | UV chamber and digester | area
PROPOSED-WAS-PUMP-DISCHARGE-TO-DIGESTER | CWP 33 | 33-C05 Yard Piping & Utilities — UV chamber and digester | UV chamber and digester | area
PROPOSED-FINAL-EFFLUENT-LINE | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
S1–S2 [Aerobic Digester] | CWP 26 | 26-C17 Electrical, Instrumentation & Controls — UV chamber and digester | UV chamber and digester | area
PROPOSED-ROTARY-FAN-PRESS | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-FLOCCULATOR | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-SLUDGE-MANIFOLD | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-CAKE-CHUTE | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-AIR-COMPRESSOR | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-CONTROL-PANEL | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-POLYMER-SYSTEM | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-SCREW-CONVEYOR | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-DIGESTED-SLUDGE-FEED-TO-PRESS | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-2W-SUPPLY-TO-PRESS | CWP 43 | 43-C03 Blowers & 2W Plant Water System — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-WAS-PUMP | CWP 22 | 22-C02 Plumbing & Process Pumps — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-SWING-SLUDGE-PUMP | CWP 22 | 22-C02 Plumbing & Process Pumps — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-DIGESTED-SLUDGE-PUMP | CWP 22 | 22-C02 Plumbing & Process Pumps — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-WAS-SOLENOID-VALVES | CWP 46 | 46-C03 Treatment Equipment — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-SLUDGE-MANIFOLD-PIPING | CWP 45 | 45-C03 Process Valves — Sludge pumps and valving | Sludge pumps and valving | area
ESWD WWTP – Aerobic Digester Blower | CWP 43 | 43-C04 Blowers & 2W Plant Water System — Aerobic digester | Aerobic digester | area
ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
PROPOSED-AERATION-AIR-HEADER | CWP 33 | 33-C01 Yard Piping & Utilities — Blower Building | Blower Building | area
PROPOSED-AIR-TO-TRAIN-3 | CWP 33 | 33-C01 Yard Piping & Utilities — Blower Building | Blower Building | area
PROPOSED-AIR-TO-TRAIN-1-STUB | CWP 33 | 33-C01 Yard Piping & Utilities — Blower Building | Blower Building | area
PROPOSED-AIR-TO-TRAIN-2-STUB | CWP 33 | 33-C01 Yard Piping & Utilities — Blower Building | Blower Building | area
PROPOSED-2W-BLADDER-TANK-SUPPLY | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | keyword (area not stated)
PROPOSED-BLOWER-BUILDING ¦ PROPOSED-Blower-Building | CWP 13 | 13-C01 Pre-Engineered Metal Building — Blower Building | Blower Building | area
PROPOSED-IPS-MOTOR-SAVER-RELAYS | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-SLUDGE-PUMP-LOCAL-PANELS | CWP 22 | 22-C02 Plumbing & Process Pumps — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-YARD-HYDRANTS | CWP 22 | 22-C04 Plumbing & Process Pumps — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-POST-HYDRANTS | CWP 22 | 22-C04 Plumbing & Process Pumps — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-EXTERIOR-SANITARY-DRAINS | CWP 22 | 22-C04 Plumbing & Process Pumps — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-BLOWER-BLDG-WALL-FANS | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-BLOWER-BLDG-MOTORIZED-LOUVER | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-BLOWER-BLDG-MANUAL-LOUVER | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-EXISTING-BLDG-WALL-FANS | CWP 23 | 23-C02 HVAC & Ventilation — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-EXISTING-BLDG-LOUVERS | CWP 23 | 23-C02 HVAC & Ventilation — Existing dewatering / treatment building | Existing dewatering / treatment building | area
Receiving Conveyor | CWP 41 | 41-C01 Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
Inclined Conveyor | CWP 41 | 41-C01 Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-2W-AIR-GAP-ENCLOSURE | CWP 43 | 43-C05 Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-EYE-WASH-STATIONS | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | CWP default (area not stated)
PROPOSED-IPS-CHECK-VALVES | CWP 45 | 45-C02 Process Valves — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-IPS-GATE-VALVES | CWP 45 | 45-C02 Process Valves — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-AIR-BUTTERFLY-VALVES | CWP 45 | 45-C01 Process Valves — Aerobic digester | Aerobic digester | area
PROPOSED-UV-INTENSITY-SENSORS | CWP 46 | 46-C07 Treatment Equipment — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-TRANSMISSIVITY-ANALYZER | CWP 46 | 46-C06 Treatment Equipment — UV chamber | UV chamber | keyword (area not stated)
PROPOSED-WAS-FLOW-METER | CWP 26 | 26-C11 Electrical, Instrumentation & Controls — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-RFP-POLYMER-FLOWMETER | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-RFP-INLET-PRESSURE-TRANSMITTER | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-Utility-Transformer-480V | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
P-SEC | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
PROPOSED-CT-Enclosure-and-Meter-Base | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
ATS | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
MDP | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
TS | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
GEN | CWP 26 | 26-C07 Electrical, Instrumentation & Controls — Permanent standby generator | Permanent standby generator | area + generator
P-TPS | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Service-Area-Grounding-Electrode-System | CWP 26 | 26-C07 Electrical, Instrumentation & Controls — Permanent standby generator | Permanent standby generator | area + generator
PROPOSED-Existing-Utility-Transformer-208V | CWP 26 | 26-C04 Electrical, Instrumentation & Controls — Existing service equipment removal | Existing service equipment removal | electrical demolition
GEN (E) | CWP 26 | 26-C03 Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers | CWP 13 | 13-C02 Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
SES (E) | CWP 26 | 26-C03 Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
ATS (E) | CWP 26 | 26-C03 Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
PROPOSED-Existing-CT-Enclosure-and-Meter | CWP 26 | 26-C04 Electrical, Instrumentation & Controls — Existing service equipment removal | Existing service equipment removal | electrical demolition
PROPOSED-Existing-Meter-Base-and-Wall-Raceway | CWP 26 | 26-C04 Electrical, Instrumentation & Controls — Existing service equipment removal | Existing service equipment removal | electrical demolition
PROPOSED-Existing-200A-Feeder-to-Panel-TPS | CWP 26 | 26-C04 Electrical, Instrumentation & Controls — Existing service equipment removal | Existing service equipment removal | electrical demolition
TPS | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Existing-208V-400A-Distribution-Panel | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Existing-Grounding-Electrode-System | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | area
BL-1 | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
BL-2 | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
BL-3 | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
BL-4 | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
DB | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
PROPOSED-DB-Local-Disconnect | CWP 26 | 26-C05 Electrical, Instrumentation & Controls — Aerobic digester | Aerobic digester | keyword (area not stated)
MCC | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
MCP | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
LP-1 | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Power-Handholes | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Control-Signal-Handholes | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Smoke-Heat-Detector | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Door-Intrusion-Switch | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-2W-Pressure-Transducer | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-High-Temperature-Switches | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Grounding-Electrode-System | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
EF-1 | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
EF-2 | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
ML-1 | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Manual-Louver | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
L1 (Blower Building) | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
L2 (Blower Building) | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
X1 (Blower Building) | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Ventilation-Control-Panel | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
TCP-3 | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-Clarifier-Drive-Motor | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-Submersible-Mixer-A | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-Submersible-Mixer-B | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-Local-Disconnects | CWP 26 | 26-C14 Electrical, Instrumentation & Controls — Train 3 | Train 3 | area
PROPOSED-Train-3-Pole-Light | CWP 26 | 26-C14 Electrical, Instrumentation & Controls — Train 3 | Train 3 | area
PROPOSED-SCADA-Computer-System | CWP 26 | 26-C09 Electrical, Instrumentation & Controls — SCADA / PLC programming | SCADA / PLC programming | area
IP-1 | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
IP-2 | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
IP-3 | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
IP-4 | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
F1 (Influent Pump Station) | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
F2 (Influent Pump Station) | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
F3 (Influent Pump Station) | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
F4 (Influent Pump Station) | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
LT (Influent Pump Station) | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
IPS | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
T3 | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
LP2 | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Pump-Local-Disconnects | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Wet-Well-Power-Handhole | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Wet-Well-Instrument-Handhole | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Treatment-Building-Power-Handhole | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Treatment-Building-Control-Signal-Handhole | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Influent-Flow-Meter | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Plant-2-Flow-Meter | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Plant-3-Flow-Meter | CWP 26 | 26-C08 Electrical, Instrumentation & Controls — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-WAS-Dewatering-Flow-Meter | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Effluent-Flow-Meter | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-Effluent-Flow-Meter-Transmitter-Panel | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-2W-Flow-Meter | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
PROPOSED-Train-1-Flow-Meter | CWP 26 | 26-C06 Electrical, Instrumentation & Controls — Future provisions — not scheduled | Future provisions — not scheduled | marked future
DW-1 | CWP 46 | 46-C05 Treatment Equipment — Existing dewatering / treatment building | Existing dewatering / treatment building | area
WP-1 | CWP 22 | 22-C03 Plumbing & Process Pumps — Existing dewatering / treatment building | Existing dewatering / treatment building | area
WP-2 | CWP 22 | 22-C03 Plumbing & Process Pumps — Existing dewatering / treatment building | Existing dewatering / treatment building | area
SD-1 | CWP 22 | 22-C03 Plumbing & Process Pumps — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-WAS-and-Sludge-Pump-Local-Disconnects | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-WAS-Solenoid-Valves | CWP 46 | 46-C05 Treatment Equipment — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Polymer-Feed-Pump | CWP 46 | 46-C05 Treatment Equipment — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Hypochlorite-Feed-Pump | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | CWP default (area not stated)
PROPOSED-Influent-Sampler | CWP 46 | 46-C02 Treatment Equipment — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Effluent-Sampler | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | CWP default (area not stated)
EF-3 | CWP 23 | 23-C02 HVAC & Ventilation — Existing dewatering / treatment building | Existing dewatering / treatment building | area
EF-4 | CWP 23 | 23-C02 HVAC & Ventilation — Existing dewatering / treatment building | Existing dewatering / treatment building | area
EF-5 | CWP 23 | 23-C02 HVAC & Ventilation — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Treatment-Building-Ventilation-Control-Panel | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Methane-Sensor | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-H2S-Sensor | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Gas-Alarm-Light-and-Horn | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
L2 (Treatment Building) | CWP 26 | 26-C15 Electrical, Instrumentation & Controls — Existing dewatering / treatment building | Existing dewatering / treatment building | area
2W-P1 | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
2W-P2 | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
LSH-111 | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
F2 (2W Pump Station) | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
F3 (2W Pump Station) | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
LSL-111 | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-Pump-Local-Disconnects | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
PROPOSED-Hot-Box-1 | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-Hot-Box-2 | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-Hot-Box-Heat-Trace | CWP 26 | 26-C01 Electrical, Instrumentation & Controls — 2W air gap water system | 2W air gap water system | area
PROPOSED-2W-Isolation-Valve-Solenoid | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
UV1 | CWP 46 | 46-C06 Treatment Equipment — UV chamber | UV chamber | area
UV2 | CWP 46 | 46-C06 Treatment Equipment — UV chamber | UV chamber | area
PROPOSED-UV-Control-Panel-1 | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-UV-Control-Panel-2 | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-UV-Power-Distribution-1 | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-UV-Power-Distribution-2 | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
PROPOSED-Digester-Level-Transducer | CWP 26 | 26-C05 Electrical, Instrumentation & Controls — Aerobic digester | Aerobic digester | area
PROPOSED-UV-Area-Pole-Light | CWP 26 | 26-C16 Electrical, Instrumentation & Controls — UV chamber | UV chamber | area
T2 | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-VFDs-in-MCC | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
TCP-1 | CWP 26 | 26-C06 Electrical, Instrumentation & Controls — Future provisions — not scheduled | Future provisions — not scheduled | marked future
TCP-2 | CWP 26 | 26-C06 Electrical, Instrumentation & Controls — Future provisions — not scheduled | Future provisions — not scheduled | marked future
PROPOSED-Conduit-and-Conductor-Runs | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | site-wide electrical
PROPOSED-Blower-PTC-Relay-Modules | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Influent-Pump-Seal-Fail-Overtemp-Relays | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Temporary-Backup-Generator | CWP 26 | 26-C13 Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | Temporary back-up generator (rental) | temporary generator
PROPOSED-Construction-Power-Service | CWP 26 | 26-C12 Electrical, Instrumentation & Controls — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Electrical-Equipment-Housekeeping-Pads | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-Blower-Building-Slab-and-Grade-Beams | CWP 03 | 03-C02 Concrete (Cast-in-Place & Precast) — Blower Building | Blower Building | area
PROPOSED-Blower-Pad | CWP 03 | 03-C02 Concrete (Cast-in-Place & Precast) — Blower Building | Blower Building | area
PROPOSED-Blowers-Blower-Building | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
PROPOSED-2W-Bladder-Tank-Assembly | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
PROPOSED-Louver-36x84-Motorized | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-Louver-24x24-Manual | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-Exhaust-Fans-Blower-Building | CWP 23 | 23-C01 HVAC & Ventilation — Blower Building | Blower Building | area
PROPOSED-Fire-Extinguishers-Blower-Building | CWP 10 | 10-C01 Specialties — Blower Building | Blower Building | area
101A | CWP 08 | 08-C01 Doors, Frames & Hardware — Blower Building | Blower Building | area
101B | CWP 08 | 08-C01 Doors, Frames & Hardware — Blower Building | Blower Building | area
101C | CWP 08 | 08-C01 Doors, Frames & Hardware — Blower Building | Blower Building | area
PROPOSED-Existing-Office-Louver-4x4 | CWP 13 | 13-C03 Pre-Engineered Metal Building — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing-Office-Louver-2x3 | CWP 13 | 13-C03 Pre-Engineered Metal Building — Site demolition ahead of new work | Site demolition ahead of new work | site demolition
PROPOSED-Existing-Generator-Exhaust-Assembly | CWP 13 | 13-C02 Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | Existing generator, switchgear and fuel tank removal | demolition after new generator
PROPOSED-WWTP-Building-Louver-3x7 | CWP 13 | 13-C04 Pre-Engineered Metal Building — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-WWTP-Building-Exhaust-Fan-24x24 | CWP 13 | 13-C04 Pre-Engineered Metal Building — Existing dewatering / treatment building | Existing dewatering / treatment building | area
PROPOSED-Train-3-Concrete-Tank | CWP 03 | 03-C06 Concrete (Cast-in-Place & Precast) — Train 3 | Train 3 | area
PROPOSED-Train-3-Guardrail-and-Ladders | CWP 05 | 05-C01 Metals (Grating, Railings, Ladders, Stairs) — Train 3 | Train 3 | area
PROPOSED-Blower-Building-Foundation-Drains | CWP 33 | 33-C01 Yard Piping & Utilities — Blower Building | Blower Building | area
PROPOSED-UV-Disinfection-Chamber-Basin | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-Digester-Concrete-Tank | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-Digester-Grating-Beam | CWP 05 | 05-C02 Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-Digester-Grating | CWP 05 | 05-C02 Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-Digester-Guardrail-and-Ladders | CWP 05 | 05-C02 Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | UV chamber and digester | area
PROPOSED-Drain-Pump-Station-Lid | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Drain-Pump-Station-Precast-Wet-Well | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Drain-Pump-Station-Hatches | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Generator-Slab | CWP 03 | 03-C03 Concrete (Cast-in-Place & Precast) — Permanent standby generator | Permanent standby generator | area
PROPOSED-Generator-on-S2.4 | CWP 26 | 26-C07 Electrical, Instrumentation & Controls — Permanent standby generator | Permanent standby generator | area
PROPOSED-Flow-Splitter-Pad | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Flow-Splitter | CWP 46 | 46-C02 Treatment Equipment — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Existing-Slab-Trench-Infill | CWP 03 | 03-C05 Concrete (Cast-in-Place & Precast) — Sludge pumps and valving | Sludge pumps and valving | keyword (area not stated)
PROPOSED-2W-Pump-Station-Precast-Wet-Well | CWP 03 | 03-C01 Concrete (Cast-in-Place & Precast) — 2W air gap water system | 2W air gap water system | area
PROPOSED-Influent-Pump-Station-Precast-Wet-Well | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Pump-Station-Top-Slab | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Flow-Meter-Valve-Vault | CWP 03 | 03-C08 Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Effluent-Flow-Meter-Valve-Vault | CWP 03 | 03-C08 Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Plants-2-and-3-Flow-Meter-Vault | CWP 03 | 03-C08 Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Influent-Pump-Station-Meter-Vaults | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Steel-Stairs-Ladders-Platforms | CWP 05 | 05-C01 Metals (Grating, Railings, Ladders, Stairs) — Train 3 | Train 3 | CWP default (area not stated)
PROPOSED-Boot-Brush-and-Pad | CWP 08 | 08-C01 Doors, Frames & Hardware — Blower Building | Blower Building | area
PROPOSED-Influent-Pump-Station-Interior-Coating | CWP 09 | 09-C01 Painting & Coatings — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Bollards | CWP 32 | 32-C02 Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | Site finish work (fencing, walls, landscaping, bollards) | site finish
PROPOSED-Trench-Safety-System | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Erosion-and-Sediment-Control-Measures | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Bypass-Pipe | CWP 01 | 01-C01 General Requirements & Temporary Works — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-Temporary-8in-Effluent-Piping | CWP 33 | 33-C02 Yard Piping & Utilities — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-8in-Effluent-Piping | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-8in-Effluent-Flow-Meter | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | CWP default (area not stated)
PROPOSED-Aerobic-Digester | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-Disinfection-Chamber | CWP 03 | 03-C07 Concrete (Cast-in-Place & Precast) — UV chamber and digester | UV chamber and digester | area
PROPOSED-UV-Disinfection-System | CWP 46 | 46-C07 Treatment Equipment — UV chamber and digester | UV chamber and digester | area
PROPOSED-Sludge-Pumps | CWP 22 | 22-C02 Plumbing & Process Pumps — Sludge pumps and valving | Sludge pumps and valving | area
PROPOSED-Yard-Piping | CWP 33 | 33-C06 Yard Piping & Utilities — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-Yard-Piping-Vaults | CWP 03 | 03-C08 Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | Yard piping, vaults and site utilities | site
PROPOSED-2W-Air-Gap-Water-System | CWP 43 | 43-C01 Blowers & 2W Plant Water System — 2W air gap water system | 2W air gap water system | area
PROPOSED-Influent-Pump-Station | CWP 03 | 03-C04 Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Submersible-Pump-Equipment | CWP 22 | 22-C01 Plumbing & Process Pumps — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Flow-Splitter | CWP 46 | 46-C02 Treatment Equipment — Influent pump station and flow splitter | Influent pump station and flow splitter | area
PROPOSED-Influent-Sampler | CWP 46 | 46-C02 Treatment Equipment — Influent pump station and flow splitter | Influent pump station and flow splitter | keyword (area not stated)
PROPOSED-Train-3 | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-Biological-Treatment-Equipment | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Temporary-Back-Up-Generator | CWP 26 | 26-C13 Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | Temporary back-up generator (rental) | temporary generator
PROPOSED-Automatic-Transfer-Switch | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | CWP default (area not stated)
PROPOSED-Permanent-Standby-Generator | CWP 26 | 26-C07 Electrical, Instrumentation & Controls — Permanent standby generator | Permanent standby generator | keyword (area not stated)
PROPOSED-480V-Electrical-Service | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | CWP default (area not stated)
PROPOSED-Motor-Control-Center | CWP 26 | 26-C02 Electrical, Instrumentation & Controls — Blower Building | Blower Building | area
PROPOSED-PLC-Control-Panel | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | CWP default (area not stated)
PROPOSED-Dewatering-System | CWP 46 | 46-C01 Treatment Equipment — Sludge dewatering (rotary fan press) | Sludge dewatering (rotary fan press) | area
PROPOSED-Site-Final-Surfacing-and-Pavement | CWP 32 | 32-C01 Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | Final surfacing and pavement | paving
PROPOSED-Funding-Recognition-Sign | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Barriers | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Pump-and-Process-Equipment | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Bypass-Pumping-System | CWP 01 | 01-C01 General Requirements & Temporary Works — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-Temporary-Construction-Dewatering | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Excavation-Support | CWP 31 | 31-C02 Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Contractor-Field-Office | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Construction-Power | CWP 26 | 26-C12 Electrical, Instrumentation & Controls — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Construction-Water-Connection | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Sanitary-Facilities | CWP 01 | 01-C02 General Requirements & Temporary Works — Temporary facilities and controls | Temporary facilities and controls | temporary
PROPOSED-Temporary-Bypass-Alarm-Monitoring | CWP 01 | 01-C01 General Requirements & Temporary Works — Temporary bypass and interim effluent piping | Temporary bypass and interim effluent piping | temporary bypass
PROPOSED-Aeration-Basins | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Anoxic-Basins | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Clarifier | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Blowers | CWP 43 | 43-C02 Blowers & 2W Plant Water System — Blower Building | Blower Building | area
PROPOSED-Train-3-Dissolved-Oxygen-Sensors | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Train-3-pH-Sensors | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | area
PROPOSED-Magnetic-Flow-Meters | CWP 26 | 26-C10 Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 480V service, MCC and PLC panel | CWP default (area not stated)
PROPOSED-Handrails | CWP 46 | 46-C04 Treatment Equipment — Train 3 | Train 3 | CWP default (area not stated)