## Summary
Drawing Controls Register — Eastsound WWTP Upgrade Phase I
97 sheets: the 96 on the cover index plus C1.6A (issued by Add. 4), and one referenced sheet that does not exist (C8.1). Titles, availability, Add. 4 status and read methods come from 01 rev1; findings from the lane Issues files; the four resplit images were crawled in the Civil & Site resplit pass.
Measure | Count (formula)
Sheets in the register (97 + C8.1 reference) | 98
Available in the drawing files | 87
Resplit image in Project files — crawled | 4
Missing — not in the library | 6
Reissued by Add. 4 | 6
Issued by Add. 4 (new sheet) | 1
Cited by an Add. 4 clarification only | 3
Title differs from cover index — substantive | 1
Title differs — wording | 5
Title differs — cosmetic | 2
Values unreadable or low-confidence at stored resolution | 10
Read-method index fixes (no rescan) | 16
Sheets needing a rescan or better copy | 10
Sheets needing upload from the source set | 6

## Register
Set p. | Sheet | Title (title block) | Cover-index title | Title check | Discipline | Lane | File | PDF p. | Availability | Addendum 4 | Read method (01) | Read-method finding | Legibility (about 80 dpi) | Other controls notes | Ledger rows citing it | Exceptions citing it | Action | Tag
1 | G0.1 | COVER SHEET | Same as title block | Match | General | Civil & Site (adj.) | plans_1.pdf | 1 | Available | — | Text |  |  |  | 0 |  | None | Verified
2 | G0.2 | LEGEND AND ABBREVIATIONS - CIVIL & ARCHITECTURAL | LEGEND & ABBREVIATIONS - CIVIL & ARCHITECTURAL | Cosmetic (& vs and) | General | Civil & Site (adj.) | plans_1.pdf | 2 | Available | — | Text | Flagged Text, needs a visual pass: Legends are graphics only (Civil & Site design gap) |  | Title differs from the cover index (01 log #7) | 0 |  | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
3 | G0.3 | NOTES & SPECIFICATIONS | Same as title block | Match | General | Civil & Site (adj.) | plans_1.pdf | 3 | Available | — | Text |  |  |  | 3 | #14, #68, #70, #142, #154, #259 | None | Verified
4 | G0.4 | W.A.C. 332-130 COMPLIANCE SHEET | Same as title block | Match | General | Civil & Site (adj.) | plans_1.pdf | 4 | Available | — | Text |  |  |  | 0 |  | None | Verified
5 | G0.5 | PROCESS SCHEMATIC | Same as title block | Match | General | Process & Mechanical (adj.) | plans_1.pdf | 5 | Available | — | Visual |  | Revision triangle number reads 6 — Process & Mechanical note for G0.5 |  | 38 | #4, #7, #8, #9, #10, #29, #30, #37, #54, #56, #59, #60 … | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
6 | G0.6 | HYDRAULIC PROFILE | Same as title block | Match | General | Process & Mechanical (adj.) | plans_1.pdf | 6 | Available | — | Visual |  |  |  | 20 | #4, #7, #8, #9, #10, #29, #30, #37, #54, #56, #59, #60 … | None | Verified
7 | G0.7 | DESIGN CRITERIA | Same as title block | Match | General | Process & Mechanical (adj.) | plans_1.pdf | 7 | Available | — | Text |  |  |  | 22 | #7, #8, #9, #10, #11, #29, #30, #32, #36, #45, #54, #59 … | None | Verified
8 | C0.1 | EXISTING CONDITIONS | Same as title block | Match | Civil | Civil & Site | plans_1.pdf | 8 | Available | — | Visual (rev1) |  | Low-confidence read: second easement number (Civil & Site Known Issues K-03) |  | 4 | #28 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
9 | C0.2 | T.E.S.C. NARRATIVE | Same as title block | Match | Civil | Civil & Site | plans_2Part-1.pdf | 1 | Available | — | Visual |  |  |  | 6 | #15, #69, #71 | None | Verified
10 | C0.3 | T.E.S.C. PLAN (cover index) | Same as title block | Resplit title block reads "T.E.S.C. PLAN" | Civil | Civil & Site | not in library | — | Not in the drawing files; resplit image in Project files (Missing_Pages_Page_001.png), page 10 of 96 — crawled in the Civil & Site resplit pass | — | Set on upload |  |  |  | 7 | #71 | None | Verified-Visual
11 | C0.4 | T.E.S.C. DETAILS | Same as title block | Match | Civil | Civil & Site | plans_2Part-3.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 6 | #71 | None | Verified
12 | C0.5 | DEMOLITION PLAN | Same as title block | Match | Civil | Civil & Site | plans_2Part-4.pdf | 1 | Available | Cited — Add. 4 p.1, Clarification 1 | Visual |  | Low-confidence read: SSMH 1286 label under the X (Civil & Site Known Issues K-03) |  | 24 | #28, #68, #74, #77, #143, #144, #147, #150, #151, #163 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
13 | C0.6 | STAGING PLAN | Same as title block | Match | Civil | Civil & Site | plans_2Part-5.pdf | 1 | Available | — | Visual |  |  |  | 2 | #71 | None | Verified
14 | C0.7 | WWTP INTERIM PLAN OF OPERATION (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 2 | #74 | Get the sheet from the source set (upload) | Unresolved
15 | C1.1 | SITE PIPING PLAN WITH GENERAL NOTES (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 0 | #53, #231 | Get the sheet from the source set (upload) | Unresolved
16 | C1.2 | SITE DIMENSIONAL PLAN (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 0 |  | Get the sheet from the source set (upload) | Unresolved
17 | C1.3 | SITE PIPING PLAN WITH PIPING ID | Same as title block | Match | Civil | Civil & Site | plans_3Part-1.pdf | 1 | Available | Reissued — Add. 4 p.7 governs | Text | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) |  | Reissue keeps the base title block (01 log #12) | 30 | #4, #16, #17, #50, #51, #52, #79, #80, #81, #82, #83, #84 … | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
18 | C1.4 | SITE PIPING PLAN WITH BURIED VALVE ID | Same as title block | Match | Civil | Civil & Site | plans_3Part-2.pdf | 1 | Available | — | Text | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) |  |  | 15 | #4, #99, #177 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
19 | C1.5 | SITE PIPING PLAN WITH PIPE ELEVATIONS | Same as title block | Match | Civil | Civil & Site | plans_3Part-3.pdf | 1 | Available | — | Text | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) |  |  | 0 |  | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
20 | C2.1 | GRADING & STORM DRAINAGE PLAN (cover index) | Same as title block | Resplit title block reads "GRADING & STORM DRAINAGE PLAN" | Civil | Civil & Site | not in library | — | Not in the drawing files; resplit image in Project files (Missing_Pages_Page_002.png), page 20 of 96 — crawled in the Civil & Site resplit pass | — | Set on upload |  |  |  | 18 |  | None | Verified-Visual
21 | C2.2 | STORM DRAINAGE PLAN & PROFILE | Same as title block | Match | Civil | Civil & Site | plans_3Part-5.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 6 | #3 | None | Verified
22 | C2.3 | STORM DRAINAGE PLAN & PROFILES (cover index) | Same as title block | Resplit title block reads "STORM DRAINAGE PLAN & PROFILES" | Civil | Civil & Site | not in library | — | Not in the drawing files; resplit image in Project files (Missing_Pages_Page_003.png), page 22 of 96 — crawled in the Civil & Site resplit pass | — | Set on upload |  |  |  | 11 |  | None | Verified-Visual
23 | C2.4 | STORM DRAINAGE PLAN & PROFILES | Same as title block | Match | Civil | Civil & Site | plans_3Part-7.pdf | 1 | Available | — | Text | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) |  |  | 10 |  | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
24 | C2.5 | RETAINING WALL PLAN & PROFILE | Same as title block | Match | Civil | Civil & Site | plans_3Part-8.pdf | 1 | Available | — | Visual |  | Fence height in Keyed Note 4 reads 6" — Civil & Site CS-12 |  | 3 | #147 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
25 | C2.6 | PAVING PLAN (cover index) | Same as title block | Resplit title block reads "PAVING PLAN" | Civil | Civil & Site | not in library | — | Not in the drawing files; resplit image in Project files (Missing_Pages_Page_004.png), page 25 of 96 — crawled in the Civil & Site resplit pass | Cited — Add. 4 p.1, Clarification 1 | Set on upload |  |  |  | 5 | #73, #96, #97, #131 | None | Verified-Visual
26 | C3.1 | INFLUENT FLOW SPLITTER SITE PLAN | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-2.pdf | 1 | Available | — | Visual |  |  |  | 15 | #5, #6, #7, #8, #9, #44, #75, #76, #77, #79, #80, #81 … | None | Verified
27 | C3.2 | INFLUENT FLOW SPLITTER ELEVATIONS | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-3.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 6 | #75, #76, #79, #80, #81, #86, #103, #144, #157, #160, #237 | None | Verified
28 | C3.3 | TRAIN 3 PLAN | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-4.pdf | 1 | Available | — | Visual |  |  |  | 16 | #1, #2, #29, #30, #32, #33, #34, #35, #81, #84, #85, #93 … | None | Verified-Visual
29 | C3.4 | TRAIN 3 SECTION A | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-5.pdf | 1 | Available | — | Visual |  |  |  | 10 | #29, #30, #32, #33, #34, #85 | None | Verified-Visual
30 | C3.5 | TRAIN 3 SECTION B | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-6.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 11 | #29, #30, #33, #34, #81, #84, #93, #232 | None | Verified
31 | C4.1 | INFLUENT PUMP STATION | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-7.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 13 | #4, #36, #37, #38, #39, #40, #41, #86, #87, #89, #130, #166 … | None | Verified
32 | C4.2 | 2W PUMP STATION PLAN & PROFILE | Same as title block | Match | Civil | Process & Mechanical | plans_4Part-8.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 5 | #45, #46, #47, #50, #168, #169, #183, #222, #240 | None | Verified
33 | C4.3 | 2W EQUIPMENT LAYOUT | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 1 | Available | — | Visual (rev1) |  |  |  | 2 | #25, #48, #183, #227 | None | Verified
34 | C5.1 | UV DISINFECTION CHAMBER & DIGESTER PLAN | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 2 | Available | — | Text | Flagged Text, needs a visual pass: Content is image-only (Process & Mechanical log) |  |  | 13 | #54, #55, #56, #57, #88, #89, #90, #91, #94, #104, #105, #166 … | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
35 | C5.2 | UV DISINFECTION CHAMBER & DIGESTER SECTION "A" | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 3 | Available | — | Visual (rev1) |  |  |  | 10 | #54, #55, #56, #57, #88, #92, #94, #104, #105 | None | Verified
36 | C5.3 | UV DISINFECTION CHAMBER & DIGESTER SECTION "B" | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 4 | Available | — | Visual (rev1) |  |  |  | 15 | #54, #55, #56, #57, #58, #88, #89, #90, #91, #92, #94, #104 … | None | Verified
37 | C5.4 | UV DISINFECTION EQUIPMENT | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 5 | Available | — | Visual (rev1) |  | UV module callout "4-64" and "6 required / bank" not fully legible — Process & Mechanical Issue 13 |  | 2 | #54, #55, #234 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
38 | C6.1 | ROTARY FAN PRESS SYSTEM | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 6 | Available | — | Visual (rev1) |  |  |  | 11 | #63, #64, #89, #106, #191 | None | Verified
39 | C6.2 | SLUDGE PUMP AND VALVING AREA | SLUDGE PUMP & VALVING AREA | Cosmetic (& vs and) | Civil | Process & Mechanical | plans_5.pdf | 7 | Available | — | Visual (rev1) |  |  | Title differs from the cover index (01 log #8) | 13 | #12, #43, #59, #60, #61, #85, #90, #91, #101, #102, #106, #107 … | None | Verified
40 | C6.3 | DIGESTER BLOWER | Same as title block | Match | Civil | Process & Mechanical | plans_5.pdf | 8 | Available | — | Visual (rev1) |  |  |  | 4 | #19, #50, #94, #173, #185, #202 | None | Verified
41 | C6.4 | BIOLOGICAL TREATMENT BLOWERS | Same as title block | Match | Civil | Process & Mechanical | plans_6.pdf | 1 | Available | Reissued — Add. 4 p.6 governs | Visual |  |  | Reissue keeps the base title block (01 log #12) | 8 | #18, #19, #25, #50, #51, #93, #146, #185, #202, #224, #227, #231 … | None | Verified
42 | C6.5 | BIOLOGICAL TREATMENT BLOWER ELEVATION | Same as title block | Match | Civil | Process & Mechanical | plans_6.pdf | 2 | Available | — | Visual |  |  |  | 7 | #18, #93, #108, #109, #202, #224, #231, #233 | None | Verified
43 | C7.1 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 3 | Available | — | Visual (rev1) |  |  |  | 7 | #4, #52, #96 | None | Verified
44 | C7.2 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 4 | Available | — | Text |  |  |  | 1 | #97, #160, #168 | None | Verified
45 | C7.3 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 5 | Available | — | Visual |  |  |  | 17 | #73, #98, #99, #177 | None | Verified-Visual
46 | C7.4 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 6 | Available | — | Visual (rev1) |  |  | Duplicate copy at plans_7 pp.1–3; the plans_6 copy is indexed (01) | 6 | #73, #97, #148, #152, #160, #173, #240 | None | Verified
47 | C7.5 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 7 | Available | — | Text |  |  | Duplicate copy at plans_7 pp.1–3; the plans_6 copy is indexed (01) | 4 | #4, #52, #53, #168 | None | Verified
48 | C7.6 | CIVIL DETAILS | Same as title block | Match | Civil | Civil & Site | plans_6.pdf | 8 | Available | — | Visual (rev1) |  |  | Duplicate copy at plans_7 pp.1–3; the plans_6 copy is indexed (01) | 4 | #11, #16, #17, #49, #95, #100, #149 | None | Verified
49 | C7.7 | CIVIL DETAILS (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 0 |  | Get the sheet from the source set (upload) | Unresolved
50 | C7.8 | CIVIL DETAILS (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 0 |  | Get the sheet from the source set (upload) | Unresolved
51 | C7.9 | FLOW METER & VALVE VAULT DETAILS (cover index) | Same as title block | Not checked (sheet missing) | Civil | Civil & Site | not in library | — | Missing — not in the library | — | Set on upload |  |  |  | 0 | #44, #156 | Get the sheet from the source set (upload) | Unresolved
52 | C7.10 | FLOW METER & VALVE VAULT DETAILS | Same as title block | Match | Civil | Civil & Site | plans_7.pdf | 4 | Available | — | Visual (rev1) |  |  |  | 8 | #5, #6, #7, #8, #81, #149, #156 | None | Verified
53 | A1.1 | BLOWER BUILDING PLAN | Same as title block | Match | Architectural | Structural & Building | plans_7.pdf | 5 | Available | Reissued — Add. 4 p.4 governs | Visual (rev1) |  | Door 101B height illegible in the door schedule (same on the Add. 4 p.4 reissue) — Structural & Building Issues §2 #1 | Add. 4 p.4 reissue shows no new revision entry | 14 | #18, #20, #21, #22, #23, #24, #25, #145, #146, #170, #175, #195 … | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
54 | A1.2 | BLOWER BUILDING EXTERIOR ELEVATIONS 1 | Same as title block | Match | Architectural | Structural & Building | plans_7.pdf | 6 | Available | Reissued — Add. 4 p.5 governs | Visual (rev1) |  |  | Add. 4 p.5 reissue shows no new revision entry | 8 | #20, #21, #22, #145, #146, #170, #175, #217, #228 | None | Verified
55 | A1.3 | BUILDING DETAILS | Same as title block | Match | Architectural | Structural & Building | plans_7.pdf | 7 | Available | — | Text |  |  |  | 8 | #18, #26, #27, #28, #200, #224, #229, #230, #231 | None | Verified
56 | S1.1 | STRUCTURAL NOTES | Same as title block | Match | Structural | Structural & Building | plans_7.pdf | 8 | Available | — | Visual |  |  | Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 9 | #29, #56, #222, #256 | None | Verified-Visual
57 | S2.1 | TRAIN 3 PLANS & SECTION | Same as title block | Match | Structural | Structural & Building | plans_8.pdf | 1 | Available | — | Visual |  |  | Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 2 | #29, #34, #158, #232 | None | Verified-Visual
58 | S2.2 | UV DISINFECTION CHAMBER & DIGESTER PLAN & SECTIONS | UV DISINFECTION & DIGESTER PLAN & SECTIONS | Wording differs | Structural | Structural & Building | plans_8.pdf | 2 | Available | — | Visual |  | Low-confidence read: mat slab spacing (#6 @ 10" vs @ 12") — confirm on the native sheet before any RFI (Structural & Building Known Issues 1) | Title differs from the cover index (01 log #2); Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 5 | #56, #57, #166, #220, #234 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
59 | S2.3 | BLOWER BUILDING FOUNDATION PLAN & DETAILS | Same as title block | Match | Structural | Structural & Building | plans_8.pdf | 3 | Available | Reissued — Add. 4 p.9 governs | Visual |  | Perimeter grade beam bar size illegible on the base sheet and the Add. 4 p.9 reissue — Structural & Building Issues §2 #6 | Add. 4 p.9 revision block shows revision 3 "Blower Building" TH 2/8/23 (Structural & Building, Verified-Visual); Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 4 | #128, #145, #170, #185, #217, #233, #239 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
60 | S2.4 | PUMP STATION LID, GENERATOR PAD, & FLOW SPLITTER PAD | Same as title block | Match | Structural | Structural & Building | plans_8.pdf | 4 | Available | — | Visual |  | Low-confidence read: hatch openings and thickened-edge depth — confirm on the native sheet before any RFI (Structural & Building Known Issues 1) | Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 7 | #37, #38, #65, #75, #76, #103, #151, #157, #166, #201, #222, #223 … | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
61 | S4.1 | TYP STRUCTURAL DETAILS | Same as title block | Match | Structural | Structural & Building | plans_8.pdf | 5 | Available | Reissued — Add. 4 p.10 governs; Detail 8 cited p.3 | Visual |  |  | Add. 4 p.10 revision block shows revision 3 "Blower Building" TH 2/8/23 (Structural & Building, Verified-Visual); Page total reads "OF 98" at stored resolution; all other sheets read 96 (01 log #10, low priority) | 5 | #29, #56, #78, #217, #238 | None | Verified-Visual
62 | E0.1 | ELECTRICAL SYMBOLS AND ABBREVIATIONS | Same as title block | Match | Electrical | Electrical & Controls | plans_8.pdf | 6 | Available | — | Text |  |  |  | 0 | #258 | None | Verified
63 | E0.2 | ELECTRICAL DEMOLITION SITE PLAN AND ONE LINE DIAGRAM | Same as title block | Match | Electrical | Electrical & Controls | plans_8.pdf | 7 | Available | — | Text |  |  |  | 14 | #28, #194, #200 | None | Verified
64 | E0.3 | OVERALL ELECTRICAL SITE PLAN | Same as title block | Match | Electrical | Electrical & Controls | plans_8.pdf | 8 | Available | — | Text |  |  |  | 1 |  | None | Verified
65 | E0.4 | AREA CLASSIFICATION SITE PLAN | AREA CLASSIFICATION PLAN | Wording differs | Electrical | Electrical & Controls | plans_9.pdf | 1 | Available | — | Text |  |  | Title differs from the cover index (01 log #3); E0.1 sheet index matches the cover index (Electrical & Controls, Verified) | 0 | #194, #196, #205 | None | Verified
66 | E1.1 | ELECTRIC SERVICE AREA PLAN | ELECTRICAL SERVICE AREA PLAN | Wording differs | Electrical | Electrical & Controls | plans_9.pdf | 2 | Available | — | Text | Flagged Text, needs a visual pass: Text layer mis-associates tags (TS reads as a transfer switch; it is the transformer) (Electrical & Controls log) |  | Title differs from the cover index (01 log #4); E0.1 sheet index matches the cover index (Electrical & Controls, Verified) | 15 | #23, #65, #66, #201, #223 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
67 | E2.1 | BLOWER BUILDING POWER, CONTROL AND GROUNDING PLAN | Same as title block | Match | Electrical | Electrical & Controls | plans_9.pdf | 3 | Available | — | Text |  |  |  | 16 | #18, #19, #23, #24, #48, #118, #199, #202, #213 | None | Verified
68 | E2.2 | BLOWER BUILDING LIGHTING AND HVAC PLAN | Same as title block | Match | Electrical | Electrical & Controls | plans_9.pdf | 4 | Available | — | Text |  | Light fixture L1 catalog number not legible (L1 (Blower Building)) — Electrical & Controls Ledger |  | 13 | #20, #21, #22, #23, #24, #119, #121, #123, #192, #199, #203 | Higher-resolution copy (native PDF) for the unreadable value | Unresolved
69 | E3.1 | TRAIN NO.3 ELECTRICAL PLAN AND ELEVATION | TRAIN CELL NO.3 ELECTRICAL PLAN AND ELEVATION | Wording differs | Electrical | Electrical & Controls | plans_9.pdf | 5 | Available | — | Text |  |  | Title differs from the cover index (01 log #5); E0.1 sheet index matches the title block (Electrical & Controls, Verified) | 8 | #1, #2, #31, #32, #33, #35, #204 | None | Verified
70 | E4.1 | INFLUENT PUMP STATION, WAS, DEWATERING ELECTRICAL PLAN | Same as title block | Match | Electrical | Electrical & Controls | plans_9.pdf | 6 | Available | — | Text |  |  |  | 41 | #3, #7, #8, #9, #12, #13, #26, #36, #39, #40, #43, #59 … | None | Verified
71 | E4.2 | INFLUENT PUMP STATION ELECTRICAL PLAN AND ELEVATION | Same as title block | Match | Electrical | Electrical & Controls | plans_9.pdf | 7 | Available | — | Text |  |  |  | 11 | #36, #39, #40, #207 | None | Verified
72 | E4.3 | 2W PUMP STATION ELECTRICAL PLAN AND ELEVATION | Same as title block | Match | Electrical | Electrical & Controls | plans_9.pdf | 8 | Available | — | Text |  |  |  | 11 | #11, #16, #17, #45, #46, #49, #95, #100, #124, #167, #193, #199 … | None | Verified
73 | E5.1 | UV DISINFECTION CHAMBER & DIGESTER ELECTRICAL PLAN AND ELEVATION | UV DISINFECTION & CLARIFIER ELECTRICAL PLAN AND ELEVATION | Substantive difference | Electrical | Electrical & Controls | plans_10.pdf | 1 | Available | — | Text |  |  | Title differs from the cover index (01 log #1); E0.1 sheet index matches the title block (Electrical & Controls, Verified) | 10 | #10, #54, #55, #58, #209, #212, #258 | None | Unresolved
74 | E6.1 | ELECTRICAL ONE LINE DIAGRAM AND LOAD CALCULATIONS | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 2 | Available | — | Text | Flagged Text, needs a visual pass: Load tables are image-only (Electrical & Controls log) |  |  | 39 | #3, #18, #19, #23, #31, #36, #45, #59, #60, #61, #62, #63 … | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
75 | E6.2 | ELECTRICAL PANEL SCHEDULES | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 3 | Available | — | Visual |  |  |  | 25 | #13, #16, #17, #20, #23, #24, #26, #54, #55, #64, #95, #121 … | None | Verified
76 | E6.3 | CONDUIT AND CONDUCTOR SCHEDULES | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 4 | Available | — | Visual |  |  |  | 70 | #2, #3, #7, #8, #9, #10, #11, #12, #13, #16, #17, #18 … | None | Verified
77 | E7.0 | CONTROL SYSTEM OVERVIEW | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 5 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 15 | #7, #8, #9, #10, #11, #23, #24, #43, #63, #120, #184, #197 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
78 | E7.1 | MAIN PLC CONTROL PANEL ELEVATION | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 6 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 9 | #18, #19, #24, #58, #127, #213, #214 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
79 | E7.2 | MAIN PLC CONTROL PANEL - POWER WIRING DIAGRAM | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 7 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 8 | #18, #19, #24, #127, #214 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
80 | E7.3 | MAIN PLC CONTROL PANEL - DIGITAL INPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_10.pdf | 8 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 27 | #3, #18, #19, #24, #31, #45, #46, #54, #59, #60, #61, #65 … | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
81 | E7.4 | MAIN PLC CONTROL PANEL - DIGITAL OUTPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 1 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 13 | #3, #18, #19, #24, #45, #49, #59, #60, #61, #100 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
82 | E7.5 | MAIN PLC CONTROL PANEL - ANALOG INPUTS - SHEET 1 | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 2 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 5 | #24, #48, #54, #58 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
83 | E7.6 | MAIN PLC CONTROL PANEL - ANALOG INPUTS - SHEET 2 | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 3 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 5 | #1, #2, #24, #35, #125, #126, #197 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
84 | E7.7 | MAIN PLC CONTROL PANEL - ANALOG OUTPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 4 | Available | — | Text | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) |  |  | 4 | #24, #121, #123 | Index fix: flag Text + Visual (no rescan; lane already read it visually) | Verified
85 | E8.1 | INFLUENT PUMP STATION CONTROL PANEL ELEVATIONS | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 5 | Available | — | Text |  |  |  | 20 | #7, #8, #9, #36, #39, #40, #42, #120, #167, #197, #213, #214 | None | Verified
86 | E8.2 | INFLUENT PUMP STATION CONTROL PANEL-POWER WIRING DIAGRAM | INFLUENT PUMP STATION CONTROL PANEL - POWER WIRING DIAGRAMS | Wording differs | Electrical | Electrical & Controls | plans_11.pdf | 6 | Available | — | Text |  |  | Title differs from the cover index (01 log #6); E0.1 sheet index matches the cover index (Electrical & Controls, Verified) | 5 | #36 | None | Verified
87 | E8.3 | INFLUENT PUMP STATION CONTROL PANEL - DIGITAL INPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 7 | Available | — | Text |  |  |  | 13 | #26, #36, #40 | None | Verified
88 | E8.4 | INFLUENT PUMP STATION CONTROL PANEL - DIGITAL OUTPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_11.pdf | 8 | Available | — | Text |  |  |  | 10 | #12, #36, #107, #196 | None | Verified
89 | E8.5 | INFLUENT PUMP STATION CONTROL PANEL - ANALOG INPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 1 | Available | — | Text |  |  |  | 4 | #39 | None | Verified
90 | E8.6 | INFLUENT PUMP STATION CONTROL PANEL - ANALOG OUTPUTS | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 2 | Available | — | Text |  |  |  | 3 | #13, #64, #122, #167 | None | Verified
91 | E9.1 | BLOWER BUILDING MOTOR CONTROL CENTER ELEVATION | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 3 | Available | Cited — Add. 4 p.1, Clarification 4 | Text |  |  |  | 20 | #3, #18, #19, #23, #31, #45, #59, #60, #61, #63, #125, #126 … | None | Verified
92 | E9.2 | BLOWER BUILDING MOTOR CONTROL CENTER - VFD WIRING DIAGRAMS | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 4 | Available | — | Text |  |  |  | 7 | #18, #19, #23, #215 | None | Verified
93 | E9.3 | VENTILATION CONTROL PANEL ELEVATION AND WIRING DIAGRAM | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 5 | Available | — | Text |  |  |  | 7 | #26, #175, #186, #196, #203, #205, #228 | None | Verified
94 | E10.1 | ELECTRICAL DETAILS - SHEET 1 | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 6 | Available | — | Text |  |  |  | 14 | #39, #40 | None | Verified
95 | E10.2 | ELECTRICAL DETAILS - SHEET 2 | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 7 | Available | — | Text |  |  |  | 11 | #7, #8, #9, #10, #11, #43, #64, #120, #121, #184, #197, #216 | None | Verified
96 | E10.3 | STANDBY DIESEL GENERATOR ELEVATIONS | Same as title block | Match | Electrical | Electrical & Controls | plans_12.pdf | 8 | Available | — | Text |  |  |  | 1 | #65, #198, #236 | None | Verified
Add. | C1.6A | BURIED PIPING IN BUILDING | Same as title block | Match | Civil | Civil & Site | addendum-no4-eswd.pdf | 8 | Available | Issued by Add. 4 p.8 (governs) | Visual |  |  | Issued by Add. 4; page "XX of 96"; note "SEE ADDENDUM #3" — base issue not in the library; Not on the cover index (01 log #11) | 9 | #50, #51, #78, #83, #85, #89, #90, #91, #94, #171, #194, #238 | None | Verified-Visual
— | C8.1 | (referenced, not in the set) | — | — | Civil | — | — | — | Referenced by 08 70 00 ¶2.07 A (exterior door stop detail); no such sheet in the set | — | — |  |  | Structural & Building Issues §2 #12 | 0 |  | Engineer to issue the sheet or delete the reference | Unresolved

## Rescan & Upload
Action | Sheet | Title | What it resolves | Ledger rows citing it | Source
Upload — not in the library | C0.7 | WWTP INTERIM PLAN OF OPERATION (cover index) | Unblocks 2 Ledger rows; lanes carry cover-index titles only | 2 | 01 log #9; SETUP_Resplit_List_rev1.md
Upload — not in the library | C1.1 | SITE PIPING PLAN WITH GENERAL NOTES (cover index) | Unblocks 0 Ledger rows; lanes carry cover-index titles only | 0 | 01 log #9; SETUP_Resplit_List_rev1.md
Upload — not in the library | C1.2 | SITE DIMENSIONAL PLAN (cover index) | Unblocks 0 Ledger rows; lanes carry cover-index titles only | 0 | 01 log #9; SETUP_Resplit_List_rev1.md
Upload — not in the library | C7.7 | CIVIL DETAILS (cover index) | Unblocks 0 Ledger rows; lanes carry cover-index titles only | 0 | 01 log #9; SETUP_Resplit_List_rev1.md
Upload — not in the library | C7.8 | CIVIL DETAILS (cover index) | Unblocks 0 Ledger rows; lanes carry cover-index titles only | 0 | 01 log #9; SETUP_Resplit_List_rev1.md
Upload — not in the library | C7.9 | FLOW METER & VALVE VAULT DETAILS (cover index) | Unblocks 0 Ledger rows; lanes carry cover-index titles only | 0 | 01 log #9; SETUP_Resplit_List_rev1.md
Rescan / native PDF — unreadable or low-confidence value | G0.5 | PROCESS SCHEMATIC | Revision triangle number reads 6 — Process & Mechanical note for G0.5 | 38 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | C0.1 | EXISTING CONDITIONS | Low-confidence read: second easement number (Civil & Site Known Issues K-03) | 4 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | C0.5 | DEMOLITION PLAN | Low-confidence read: SSMH 1286 label under the X (Civil & Site Known Issues K-03) | 24 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | C2.5 | RETAINING WALL PLAN & PROFILE | Fence height in Keyed Note 4 reads 6" — Civil & Site CS-12 | 3 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | C5.4 | UV DISINFECTION EQUIPMENT | UV module callout "4-64" and "6 required / bank" not fully legible — Process & Mechanical Issue 13 | 2 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | A1.1 | BLOWER BUILDING PLAN | Door 101B height illegible in the door schedule (same on the Add. 4 p.4 reissue) — Structural & Building Issues §2 #1 | 14 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | S2.2 | UV DISINFECTION CHAMBER & DIGESTER PLAN & SECTIONS | Low-confidence read: mat slab spacing (#6 @ 10" vs @ 12") — confirm on the native sheet before any RFI (Structural & Building Known Issues 1) | 5 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | S2.3 | BLOWER BUILDING FOUNDATION PLAN & DETAILS | Perimeter grade beam bar size illegible on the base sheet and the Add. 4 p.9 reissue — Structural & Building Issues §2 #6 | 4 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | S2.4 | PUMP STATION LID, GENERATOR PAD, & FLOW SPLITTER PAD | Low-confidence read: hatch openings and thickened-edge depth — confirm on the native sheet before any RFI (Structural & Building Known Issues 1) | 7 | Lane Issues
Rescan / native PDF — unreadable or low-confidence value | E2.2 | BLOWER BUILDING LIGHTING AND HVAC PLAN | Light fixture L1 catalog number not legible (L1 (Blower Building)) — Electrical & Controls Ledger | 13 | Lane Issues
Index fix only — no rescan | G0.2 | LEGEND AND ABBREVIATIONS - CIVIL & ARCHITECTURAL | Flagged Text, needs a visual pass: Legends are graphics only (Civil & Site design gap) | 0 | Lane design-gap logs
Index fix only — no rescan | C1.3 | SITE PIPING PLAN WITH PIPING ID | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) | 30 | Lane design-gap logs
Index fix only — no rescan | C1.4 | SITE PIPING PLAN WITH BURIED VALVE ID | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) | 15 | Lane design-gap logs
Index fix only — no rescan | C1.5 | SITE PIPING PLAN WITH PIPE ELEVATIONS | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) | 0 | Lane design-gap logs
Index fix only — no rescan | C2.4 | STORM DRAINAGE PLAN & PROFILES | Flagged Text, needs a visual pass: Text layer is mostly repeated labels (Civil & Site design gap) | 10 | Lane design-gap logs
Index fix only — no rescan | C5.1 | UV DISINFECTION CHAMBER & DIGESTER PLAN | Flagged Text, needs a visual pass: Content is image-only (Process & Mechanical log) | 13 | Lane design-gap logs
Index fix only — no rescan | E1.1 | ELECTRIC SERVICE AREA PLAN | Flagged Text, needs a visual pass: Text layer mis-associates tags (TS reads as a transfer switch; it is the transformer) (Electrical & Controls log) | 15 | Lane design-gap logs
Index fix only — no rescan | E6.1 | ELECTRICAL ONE LINE DIAGRAM AND LOAD CALCULATIONS | Flagged Text, needs a visual pass: Load tables are image-only (Electrical & Controls log) | 39 | Lane design-gap logs
Index fix only — no rescan | E7.0 | CONTROL SYSTEM OVERVIEW | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 15 | Lane design-gap logs
Index fix only — no rescan | E7.1 | MAIN PLC CONTROL PANEL ELEVATION | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 9 | Lane design-gap logs
Index fix only — no rescan | E7.2 | MAIN PLC CONTROL PANEL - POWER WIRING DIAGRAM | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 8 | Lane design-gap logs
Index fix only — no rescan | E7.3 | MAIN PLC CONTROL PANEL - DIGITAL INPUTS | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 27 | Lane design-gap logs
Index fix only — no rescan | E7.4 | MAIN PLC CONTROL PANEL - DIGITAL OUTPUTS | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 13 | Lane design-gap logs
Index fix only — no rescan | E7.5 | MAIN PLC CONTROL PANEL - ANALOG INPUTS - SHEET 1 | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 5 | Lane design-gap logs
Index fix only — no rescan | E7.6 | MAIN PLC CONTROL PANEL - ANALOG INPUTS - SHEET 2 | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 5 | Lane design-gap logs
Index fix only — no rescan | E7.7 | MAIN PLC CONTROL PANEL - ANALOG OUTPUTS | Text layer order misassigns PLC I/O points (reported on E7.3–E7.5; applied to the E7 series, Inferred) (Electrical & Controls log) | 4 | Lane design-gap logs
Engineer — phantom reference | C8.1 | (referenced, not in the set) | Referenced by 08 70 00 ¶2.07 A (exterior door stop detail); no such sheet in the set | 0 | Structural & Building Issues §2 #12