## Tracker Summary
Installation Tracker — Summary by CWP
| Status date | 2023-03-15 | Input — set to the reporting date. Default = Notice to Proceed (Mar 15, 2023); no actual progress is entered in this sample.
CWP | Name | Items | Weight | Planned % | Earned % | Variance | Not started | On track | Behind | Overdue | Complete | Planned start | Planned finish
CWP 01 | General Requirements & Temporary Works | 12 | 12 | 0% | 0% | 0% | 4 | 8 | 0 | 0 | 0 | 2023-03-15 | 2024-10-16
CWP 02 | Demolition & Existing Conditions | 21 | 21 | 0% | 0% | 0% | 21 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-05-31
CWP 03 | Concrete (Cast-in-Place & Precast) | 30 | 30 | 0% | 0% | 0% | 30 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-07-08
CWP 05 | Metals (Grating, Railings, Ladders, Stairs) | 6 | 6 | 0% | 0% | 0% | 6 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-07-08
CWP 08 | Doors, Frames & Hardware | 4 | 4 | 0% | 0% | 0% | 4 | 0 | 0 | 0 | 0 | 2023-04-01 | 2023-07-31
CWP 09 | Painting & Coatings | 1 | 1 | 0% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | 2023-06-01 | 2023-10-25
CWP 10 | Specialties | 3 | 3 | 0% | 0% | 0% | 3 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-07-08
CWP 13 | Pre-Engineered Metal Building | 7 | 7 | 0% | 0% | 0% | 7 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-05-31
CWP 22 | Plumbing & Process Pumps | 25 | 25 | 0% | 0% | 0% | 25 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-02-09
CWP 23 | HVAC & Ventilation | 15 | 15 | 0% | 0% | 0% | 15 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-02-09
CWP 26 | Electrical, Instrumentation & Controls | 103 | 103 | 0% | 0% | 0% | 101 | 2 | 0 | 0 | 0 | 2023-03-15 | 2024-10-16
CWP 31 | Earthwork, Dewatering & Erosion Control | 19 | 19 | 0% | 0% | 0% | 5 | 14 | 0 | 0 | 0 | 2023-03-15 | 2024-10-16
CWP 32 | Paving, Fencing, Walls & Landscaping | 12 | 12 | 0% | 0% | 0% | 11 | 1 | 0 | 0 | 0 | 2023-03-15 | 2024-10-16
CWP 33 | Yard Piping & Utilities | 88 | 88 | 0% | 0% | 0% | 88 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-07-08
CWP 40 | Process Interconnections | 1 | 1 | 0% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | 2023-04-01 | 2023-11-01
CWP 41 | Material Handling (Screw Conveyors) | 2 | 2 | 0% | 0% | 0% | 2 | 0 | 0 | 0 | 0 | 2023-11-01 | 2024-02-09
CWP 43 | Blowers & 2W Plant Water System | 31 | 31 | 0% | 0% | 0% | 31 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-02-09
CWP 45 | Process Valves | 4 | 4 | 0% | 0% | 0% | 4 | 0 | 0 | 0 | 0 | 2023-04-01 | 2023-11-01
CWP 46 | Treatment Equipment | 60 | 60 | 0% | 0% | 0% | 60 | 0 | 0 | 0 | 0 | 2023-04-01 | 2024-07-08
Total |  | 444 | 444 | 0% | 0% | 0% | 419 | 25 | 0 | 0 | 0 | 2023-03-15 | 2024-10-16
Formulas:
Planned start = MINIFS(Tracker!$H5:H467,Tracker!$A5:A467,"Item",Tracker!$B5:B467,[CWP])
Planned start = MIN(M6:[Planned start, row above])
Planned finish = MAXIFS(Tracker!$I5:I467,Tracker!$A5:A467,"Item",Tracker!$B5:B467,[CWP])
Planned finish = MAX(N6:[Planned finish, row above])

## Tracker
Eastsound WWTP Upgrade Phase I — Installation Tracker by CWP (proof of concept)
Blue cells are inputs (dates or N/A). Planned dates come from the Schedule tab; progress uses the Rules of Credit tab; status date is on Tracker Summary. Rows sharing an item with another row are listed in 'Also tracked as' — update one of them.
Row | CWP | Tag | Item | Area/Building | Work type | Schedule activity ID | Planned start | Planned finish | Submittal approved | On site / ready | Installed / removed | Tested / inspected | Turned over / closed | Weight | Earned % | Planned % | Variance | Flag | Remarks | Schedule activity | Submittal approve-by | Submittal req | Testing req | Submittal lines | ITP lines | Also tracked as (same item) | Open exceptions | Ledger tag level | Bid item | Drawing sheets | Spec sections | Wiki note(s) | Lane
Section | CWP 01 | General Requirements & Temporary Works | 12 items · 0 overdue · 0 complete |  |  |  | 2023-03-15 | 2024-10-16 | [5 empty] | 12 | 0% | 0% | 0%
Item | CWP 01 | PROPOSED-Off-site staging area | Contractor staging area off Mt Baker Road, with vehicle path to the project site | Site (off-site staging) | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.6 |  | C0.6 | Civil & Site
Item | CWP 01 | PROPOSED-Temporary construction sign | Temporary construction sign, 4 x 8 ft plywood, Ecology and CDBG Commerce requirements | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 | PROPOSED-Funding-Recognition-Sign (Contract & General) | #72 | Inferred | 1 | — | 15 08 13 | 15 08 13 | Civil & Site
Item | CWP 01 | PROPOSED-Funding-Recognition-Sign | Funding recognition sign (Ecology financial assistance) | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary construction sign (Civil & Site) | #72, #250 | Inferred | 1 |  | 00 53 00 | 00 53 00 | Contract & General
Item | CWP 01 | PROPOSED-Temporary-Barriers | Temporary barriers at openings and hazards (fencing, railing, barricades, steel plates, with warning signs or lights) | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Inferred | 1 |  | 00 73 00; 01 50 00 | 00 73 00; 01 50 00 | Contract & General
Item | CWP 01 | PROPOSED-Temporary-Pump-and-Process-Equipment | Temporary pump and process equipment (removed at Final Completion) | Not stated | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  | #251 | Inferred | 1 |  | 00 73 00; 01 50 00; 01 70 00 | 00 73 00; 01 50 00; 01 70 00 | Contract & General
Item | CWP 01 | PROPOSED-Contractor-Field-Office | Contractor's field office (optional) | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Unresolved | 1 |  | 01 50 00; 01 31 00 | 01 50 00; 01 31 00; CQA Plan | Contract & General
Item | CWP 01 | PROPOSED-Temporary-Construction-Water-Connection | Temporary metered construction water connection with backflow preventer (if agreed) | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Unresolved | 1 |  | 01 50 00 | 01 50 00 | Contract & General
Item | CWP 01 | PROPOSED-Temporary-Sanitary-Facilities | Temporary restrooms (contract service allowed) | Site | Temporary | 01-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Unresolved | 1 |  | 01 50 00 | 01 50 00 | Contract & General
Item | CWP 01 | PROPOSED-Temporary bypass pumping system | Temporary bypass pumping, piping, holding tanks and storage | Site | Temporary | 01-C01 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary-Bypass-Pipe (Contract & General); PROPOSED-Temporary-Bypass-Alarm-Monitoring (Contract & General); PROPOSED-Bypass-Pumping-System (Contract & General) | #68 | Inferred | 1 | G0.3; C0.5 |  | G0.3; C0.5; Appendix F | Civil & Site
Item | CWP 01 | PROPOSED-Temporary-Bypass-Pipe | Temporary bypass pipe (chlorine contact tank outlet to 8-inch plant outlet) | Site | Temporary | 01-C01 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary bypass pumping system (Civil & Site) | #68, #250 | Inferred | 1 |  | 00 31 13 | 00 31 13 | Contract & General
Item | CWP 01 | PROPOSED-Bypass-Pumping-System | Bypass pumping systems (influent and effluent) for WWTP shutdowns | Site | Temporary | 01-C01 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-03-14 | Y | N | 6 | 0 | PROPOSED-Temporary bypass pumping system (Civil & Site) | #68, #250, #251 | Inferred | 1 |  | 01 33 00; 01 50 00 | 01 33 00; 01 50 00 | Contract & General
Item | CWP 01 | PROPOSED-Temporary-Bypass-Alarm-Monitoring | Temporary bypass alarm and status monitoring (cellular notification; wired to the existing WWTP control system) | Not stated | Temporary | 01-C01 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary bypass pumping system (Civil & Site) | #68, #253 | Inferred | 1 |  | 01 50 00 | 01 50 00 | Contract & General
Section | CWP 02 | Demolition & Existing Conditions | 21 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-05-31 | [5 empty] | 21 | 0% | 0% | 0%
Item | CWP 02 | PROPOSED-Existing 8in effluent outfall pipe | Existing 8-inch effluent (outfall) pipe, 40 LF — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 1); C0.7 (cited) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 4in roof drain pipe | Existing 4-inch roof drain pipe, 40 LF — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 2) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | SSMH 1286 | Existing sump pump station (sewage pump) — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 3, 5); C0.1 | 02 41 00 | C0.5; C0.1; 02 41 00 | Civil & Site
Item | CWP 02 | SSMH 1285 | Existing septic tank — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 4); C0.1 | 02 41 00 | C0.5; C0.1; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 10in effluent outfall pipe | Existing 10-inch effluent (outfall) pipe, 60 LF — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 8) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing storm drain and catch basin 87 LF | Existing storm drain, 87 LF, and catch basin — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 9) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 6in drain pipe to sump station | Existing 6-inch drain pipe to sump pump station, 20 LF — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 11) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 1.5in sump force main | Existing 1-1/2-inch sump pump force main, 60 LF — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 12) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing chain link fence 149 LF | Existing chain link fence, 149 LF — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 16) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing storm drain at roof drain 7 ft | Existing storm drain connected to roof drain, 7 ft — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 17) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing retaining wall 61 LF | Existing retaining wall, 61 LF — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 18) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing chain link fence 119 LF | Existing chain link fence, 119 LF — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 20) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 4in storm drain 8 LF | Existing 4-inch storm drain, 8 LF — remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 21) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 8in influent pipe | Existing 8-inch influent pipe — abandon and remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 | PROPOSED-EXISTING-INFLUENT-PIPING-REMOVAL (Process & Mechanical) | #77, #163 | Inferred | 1 | C0.5 (KN 24); C3.1 (cited) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Asphalt pavement sawcut and removal | Existing asphalt pavement — sawcut and remove (new surfacing on C2.6) | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 25); C2.6 (cited by Add. 4); C2.1; C2.6 | 02 41 00; 32 12 16 | C0.5; 02 41 00; 32 12 16 | Civil & Site
Item | CWP 02 | PROPOSED-Existing 8in slab over pre-aeration basin | Existing 8-inch slab over original pre-aeration basin — saw cut, remove and dispose | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (Demo Schedule 1) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing basin internal piping | Existing internal piping in existing basin — support during fill removal, then remove | Site | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (Demo Schedule 2–3) | 02 41 00 | C0.5; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-EXISTING-INFLUENT-PIPING-REMOVAL | Existing influent piping conflicts at the splitter: dewater, abandon, remove | Influent Flow Splitter | Remove | 02-C02 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Existing 8in influent pipe (Civil & Site) | #77, #143, #163 | Inferred | 1 | C3.1 |  | C3.1 | Process & Mechanical
Item | CWP 02 | PROPOSED-Existing holding tanks | Existing holding tanks — remove and relocate on site per Owner | Site | Modify / connect | 02-C03 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 15) |  | C0.5 | Civil & Site
Item | CWP 02 | PROPOSED-Existing Train 1 influent pipe | Existing Train 1 influent pipe — abandon and plug | Site | Modify / connect | 02-C03 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) KN 2 | 02 41 00 | C1.3; 02 41 00 | Civil & Site
Item | CWP 02 | PROPOSED-Existing generator fuel tank and spill basin | Existing generator fuel tank and concrete fuel spill basin — remove, restore as asphalt pavement | Site | Remove | 02-C01 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Demolition & Existing Conditions — Existing generator, switchgear and fuel tank removal | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Existing-Office-Louver-4x4 (Structural & Building); PROPOSED-Existing-Office-Louver-2x3 (Structural & Building); PROPOSED-Existing-Generator-Exhaust-Assembly (Structural & Building); PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers (Electrical & Controls) | #28 | Inferred | 1 | C0.5 (KN 19); C0.1 | 02 41 00 | C0.5; C0.1; 02 41 00; Appendix F | Civil & Site
Section | CWP 03 | Concrete (Cast-in-Place & Precast) | 30 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-07-08 | [5 empty] | 30 | 0% | 0% | 0%
Item | CWP 03 | PROPOSED-Blower-Building-Slab-and-Grade-Beams | Blower Building concrete slab-on-grade and grade beams | Blower Building | Install | 03-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Blower Building | 2023-03-31 | Y | Y | 6 | 3 |  |  | Inferred | 1 (Inferred per 04) | A1.1; A1.2; S1.1; S2.3; S4.1 | 03 30 00 | A1.1; A1.2; S1.1; S2.3; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Blower-Pad | Concrete blower equipment pad carrying 4 blowers | Blower Building | Install | 03-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Blower Building | 2023-03-31 | Y | Y | 5 | 3 |  | #233 | Inferred | 1 (Inferred per 04) | A1.1; A1.3; S1.1; S2.3 | 03 30 00 | A1.1; S1.1; S2.3; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Existing-Slab-Trench-Infill | Trench cut and concrete infill in existing slab for sub-floor sludge piping (Detail 8) | Not stated (existing building per C1.6A) | Install | 03-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Sludge pumps and valving | 2023-03-31 | Y | Y | 3 | 1 | PROPOSED-Existing slab coring and repair (Civil & Site) | #78, #238 | Inferred | 1 (Inferred per 04) | S4.1 | 03 30 00 | S4.1; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-EFFLUENT-SAMPLE-SUMP | Effluent sample sump (effluent sample chamber) | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 |  | #104 | Inferred | 1 | G0.6; C5.1; C5.2; C5.3 |  | G0.6; C5.1; C5.2; C5.3 | Process & Mechanical
Item | CWP 03 | PROPOSED-UV-DIGESTER-STRUCTURE | UV Disinfection Chamber & Digester structure, concrete, about 45 x 13 ft: UV chamber, effluent sample chamber, aerobic digester | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Aerobic-Digester (Contract & General); PROPOSED-UV-Disinfection-Chamber (Contract & General); PROPOSED-UV-Disinfection-Chamber-Basin (Structural & Building); PROPOSED-Digester-Concrete-Tank (Structural & Building) | #56 | Unresolved | 1 | G0.5; G0.6; C5.1; C5.2; C5.3 |  | C5.1; G0.6; C5.2; C5.3 | Process & Mechanical
Item | CWP 03 | PROPOSED-UV-Disinfection-Chamber-Basin | UV Disinfection Chamber basin — 8 in CIP concrete walls on 12 in mat slab, with 8 in equipment support walls (4) | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | Y | Y | 6 | 2 | PROPOSED-UV-DIGESTER-STRUCTURE (Process & Mechanical); PROPOSED-Aerobic-Digester (Contract & General) | #56, #234 | Unresolved | 1 (Inferred per 04) | S2.2; S1.1; S4.1 | 03 30 00 | S2.2; S1.1; S4.1; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Digester-Concrete-Tank | Digester — 12 in CIP concrete walls on 12 in mat slab with sloped unreinforced topping | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | Y | Y | 6 | 2 | PROPOSED-UV-DIGESTER-STRUCTURE (Process & Mechanical); PROPOSED-Aerobic-Digester (Contract & General); PROPOSED-UV-Disinfection-Chamber (Contract & General) | #56 | Unresolved | 1 (Inferred per 04) | S2.2; S1.1; S4.1 | 03 30 00 | S2.2; S1.1; S4.1; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Aerobic-Digester | Aerobic digester | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | N | Y | 0 | 6 | PROPOSED-UV-DIGESTER-STRUCTURE (Process & Mechanical); PROPOSED-UV-Disinfection-Chamber-Basin (Structural & Building); PROPOSED-Digester-Concrete-Tank (Structural & Building) | #56, #251, #252 | Inferred | 1 |  | 00 24 13; 00 31 13; 00 73 00; 01 45 00; 01 50 00 | 00 24 13; 00 31 13; 00 73 00; 01 45 00; 01 50 00; CQA Plan | Contract & General
Item | CWP 03 | PROPOSED-UV-Disinfection-Chamber | UV disinfection chamber (UV channels #1 and #2) | UV Disinfection Chamber & Digester | Install | 03-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-03-31 | N | Y | 0 | 4 | PROPOSED-UV-DIGESTER-STRUCTURE (Process & Mechanical); PROPOSED-UV-Disinfection-Chamber-Basin (Structural & Building); PROPOSED-Digester-Concrete-Tank (Structural & Building) | #56, #252 | Inferred | 1 |  | 00 31 13; 01 45 00; 01 50 00 | 00 31 13; 01 45 00; 01 50 00 | Contract & General
Item | CWP 03 | PROPOSED-Existing slab coring and repair | Existing building slab — core or saw cut for under-slab piping, then repair | Existing building (C1.6A) | Modify / connect | 03-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Existing-Slab-Trench-Infill (Structural & Building) | #78 | Inferred | 1 | C1.6A (Add. 4 p.8) |  | C1.6A | Civil & Site
Item | CWP 03 | PROPOSED-Influent-Flow-Meter-Valve-Vault | Precast vault, 4 ft x 4 ft (Oldcastle Infrastructure 4686-LA), with 36 in x 36 in H-20 single-leaf hatch (Halliday H1R3636) — Influent Flow Meter Valve Vault | Site | Install | 03-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-INFLUENT-FLOW-METER-VAULT (Process & Mechanical) | #44, #240 | Inferred | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Effluent-Flow-Meter-Valve-Vault | Precast vault, 4 ft x 4 ft (Oldcastle Infrastructure 4686-LA), with 36 in x 36 in H-20 single-leaf hatch (Halliday H1R3636) — Effluent Flow Meter Valve Vault | Site | Install | 03-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  | #240 | Inferred | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Plants-2-and-3-Flow-Meter-Vault | Precast vault, 4 ft x 4 ft (Oldcastle Infrastructure 4686-LA), with 36 in x 36 in H-20 single-leaf hatch (Halliday H1R3636) — Plants 2 & 3 Flow Meter Vault | Site | Install | 03-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-TRAIN-2-FLOW-METER-VAULT (Process & Mechanical); PROPOSED-Train 2 flow meter vault (Civil & Site); PROPOSED-Train 3 flow meter vault (Civil & Site); PROPOSED-TRAIN-3-FLOW-METER-VAULT (Process & Mechanical) | #5, #6, #240 | Inferred | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Yard-Piping-Vaults | Vaults associated with yard piping | Site | Install | 03-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  | #250 | Inferred | 1 |  | 00 31 13 | 00 31 13 | Contract & General
Item | CWP 03 | PROPOSED-2W-Pump-Station-Precast-Wet-Well | Precast wet well, 8 ft ID (Oldcastle Infrastructure 96 in diameter), with 48 in x 30 in H-20 aluminum hatch and safety grate (LW Products HD-3C) — 2W Plant Water Pump Station | 2W Pump Station | Install | 03-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — 2W air gap water system | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-2W-PUMP-STATION-WET-WELL (Process & Mechanical); PROPOSED-2W-Pump-Station-Wet-Well (Process & Mechanical) | #47, #240 | Inferred | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-FLOW-SPLITTER-SUPPORT | Concrete support pad for flow splitter box, about 6.5 x 4.0 x 1.3 ft tall, top elev 26.00 | Influent Flow Splitter | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Flow-Splitter-Pad (Structural & Building) | #76, #157 | Inferred | 1 | C3.1; C3.2 |  | C3.1; C3.2 | Process & Mechanical
Item | CWP 03 | PROPOSED-INFLUENT-FLOW-METER-VAULT | Flow meter vault on the splitter inlet line (north) | Influent Flow Splitter | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Influent-Flow-Meter-Valve-Vault (Structural & Building) | #44 | Inferred | 1 | C3.1 |  | C3.1 | Process & Mechanical
Item | CWP 03 | PROPOSED-TRAIN-2-FLOW-METER-VAULT | Train 2 flow meter vault | Influent Flow Splitter | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Plants-2-and-3-Flow-Meter-Vault (Structural & Building); PROPOSED-Train 2 flow meter vault (Civil & Site) | #5 | Inferred | 1 | C3.1 |  | C3.1 | Process & Mechanical
Item | CWP 03 | PROPOSED-TRAIN-3-FLOW-METER-VAULT | Train 3 flow meter vault | Influent Flow Splitter | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Train 3 flow meter vault (Civil & Site); PROPOSED-Plants-2-and-3-Flow-Meter-Vault (Structural & Building) | #6 | Inferred | 1 | C3.1 |  | C3.1 | Process & Mechanical
Item | CWP 03 | PROPOSED-IPS-HATCHES | Influent Pump Station access hatches: 36x36-in. single leaf H-20 (Halliday H1R3636) and 30x48-in. single leaf H-20 over pumps (Halliday H1R3048) | Influent Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Influent-Pump-Station-Precast-Wet-Well (Structural & Building); PROPOSED-Drain-Pump-Station-Hatches (Structural & Building); PROPOSED-Influent-Pump-Station-Top-Slab (Structural & Building) | #38 | Inferred | 1 | C4.1 |  | C4.1 | Process & Mechanical
Item | CWP 03 | PROPOSED-Drain-Pump-Station-Lid | Drain pump station lid — 16 in CIP concrete, H-20 loading, two hatch openings and center beam | Drain Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 4 | 2 |  |  | Unresolved | 1 (Inferred per 04) | S2.4; S1.1 | 03 30 00 | S2.4; S1.1; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Drain-Pump-Station-Precast-Wet-Well | Precast concrete wet well, 8 ft min., 96 in I.D. — per civil | Drain Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | N | 2 | 0 |  | #235 | Unresolved | 1 (Inferred per 04) | S2.4 | 03 40 00 | S2.4; 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Drain-Pump-Station-Hatches | Access hatches (2), 2 ft-6 in x 4 ft-0 in rough openings, in the drain pump station lid — per civil | Drain Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-IPS-HATCHES (Process & Mechanical) | #38, #235 | Inferred | 1 (Inferred per 04) | S2.4 |  | S2.4 | Structural & Building
Item | CWP 03 | PROPOSED-Flow-Splitter-Pad | Concrete equipment pad for the flow splitter, on the existing equipment slab-on-grade | Flow Splitter | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 3 | 1 | PROPOSED-FLOW-SPLITTER-SUPPORT (Process & Mechanical) | #76, #157 | Inferred | 1 (Inferred per 04) | S2.4 | 03 30 00 | S2.4; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Influent-Pump-Station-Precast-Wet-Well | Precast wet well, 8 ft ID (Oldcastle Infrastructure 96 in diameter), with 48 in x 30 in H-20 aluminum hatch and safety grate (LW Products HD-3C) — Influent Pump Station | Influent Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-INFLUENT-PUMP-STATION-WET-WELL (Process & Mechanical); PROPOSED-IPS-HATCHES (Process & Mechanical) | #37, #38, #240 | Unresolved | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Influent-Pump-Station-Top-Slab | Influent Pump Station top slab per Contract Plan details, with new aluminum access hatch and safety grates | Influent Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-IPS-HATCHES (Process & Mechanical) | #38, #240 | Unresolved | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Influent-Pump-Station-Meter-Vaults | Precast vaults, 4 ft x 4 ft (Oldcastle Infrastructure 4686-LA), with 36 in x 36 in H-20 single-leaf hatches (Halliday H1R3636) — Influent Pump Station Meter Vaults, quantity not stated | Influent Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-IPS-VALVE-VAULTS (Process & Mechanical) | #41, #240 | Inferred | 1 (Inferred per 04) |  | 03 40 00 | 03 40 00 | Structural & Building
Item | CWP 03 | PROPOSED-Influent-Pump-Station | Influent pump station | Influent Pump Station | Install | 03-C04 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-03-31 | N | Y | 0 | 6 | PROPOSED-INFLUENT-PUMP-STATION-WET-WELL (Process & Mechanical); PROPOSED-Influent-Pump-Station-Precast-Wet-Well (Structural & Building) | #37, #251 | Inferred | 1 |  | 00 31 13; 00 73 00; 01 45 00; 01 50 00 | 00 31 13; 00 73 00; 01 45 00; 01 50 00; CQA Plan | Contract & General
Item | CWP 03 | PROPOSED-Train-3-Concrete-Tank | Train 3 cast-in-place concrete tank — 12 in circular wall on 12 in mat slab with raised center pedestal | Train 3 | Install | 03-C06 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Train 3 | 2023-03-31 | Y | Y | 5 | 2 | PROPOSED-TRAIN-3-TANK (Process & Mechanical) | #29, #158 | Unresolved | 1 (Inferred per 04) | S2.1; S1.1; S4.1 | 03 30 00 | S2.1; S1.1; 03 30 00 | Structural & Building
Item | CWP 03 | PROPOSED-Generator-Slab | Generator slab-on-grade, 6 in with thickened edge (about 1 ft-6 in min. deep) | Generator Pad | Install | 03-C03 | 2024-03-01 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Concrete (Cast-in-Place & Precast) — Permanent standby generator | 2023-03-31 | Y | Y | 3 | 1 |  | #201 | Unresolved | 1 (Inferred per 04) | S2.4 | 03 30 00 | S2.4; 03 30 00 | Structural & Building
Section | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) | 6 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-07-08 | [5 empty] | 6 | 0% | 0% | 0%
Item | CWP 05 | PROPOSED-UV-DIGESTER-GRATING-GUARDRAIL | UV/digester guardrail with removable guard chains, removable grating over digester, aluminum access ladders (nominal 2 ft wide) | UV Disinfection Chamber & Digester | Install | 05-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | PROPOSED-UV-Digester-Grating (Structural & Building); PROPOSED-UV-Digester-Guardrail-and-Ladders (Structural & Building) | #57 | Inferred | 1 | C5.1; C5.2; C5.3 |  | C5.1; C5.2; C5.3 | Process & Mechanical
Item | CWP 05 | PROPOSED-Digester-Grating-Beam | Steel beam, HDG W8x18, spanning the digester for grating support | UV Disinfection Chamber & Digester | Install | 05-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-03-31 | Y | Y | 4 | 2 |  |  | Inferred | 1 (Inferred per 04) | S2.2; S1.1 | 05 50 00 | S2.2; S1.1; 05 50 00 | Structural & Building
Item | CWP 05 | PROPOSED-UV-Digester-Grating | Aluminum solid plank grating with continuous HDG edge angles — UV basin and digester | UV Disinfection Chamber & Digester | Install | 05-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-03-31 | Y | N | 3 | 0 | PROPOSED-UV-DIGESTER-GRATING-GUARDRAIL (Process & Mechanical) | #57 | Unresolved | 1 (Inferred per 04) | S2.2 | 05 53 00 | S2.2; 05 53 00 | Structural & Building
Item | CWP 05 | PROPOSED-UV-Digester-Guardrail-and-Ladders | Guardrail and ladders at the UV basin and digester — shown "per civil" | UV Disinfection Chamber & Digester | Install | 05-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-03-31 | Y | N | 5 | 0 | PROPOSED-UV-DIGESTER-GRATING-GUARDRAIL (Process & Mechanical) | #57, #234 | Unresolved | 1 (Inferred per 04) | S2.2 | 05 52 00; 05 51 10 | S2.2; 05 52 00; 05 51 10 | Structural & Building
Item | CWP 05 | PROPOSED-Train-3-Guardrail-and-Ladders | Train 3 guardrail and ladders — shown "per civil" | Train 3 | Install | 05-C01 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — Train 3 | 2023-03-31 | Y | N | 4 | 0 | PROPOSED-TRAIN-3-WALKWAYS-AND-LADDER (Process & Mechanical); PROPOSED-Handrails (Contract & General) | #34, #232, #255 | Unresolved | 18 — Unresolved (see 04) | S2.1 | 05 52 00; 05 51 10 | S2.1; 05 52 00; 05 51 10 | Structural & Building
Item | CWP 05 | PROPOSED-Steel-Stairs-Ladders-Platforms | Steel stairs, ladders and grating platforms — galvanized, Contractor-designed, where shown on the plans | Not stated (locations per civil drawings) | Install | 05-C01 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Metals (Grating, Railings, Ladders, Stairs) — Train 3 | 2023-03-31 | Y | N | 5 | 0 |  | #241, #255 | Unresolved | 1 (Inferred per 04); any Train 3 portion: 18 — Unresolved (see 04) | S1.1 | 05 51 10; 05 53 00; 05 52 00 | S1.1; 05 51 10 | Structural & Building
Section | CWP 08 | Doors, Frames & Hardware | 4 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2023-07-31 | [5 empty] | 4 | 0% | 0% | 0%
Item | CWP 08 | 101A | Door pair, 10 ft-0 in x 8 ft-0 in x 1-3/4 in, insulated hollow metal, painted, Type B — 2 openings tagged 101A | Blower Building | Install | 08-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Doors, Frames & Hardware — Blower Building | 2023-03-31 | Y | Y | 4 | 3 |  |  | Unresolved | 1 (Inferred per 04) | A1.1; A1.2 | 08 10 00; 08 70 00; 09 90 00 | A1.1; A1.2; 08 10 00; 08 70 00; 09 90 00 | Structural & Building
Item | CWP 08 | 101B | Door, 3 ft-0 in wide, insulated hollow metal, painted, Type A | Blower Building | Install | 08-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Doors, Frames & Hardware — Blower Building | 2023-03-31 | Y | Y | 4 | 3 |  |  | Unresolved | 1 (Inferred per 04) | A1.1; A1.2 | 08 10 00; 08 70 00; 09 90 00 | A1.1; A1.2; 08 10 00; 08 70 00; 09 90 00 | Structural & Building
Item | CWP 08 | 101C | Door, 5 ft-0 in x 8 ft-0 in x 1-3/4 in, insulated hollow metal, painted, Type A | Blower Building | Install | 08-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Doors, Frames & Hardware — Blower Building | 2023-03-31 | Y | Y | 4 | 3 |  |  | Unresolved | 1 (Inferred per 04) | A1.1; A1.2 | 08 10 00; 08 70 00; 09 90 00 | A1.1; A1.2; 08 10 00; 08 70 00; 09 90 00 | Structural & Building
Item | CWP 08 | PROPOSED-Boot-Brush-and-Pad | Boot and shoe brush with scraper (Gempler's #2900) on a concrete pad next to the Blower Building exterior door | Blower Building | Install | 08-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Doors, Frames & Hardware — Blower Building | 2023-03-31 | Y | N | 1 | 0 |  | #129 | Inferred | 1 (Inferred per 04) |  | 08 70 00 | 08 70 00 | Structural & Building
Section | CWP 09 | Painting & Coatings | 1 items · 0 overdue · 0 complete |  |  |  | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0%
Item | CWP 09 | PROPOSED-Influent-Pump-Station-Interior-Coating | Epoxy protective lining, spray-applied 100% solids (Raven 405 or Tnemec G436), on all interior concrete surfaces — Influent Pump Station | Influent Pump Station | Install | 09-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Painting & Coatings — Influent pump station and flow splitter | 2023-05-31 | Y | Y | 2 | 1 |  | #130, #243 | Inferred | 1 (Inferred per 04) |  | 09 97 23 | 09 97 23 | Structural & Building
Section | CWP 10 | Specialties | 3 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-07-08 | [5 empty] | 3 | 0% | 0% | 0%
Item | CWP 10 | PROPOSED-Fire-Extinguishers-Blower-Building | Fire extinguisher assemblies (2), wall-mounted — Blower Building | Blower Building | Install | 10-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Specialties — Blower Building | 2023-03-31 | Y | Y | 2 | 1 |  |  | Inferred | 1 (Inferred per 04) | A1.1 | 10 52 00 | A1.1; 10 52 00 | Structural & Building
Item | CWP 10 | PROPOSED-WWTP tank and building signs | WWTP tank and building signs, 9 (UV Disinfection Chamber, Blower Building, Dewatering Facility, Influent Pump Station, Aerobic Digester, Train 1–3, 2W Water System Pump Station) | Site | Install | 10-C03 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Specialties — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  | #98 | Inferred | 1 | C7.3 (Det. 1) |  | C7.3 | Civil & Site
Item | CWP 10 | PROPOSED-TRAIN-3-FRP-LAUNDER-COVER | FRP launder cover, Train 3 clarifier effluent trough | Train 3 | Install | 10-C02 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Specialties — Train 3 | 2023-03-31 | Y | Y | 2 | 2 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | C3.4; C3.5 | 10 73 05 | C3.4; C3.5; 10 73 05 | Process & Mechanical
Section | CWP 13 | Pre-Engineered Metal Building | 7 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-05-31 | [5 empty] | 7 | 0% | 0% | 0%
Item | CWP 13 | PROPOSED-BLOWER-BUILDING ¦ PROPOSED-Blower-Building | Blower Building, prefabricated metal building housing the biological treatment blowers ¦ Blower Building — pre-engineered metal building, one room (Blower Room 101) ¦ Blower Building | Blower Building | Install | 13-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Blower Building | 2023-03-31 | Y | Y | 15 | 13 |  | #170, #252 | Unresolved | 1 ¦ 1 (Inferred per 04) | C6.4; C6.5; A1.1; A1.2; A1.3; S1.1; S2.3 | 13 12 20; 07 20 00; 09 25 00; 09 90 00; 00 31 13; 00 73 00; 01 45 00; 01 70 00 | C6.4; C6.5; A1.1; A1.2; A1.3; S1.1; S2.3; 13 12 20; 07 20 00; 09 25 00; 09 90 00; 00 31 13; 00 73 00; 01 45 00; 01 70 00; CQA Plan | Process & Mechanical; Structural & Building; Contract & General
Item | CWP 13 | PROPOSED-Existing-Office-Louver-4x4 | Existing louvered vent, 4 ft x 4 ft — existing office building south wall; remove, re-side floor to eave | Existing Office Building | Remove | 13-C03 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Existing generator fuel tank and spill basin (Civil & Site); PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers (Electrical & Controls) | #28 | Inferred | 1 (Inferred per 04) | A1.3 | 13 12 20 | A1.3; 13 12 20 | Structural & Building
Item | CWP 13 | PROPOSED-Existing-Office-Louver-2x3 | Existing louvered vent, 2 ft x 3 ft — existing office building east wall; remove, re-side floor to eave | Existing Office Building | Remove | 13-C03 | 2023-04-01 | 2023-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Site demolition ahead of new work | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Existing generator fuel tank and spill basin (Civil & Site); PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers (Electrical & Controls) | #28 | Inferred | 1 (Inferred per 04) | A1.3 | 13 12 20 | A1.3; 13 12 20 | Structural & Building
Item | CWP 13 | PROPOSED-WWTP-Building-Louver-3x7 | Louvered vent, 3 ft x 7 ft — existing WWTP building, 3 locations | Existing WWTP Building | Install | 13-C04 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-EXISTING-BLDG-LOUVERS (Process & Mechanical) | #27, #229 | Inferred | 1 (Inferred per 04) | A1.3 | 13 12 20 | A1.3; 13 12 20 | Structural & Building
Item | CWP 13 | PROPOSED-WWTP-Building-Exhaust-Fan-24x24 | Exhaust fan, 24 in x 24 in — existing WWTP building, 3 locations, 6 ft above slab | Existing WWTP Building | Install | 13-C04 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | EF-3 (Electrical & Controls); EF-4 (Electrical & Controls); EF-5 (Electrical & Controls); PROPOSED-EXISTING-BLDG-WALL-FANS (Process & Mechanical) | #26, #229 | Inferred | 1 (Inferred per 04) | A1.3 | 13 12 20 | A1.3; 13 12 20 | Structural & Building
Item | CWP 13 | PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers | Existing diesel fuel tank, generator exhaust system and louvers | Electric Service Area | Remove | 13-C02 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Existing-Office-Louver-4x4 (Structural & Building); PROPOSED-Existing-Office-Louver-2x3 (Structural & Building); PROPOSED-Existing-Generator-Exhaust-Assembly (Structural & Building); PROPOSED-Existing generator fuel tank and spill basin (Civil & Site) | #28 | Verified | 6 | E0.2 |  | E0.2 | Electrical & Controls
Item | CWP 13 | PROPOSED-Existing-Generator-Exhaust-Assembly | Existing generator exhaust assembly — existing office building east wall; remove | Existing Office Building | Remove | 13-C02 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Existing generator fuel tank and spill basin (Civil & Site); PROPOSED-Existing-Generator-Fuel-Tank-Exhaust-Louvers (Electrical & Controls) | #28, #230 | Inferred | 1 (Inferred per 04) | A1.3 | 13 12 20 | A1.3; 13 12 20 | Structural & Building
Section | CWP 22 | Plumbing & Process Pumps | 25 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-02-09 | [5 empty] | 25 | 0% | 0% | 0%
Item | CWP 22 | PROPOSED-WAS-PUMP | WAS pump, packaged sludge pump, 3 HP | Sludge Pump and Valving Area | Install | 22-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Sludge pumps and valving | 2023-03-31 | Y | Y | 3 | 3 | WP-1 (Electrical & Controls); PROPOSED-Sludge-Pumps (Contract & General) | #59 | Inferred | 1; 6 | G0.5; G0.6; G0.7; C6.2 | 22 13 36 | C6.2; G0.7; 22 13 36 | Process & Mechanical
Item | CWP 22 | PROPOSED-SWING-SLUDGE-PUMP | Swing pump, packaged sludge pump, 3 HP, standby for either the WAS or digested sludge pump | Sludge Pump and Valving Area | Install | 22-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Sludge pumps and valving | 2023-03-31 | Y | Y | 3 | 3 | WP-2 (Electrical & Controls) | #60 | Inferred | 1; 6 | G0.5; G0.6; G0.7; C6.2 | 22 13 36 | C6.2; G0.7; 22 13 36 | Process & Mechanical
Item | CWP 22 | PROPOSED-DIGESTED-SLUDGE-PUMP | Digested sludge pump, packaged sludge pump, 3 HP | Sludge Pump and Valving Area | Install | 22-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Sludge pumps and valving | 2023-03-31 | Y | Y | 4 | 6 | SD-1 (Electrical & Controls) | #61 | Unresolved | 1; 6 | G0.5; G0.6; G0.7; C6.2 | 22 13 36; 46 76 26 | C6.2; G0.7; 22 13 36; 46 76 26 | Process & Mechanical
Item | CWP 22 | PROPOSED-SLUDGE-PUMP-LOCAL-PANELS | Sludge pump local electrical control panels (3), by pump manufacturer | Sludge Pump and Valving Area | Install | 22-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Sludge pumps and valving | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-WAS-and-Sludge-Pump-Local-Disconnects (Electrical & Controls) | #62 | Inferred | 1; 6 |  | 22 13 36 | 22 13 36 | Process & Mechanical
Item | CWP 22 | PROPOSED-Sludge-Pumps | Sludge pumps (peristaltic; WAS and digested sludge) | Sludge Pump and Valving Area | Install | 22-C02 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Sludge pumps and valving | 2023-03-31 | Y | Y | 12 | 7 | PROPOSED-WAS-PUMP (Process & Mechanical); WP-1 (Electrical & Controls) | #59, #251 | Inferred | 1 |  | 00 31 13; 01 33 00; 01 70 00; 01 91 00; 01 45 00 | 00 31 13; 01 33 00; 01 70 00; 01 91 00; 01 45 00; CQA Plan | Contract & General
Item | CWP 22 | WP-1 | WAS Pump No.1, 3 HP, VFD in MCC | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 22-C03 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-WAS-PUMP (Process & Mechanical); PROPOSED-Sludge-Pumps (Contract & General) | #59, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 |  | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 | Electrical & Controls
Item | CWP 22 | WP-2 | WAS Pump No.2 / swing pump, 3 HP, VFD in MCC | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 22-C03 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-SWING-SLUDGE-PUMP (Process & Mechanical) | #60, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 |  | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 | Electrical & Controls
Item | CWP 22 | SD-1 | Sludge pump, 3 HP, VFD in MCC | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 22-C03 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-DIGESTED-SLUDGE-PUMP (Process & Mechanical) | #3, #61, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 |  | E4.1; E6.1; E6.3; E7.3; E7.4; E9.1 | Electrical & Controls
Item | CWP 22 | PROPOSED-YARD-HYDRANTS | 1-inch frost-proof yard hydrants with vacuum breakers (quantity not stated) | Site | Install | 22-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 2 | 0 | Pipe ID 22 (Civil & Site) | #52 | Inferred | 1 |  | 15 40 00; 43 22 10 | 15 40 00; 43 22 10 | Process & Mechanical
Item | CWP 22 | PROPOSED-POST-HYDRANTS | 2-inch post hydrants with 2-inch atmospheric vacuum breakers (quantity not stated) | Site | Install | 22-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-Post hydrant (Civil & Site) | #53 | Inferred | 1 |  | 15 40 00 | 15 40 00 | Process & Mechanical
Item | CWP 22 | PROPOSED-EXTERIOR-SANITARY-DRAINS | Exterior sanitary drain piping, ABS DWV, with unions and cleanouts | Site | Install | 22-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  | #110 | Inferred | 1 |  | 15 40 00 | 15 40 00 | Process & Mechanical
Item | CWP 22 | PROPOSED-IPS-DISCHARGE-TO-SPLITTER | Influent Pump Station discharge to flow splitter, 6-inch DI restrained rising to 12-inch DI at the box | Influent Flow Splitter | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | Pipe ID 18 (Civil & Site) | #86 | Inferred | 1 | G0.5; C3.1; C3.2; C4.1 | 22 13 29 | G0.5; C3.1; C3.2; C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-INFLUENT-PUMP-STATION-WET-WELL | Influent Pump Station wet well, 96-inch precast on 12-inch precast base, bottom elev 9.0, top 23.30, with vent and clean outs | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Y | N | 5 | 0 | PROPOSED-Influent-Pump-Station (Contract & General); PROPOSED-Influent-Pump-Station-Precast-Wet-Well (Structural & Building) | #37 | Unresolved | 1 | G0.5; G0.6; C4.1 | 22 13 29 | C4.1; G0.6; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-INFLUENT-PUMPS-SMALL | Influent pumps, small, submersible, duplex (2), 120-220 gpm each | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 3 | 3 | IP-3 (Electrical & Controls); IP-4 (Electrical & Controls); IP-2 (Electrical & Controls); IP-1 (Electrical & Controls); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36 | Inferred | 1; Equipment Alternate A | G0.7; C4.1 | 22 13 29 | G0.7; C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-INFLUENT-PUMPS-LARGE | Influent pumps, large, submersible, duplex (2), 320-500 gpm each | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 3 | 3 | IP-3 (Electrical & Controls); IP-4 (Electrical & Controls); IP-2 (Electrical & Controls); IP-1 (Electrical & Controls); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36 | Inferred | 1; Equipment Alternate A | G0.7; C4.1 | 22 13 29 | G0.7; C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-IPS-LEVEL-TRANSDUCER | Influent Pump Station wet well level transducer, set 6 in. above floor (set points T1-T7) | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | LT (Influent Pump Station) (Electrical & Controls) | #39 | Inferred | 1 | C4.1 | 22 13 29 | C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | F1–F4 [Influent Pump Station] | Influent Pump Station backup float switches F1-F4, timer control | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | N | Y | 0 | 2 | F1 (Influent Pump Station) (Electrical & Controls); F2 (Influent Pump Station) (Electrical & Controls); F3 (Influent Pump Station) (Electrical & Controls); F4 (Influent Pump Station) (Electrical & Controls) | #40 | Inferred | 1 | C4.1 | 22 13 29 | C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-IPS-VALVE-VAULTS | Influent Pump Station valve vaults (2), precast 4 ft 2 in x 4 ft 2 in x 5 ft 6 in min. inside, Utility Vault Co. 506-LA or equal | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Influent-Pump-Station-Meter-Vaults (Structural & Building) | #41 | Inferred | 1 | C4.1 | 22 13 29 | C4.1; 22 13 29 | Process & Mechanical
Item | CWP 22 | PROPOSED-IPS-MOTOR-SAVER-RELAYS | Flygt MiniCAS-120 motor saver relays for the influent pumps, supplied by Contractor to the Control Systems Integrator | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Y | N | 2 | 0 | PROPOSED-Influent-Pump-Seal-Fail-Overtemp-Relays (Electrical & Controls) | #42 | Inferred | 1; Equipment Alternate A |  | 22 13 29 | 22 13 29 | Process & Mechanical
Item | CWP 22 | IP-1 | Influent Pump No.1, 3 HP, explosion-proof (XP), 4.8 FLA | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-INFLUENT-PUMPS-SMALL (Process & Mechanical); PROPOSED-INFLUENT-PUMPS-LARGE (Process & Mechanical); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36, #167, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 |  | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 | Electrical & Controls
Item | CWP 22 | IP-2 | Influent Pump No.2, 3 HP, explosion-proof (XP), 4.8 FLA | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-INFLUENT-PUMPS-SMALL (Process & Mechanical); PROPOSED-INFLUENT-PUMPS-LARGE (Process & Mechanical); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 |  | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 | Electrical & Controls
Item | CWP 22 | IP-3 | Influent Pump No.3, 5 HP, explosion-proof (XP), 7.6 FLA | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-INFLUENT-PUMPS-SMALL (Process & Mechanical); PROPOSED-INFLUENT-PUMPS-LARGE (Process & Mechanical); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 |  | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 | Electrical & Controls
Item | CWP 22 | IP-4 | Influent Pump No.4, 5 HP, explosion-proof (XP), 7.6 FLA | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-INFLUENT-PUMPS-SMALL (Process & Mechanical); PROPOSED-INFLUENT-PUMPS-LARGE (Process & Mechanical); PROPOSED-Submersible-Pump-Equipment (Contract & General) | #36, #167, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 |  | E4.1; E4.2; E6.1; E6.3; E8.1; E8.2; E8.3; E8.4 | Electrical & Controls
Item | CWP 22 | PROPOSED-Influent-Pump-Seal-Fail-Overtemp-Relays | Influent pump seal-fail and overtemperature relays (4), Mini-CAS or equal, furnished by the pump manufacturer, installed in the IPS panel | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-IPS-MOTOR-SAVER-RELAYS (Process & Mechanical) | #42, #214 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E8.1 |  | E8.1 | Electrical & Controls
Item | CWP 22 | PROPOSED-Submersible-Pump-Equipment | Submersible pump equipment | Influent Pump Station | Install | 22-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 12 | 7 | IP-3 (Electrical & Controls); IP-4 (Electrical & Controls); PROPOSED-INFLUENT-PUMPS-SMALL (Process & Mechanical); PROPOSED-INFLUENT-PUMPS-LARGE (Process & Mechanical); IP-2 (Electrical & Controls); IP-1 (Electrical & Controls) | #36, #251 | Inferred | 1; Equipment Alternate A |  | 00 41 00; 01 33 00; 01 70 00; 01 91 00; 01 45 00 | 00 41 00; 01 33 00; 01 70 00; 01 91 00; 01 45 00 | Contract & General
Section | CWP 23 | HVAC & Ventilation | 15 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-02-09 | [5 empty] | 15 | 0% | 0% | 0%
Item | CWP 23 | PROPOSED-BLOWER-BLDG-WALL-FANS | Blower Building wall fans (2), Acme FQ18G6, 3,300 CFM, 1/2 HP, 120 V, each on its own Schaffer TH109 thermostat, with EBE445 gravity combination louver | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | N | N | 0 | 0 | EF-2 (Electrical & Controls); PROPOSED-Exhaust-Fans-Blower-Building (Structural & Building); EF-1 (Electrical & Controls) | #20 | Inferred | 1 |  | 23 34 00 | 23 34 00 | Process & Mechanical
Item | CWP 23 | PROPOSED-BLOWER-BLDG-MOTORIZED-LOUVER | Blower Building motorized louvered vent, 36 x 84 in., Pottoroff EXD-645 with AF120 120 V spring-return actuator | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | N | N | 0 | 0 | ML-1 (Electrical & Controls); PROPOSED-Louver-36x84-Motorized (Structural & Building) | #21 | Inferred | 1 |  | 23 34 00 | 23 34 00 | Process & Mechanical
Item | CWP 23 | PROPOSED-BLOWER-BLDG-MANUAL-LOUVER | Blower Building manual louvered vent, 24 x 24 in., Pottoroff EXD-645 | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Blower-Building-Manual-Louver (Electrical & Controls); PROPOSED-Louver-24x24-Manual (Structural & Building) | #22 | Inferred | 1 |  | 23 34 00 | 23 34 00 | Process & Mechanical
Item | CWP 23 | EF-1 | Exhaust Fan 1, Blower Building (motor marked 1/2), circuit LP1-5 | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-BLOWER-BLDG-WALL-FANS (Process & Mechanical); PROPOSED-Exhaust-Fans-Blower-Building (Structural & Building) | #20, #203 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.2; E6.2 |  | E2.2; E6.2 | Electrical & Controls
Item | CWP 23 | EF-2 | Exhaust Fan 2, Blower Building (motor marked 1/2), circuit LP1-7 | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-BLOWER-BLDG-WALL-FANS (Process & Mechanical); PROPOSED-Exhaust-Fans-Blower-Building (Structural & Building) | #20, #203 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.2; E6.2 |  | E2.2; E6.2 | Electrical & Controls
Item | CWP 23 | ML-1 | Motorized louver ML-1, Blower Building (motor marked 1/6), louver and HVAC control circuit LP1-3 | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Louver-36x84-Motorized (Structural & Building); PROPOSED-BLOWER-BLDG-MOTORIZED-LOUVER (Process & Mechanical) | #21, #203 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.2 |  | E2.2 | Electrical & Controls
Item | CWP 23 | PROPOSED-Blower-Building-Manual-Louver | Manual louver, Blower Building | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Louver-24x24-Manual (Structural & Building); PROPOSED-BLOWER-BLDG-MANUAL-LOUVER (Process & Mechanical) | #22 | Inferred | 1 (Inferred per 04) | E2.2 |  | E2.2 | Electrical & Controls
Item | CWP 23 | PROPOSED-Louver-36x84-Motorized | Louver, 36 in x 84 in, motorized — Blower Building west wall | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | ML-1 (Electrical & Controls); PROPOSED-BLOWER-BLDG-MOTORIZED-LOUVER (Process & Mechanical) | #21, #228 | Inferred | 1 (Inferred per 04) | A1.1; A1.2 |  | A1.1; A1.2 | Structural & Building
Item | CWP 23 | PROPOSED-Louver-24x24-Manual | Louver, 24 in x 24 in, manual — Blower Building west wall | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Blower-Building-Manual-Louver (Electrical & Controls); PROPOSED-BLOWER-BLDG-MANUAL-LOUVER (Process & Mechanical) | #22, #228 | Inferred | 1 (Inferred per 04) | A1.1; A1.2 |  | A1.1; A1.2 | Structural & Building
Item | CWP 23 | PROPOSED-Exhaust-Fans-Blower-Building | Exhaust fans (2) with 24 in x 24 in wall vents — Blower Building east wall | Blower Building | Install | 23-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | EF-2 (Electrical & Controls); PROPOSED-BLOWER-BLDG-WALL-FANS (Process & Mechanical); EF-1 (Electrical & Controls) | #20, #228 | Inferred | 1 (Inferred per 04) | A1.1; A1.2 |  | A1.1; A1.2 | Structural & Building
Item | CWP 23 | PROPOSED-EXISTING-BLDG-WALL-FANS | Existing Dewatering/Train 1&2 Building wall fans (3), Acme FQ18G6, 3,300 CFM, each on a manual on/off switch, with gravity combination louvers | Existing Dewatering/Train 1&2 Building Area | Install | 23-C02 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Existing dewatering / treatment building | 2023-03-31 | N | N | 0 | 0 | EF-3 (Electrical & Controls); EF-4 (Electrical & Controls); EF-5 (Electrical & Controls); PROPOSED-WWTP-Building-Exhaust-Fan-24x24 (Structural & Building) | #26 | Unresolved | 1 |  | 23 34 00 | 23 34 00 | Process & Mechanical
Item | CWP 23 | PROPOSED-EXISTING-BLDG-LOUVERS | Existing Dewatering/Train 1&2 Building manual louvered vents (2), 36 x 84 in., Pottoroff EXD-645 | Existing Dewatering/Train 1&2 Building Area | Install | 23-C02 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Existing dewatering / treatment building | 2023-03-31 | N | N | 0 | 0 | PROPOSED-WWTP-Building-Louver-3x7 (Structural & Building) | #27 | Inferred | 1 |  | 23 34 00 | 23 34 00 | Process & Mechanical
Item | CWP 23 | EF-3 | Exhaust Fan EF-3, Treatment Building, motor marked 1/2, circuit LP2-7 (1,127 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 23-C02 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-WWTP-Building-Exhaust-Fan-24x24 (Structural & Building); PROPOSED-EXISTING-BLDG-WALL-FANS (Process & Mechanical) | #26, #194, #205, #210 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.2; E8.3; E9.3 |  | E4.1; E6.2; E8.3; E9.3 | Electrical & Controls
Item | CWP 23 | EF-4 | Exhaust Fan EF-4, Treatment Building, motor marked 1/2, circuit LP2-9 (1,127 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 23-C02 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-WWTP-Building-Exhaust-Fan-24x24 (Structural & Building); PROPOSED-EXISTING-BLDG-WALL-FANS (Process & Mechanical) | #26, #194, #210 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.2; E8.3; E9.3 |  | E4.1; E6.2; E8.3; E9.3 | Electrical & Controls
Item | CWP 23 | EF-5 | Exhaust Fan EF-5, Treatment Building, motor marked 1/2, circuit LP2-11 (1,127 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 23-C02 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | HVAC & Ventilation — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-WWTP-Building-Exhaust-Fan-24x24 (Structural & Building); PROPOSED-EXISTING-BLDG-WALL-FANS (Process & Mechanical) | #26, #194, #205 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.2; E8.3; E9.3 |  | E4.1; E6.2; E8.3; E9.3 | Electrical & Controls
Section | CWP 26 | Electrical, Instrumentation & Controls | 103 items · 0 overdue · 0 complete |  |  |  | 2023-03-15 | 2024-10-16 | [5 empty] | 103 | 0% | 0% | 0%
Item | CWP 26 | PROPOSED-Construction-Power-Service | Dedicated construction power service (contractor-provided, contractor-paid energy) | Not stated | Temporary | 26-C12 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Electrical, Instrumentation & Controls — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary-Construction-Power (Contract & General) | #67 | Verified | 6 (Division 26 per 04) | Not shown | 26 05 00 | 26 05 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Temporary-Construction-Power | Temporary construction power and lighting (poles, transformer if required, cords, outlets, lamps) | Site | Temporary | 26-C12 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Electrical, Instrumentation & Controls — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Construction-Power-Service (Electrical & Controls) | #67 | Unresolved | 1 |  | 01 50 00 | 01 50 00 | Contract & General
Item | CWP 26 | MCC | Motor control center, 480 V 3-ph 4-W, Blower Building, Allen-Bradley Centerline 2100 IntelliCENTER ¦ Blower Building motor control center — 8 sections at 20 in, 160 in total per Add. 4 | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 5 | 2 | PROPOSED-Motor-Control-Center (Contract & General) | #23, #225 | Inferred | 6 ¦ 6 (Inferred per 04) | E1.1; E2.1; E2.2; E6.1; E6.2; E6.3; E7.0; E9.1; E9.2; A1.1 | 26 24 19 | E1.1; E2.1; E2.2; E6.1; E6.2; E6.3; E7.0; E9.1; E9.2; 26 24 19; A1.1 | Electrical & Controls; Structural & Building
Item | CWP 26 | MCP | Main Control Panel (PLC), Blower Building ¦ Main control panel (MCP) — relocated per Add. 4 | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 4 | 2 | PROPOSED-PLC-Control-Panel (Contract & General) | #24, #226 | Unresolved | 6 ¦ 6 (Inferred per 04) | E2.1; E2.2; E6.2; E6.3; E7.0; E7.1; E7.2; E7.3; E7.4; E7.5; E7.6; E7.7; A1.1 | 26 80 00 | E2.1; E2.2; E6.2; E6.3; E7.0; E7.1; E7.2; E7.3; E7.4; E7.5; E7.6; E7.7; 26 80 00; A1.1 | Electrical & Controls; Structural & Building
Item | CWP 26 | LP-1 | Lighting panel LP1, 120/240 V 1-ph 3-W, 100 A bus, 100 A main breaker, 10,000 AIC, surface mounted | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 3 | 1 |  |  | Inferred | 6 | E2.1; E2.2; E6.1; E6.2; E9.1; E9.3 | 26 24 16 | E2.1; E2.2; E6.1; E6.2; E9.1; E9.3; 26 24 16 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Power-Handholes | Electric power handholes at the Blower Building (2 shown) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | N | N | 0 | 0 |  |  | Verified-Visual | 6 | E2.1; E10.1 | 26 05 33 | E2.1; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Control-Signal-Handholes | Electric control and signal handholes at the Blower Building (2 shown) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | N | N | 0 | 0 |  |  | Verified-Visual | 6 | E2.1; E10.1 | 26 05 33 | E2.1; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Smoke-Heat-Detector | Ceiling smoke/heat detector, System Sensor 4WTAR-B, Form C relay, sounder, 4-wire | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 1 | 2 |  |  | Verified | 6 | E2.1; E6.3; E7.3 | 26 80 00 | E2.1; E6.3; E7.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Door-Intrusion-Switch | Door intrusion switch, magnetic reed SPDT, Interlogix Sentrol 2807T or equal | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 1 | 2 |  |  | Verified | 6 | E2.1; E6.3; E7.3 | 26 80 00 | E2.1; E6.3; E7.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-2W-Pressure-Transducer | 2W system pressure transducer, 0–150 psi, 4–20 mA, Blower Building | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 1 | 2 | PIT-620 (Process & Mechanical) | #48 | Verified | 6 | E2.1; E6.3; E7.5 | 26 80 00; 26 80 00 | E2.1; E6.3; E7.5; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-High-Temperature-Switches | High-temperature switches at the aeration blowers (typ.) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #118 | Verified-Visual | 6 | E2.1; E7.3 |  | E2.1; E7.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Grounding-Electrode-System | Blower Building grounding electrode system (ground rods, concrete-encased electrode, structural steel, metal water pipe) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | N | Y | 0 | 1 |  |  | Verified | 6 | E2.1; E10.1 | 26 05 26 | E2.1; E10.1; 26 05 26 | Electrical & Controls
Item | CWP 26 | L1 (Blower Building) | Light fixture type L1: narrow LED 4-ft, vapor tight, 120 V, 42 VA (Acuity CSVT-L48…) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 2 | 1 |  |  | Verified-Visual | 6 | E2.2 | 26 51 19 | E2.2 | Electrical & Controls
Item | CWP 26 | L2 (Blower Building) | Light fixture type L2: LED wall pack, wet location, photocell, 120 V, 17 VA (Acuity ARC1 LED…) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 2 | 1 |  |  | Verified-Visual | 6 | E2.2 | 26 51 19 | E2.2 | Electrical & Controls
Item | CWP 26 | X1 (Blower Building) | Light fixture type X1: LED emergency combo with battery pack, 120 V, 6 VA (Lithonia ECC) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 2 | 1 |  |  | Verified-Visual | 6 | E2.2 | 26 51 19 | E2.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-Building-Ventilation-Control-Panel | Ventilation control panel: relay controls, one thermostat per exhaust fan, louver interlock | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #119 | Verified | 6 | E2.2 |  | E2.2 | Electrical & Controls
Item | CWP 26 | T2 | Transformer T2, 20 kVA, 480–120/240V (MCC; feeds load center LP1) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | N | 2 | 0 |  |  | Inferred | 6 | E6.1; E9.1 | 26 22 13 | E6.1; E9.1; 26 22 13 | Electrical & Controls
Item | CWP 26 | PROPOSED-VFDs-in-MCC | Variable frequency drives in the MCC (10), Allen-Bradley PowerFlex 753 with Ethernet module, each with a 3% line-side reactor; dV/dt filters on motor runs over 50 ft | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 5 | 2 |  | #176 | Inferred | 6 | E6.1; E7.0; E7.3; E7.4; E7.7; E9.1; E9.2 | 26 29 23 | E6.1; E7.0; E7.3; E7.4; E7.7; E9.1; E9.2; 26 29 23 | Electrical & Controls
Item | CWP 26 | PROPOSED-Blower-PTC-Relay-Modules | Blower motor PTC relay modules (5), furnished by the blower supplier, installed in the main PLC control panel | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #127, #214 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E7.1; E7.2; E7.3 |  | E7.1; E7.2; E7.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-Electrical-Equipment-Housekeeping-Pads | Concrete housekeeping pads under floor-mounted electrical equipment (MCC, main PLC panel, IPS panel) | Blower Building (MCC, main PLC panel); Influent Pump Station (IPS panel) | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | N | N | 0 | 0 |  | #213 | Inferred | 6 (Division 26 per 04); concrete per civil specifications | E7.1; E8.1; E9.1 | 26 05 00 | E7.1; E8.1; E9.1; 26 05 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Motor-Control-Center | Motor control center (MCC) | Blower Building | Install | 26-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Blower Building | 2023-03-14 | Y | Y | 9 | 3 | MCC (Electrical & Controls) | #23, #253 | Inferred | 6 |  | 00 31 13; 01 33 00; 01 70 00 | 00 31 13; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-DB-Local-Disconnect | Local disconnect for digester blower DB, NEMA 4X stainless steel | Not stated — at DB (see DB row) | Install | 26-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Aerobic digester | 2023-03-14 | Y | N | 1 | 0 |  |  | Verified-Visual | 6 | E2.1 | 26 28 16 | E2.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Digester-Level-Transducer | Digester level transducer: WIKA submersible, 316 SS, 0–15 psi, LevelGuard, 4–20 mA, vented, desiccant, NEMA 4X; J-box with terminals and desiccant on the handrail | Digester | Install | 26-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Aerobic digester | 2023-03-14 | Y | Y | 1 | 3 | S1–S2 [Aerobic Digester] (Process & Mechanical) | #58 | Unresolved | 6 | E5.1; E6.3; E7.1; E7.5 | 26 80 00 | E5.1; E6.3; E7.1; E7.5 | Electrical & Controls
Item | CWP 26 | PROPOSED-Hot Box #1 flow meter | 1-inch flow meter in Hot Box #1, 'per electrical design requirements' | Site | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | N | N | 0 | 0 | PROPOSED-2W-FLOW-METER (Process & Mechanical); PROPOSED-2W-Flow-Meter (Electrical & Controls) | #11 | Inferred | 1 | C7.6 (Det. 1) |  | C7.6 | Civil & Site
Item | CWP 26 | PROPOSED-EFFLUENT-FLOW-METER | Plant effluent flow meter, 8-inch electromagnetic, 0-940 gpm | Site (upstream of UV per G0.5) | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Effluent-Flow-Meter (Electrical & Controls); PROPOSED-8in-Effluent-Flow-Meter (Contract & General) | #10 | Inferred | 6 | G0.5; G0.6; G0.7 |  | G0.5; G0.6; G0.7 | Process & Mechanical
Item | CWP 26 | PROPOSED-Utility-Transformer-480V | Utility transformer, 480Y/277V, 225 kVA (new; furnished and installed by OPALCO) | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified-Visual | 6 (contractor scope only: pad modification, secondary conduit and wire) | E0.2; E1.1; E6.1 | 26 05 00 | E0.2; E1.1; E6.1 | Electrical & Controls
Item | CWP 26 | P-SEC | Utility secondary conduit and conductors, new utility transformer to service equipment (by contractor) | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | N | Y | 0 | 3 |  |  | Verified-Visual | 6 | E1.1; E6.1; E6.3 | 26 05 19; 26 05 33; 26 05 00 | E1.1; E6.1; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-CT-Enclosure-and-Meter-Base | CT enclosure, landing pads and meter base (new; meter and CTs by utility) | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 | E0.2; E1.1; E6.1; E6.3 | 26 05 00 | E0.2; E1.1; E6.1; E6.3 | Electrical & Controls
Item | CWP 26 | ATS | Automatic transfer switch, service-entrance rated, 480Y/277V, 400 A (permanent) | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 3 | 3 | PROPOSED-Automatic-Transfer-Switch (Contract & General) | #66, #255 | Unresolved | 6; 18 — Unresolved (see 04) for the temporary-generator connection | E1.1; E6.1; E6.3; E7.3 | 26 36 00 | E1.1; Add. 4 Generator Exhibit; E6.1; E6.3; E7.3; 26 36 00 | Electrical & Controls
Item | CWP 26 | MDP | Main distribution panel MDP, 480Y/277V 3-ph 4-W, 400 A bus, main lugs only, 42,000 AIC, surface mounted, with SPD | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 3 | 1 |  |  | Inferred | 6 | E1.1; E6.1; E6.2; E6.3 | 26 24 16 | E1.1; E6.1; E6.2; E6.3; 26 24 16 | Electrical & Controls
Item | CWP 26 | TS | Transformer TS, 75 kVA, 480–208Y/120V | Electric Service Area | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | N | 2 | 0 |  |  | Inferred | 6 | E1.1; E6.1; E6.3 | 26 22 13 | E1.1; E6.1; E6.3; 26 22 13 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-Grounding-Electrode-System | Existing grounding electrode system (kept; new equipment and electrodes bonded to it) | Electric Service Area / existing buildings | Modify / connect | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | N | N | 0 | 0 |  |  | Verified | 6 | E0.2; E1.1 | 26 05 26 | E0.2; E1.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Conduit-and-Conductor-Runs | Conduit and conductor runs per the E6.3 schedules: 40 named power runs (+2 unnamed UV controller circuits, AC spare) and 38 named 24 VDC control/signal runs (+DC spare) | Site-wide | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | N | Y | 0 | 2 |  |  | Inferred | 6 | E6.3; E10.1; E10.2 | 26 05 19; 26 05 33 | E6.3; E10.1; E10.2; 26 05 19; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-8in-Effluent-Flow-Meter | 8-inch effluent flow meter | Not stated | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 9 | 3 | PROPOSED-Effluent-Flow-Meter (Electrical & Controls); PROPOSED-EFFLUENT-FLOW-METER (Process & Mechanical) | #10, #253 | Inferred | Not stated |  | 00 31 13; 01 33 00; 01 70 00 | 00 31 13; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-Automatic-Transfer-Switch | Automatic transfer switch (permanent) | Not stated | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 9 | 3 | ATS (Electrical & Controls) | #66, #253, #255 | Unresolved | 18 — Unresolved (see 04) |  | 01 33 00; 01 70 00 | 00 41 00; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-480V-Electrical-Service | 480V electrical service (new) | Not stated | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 9 | 3 |  | #253 | Inferred | 6 |  | 00 31 13; 01 33 00; 01 70 00 | 00 31 13; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-PLC-Control-Panel | PLC control panel (new) | Not stated | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 10 | 5 | MCP (Electrical & Controls) | #24, #253 | Inferred | 6 |  | 00 31 13; 00 73 00; 01 33 00; 01 70 00 | 00 31 13; 00 73 00; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-Magnetic-Flow-Meters | Magnetic flow meters (all units; count and locations not stated) | Not stated | Install | 26-C10 | 2023-04-01 | 2023-10-04 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-03-14 | Y | Y | 11 | 4 |  | #251, #253 | Inferred | Not stated |  | 01 91 00; 01 33 00; 01 70 00 | 01 91 00; 01 33 00; 01 70 00 | Contract & General
Item | CWP 26 | PROPOSED-WAS-FLOW-METER | WAS flow meter, 2-inch, on the WAS line to the digester, per electrical design requirements | Sludge Pump and Valving Area | Install | 26-C11 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Sludge pumps and valving | 2023-03-14 | N | N | 0 | 0 | PROPOSED-WAS-Dewatering-Flow-Meter (Electrical & Controls) | #43 | Unresolved | 6 | C6.2 |  | C6.2 | Process & Mechanical
Item | CWP 26 | P-TPS | Replacement 200 A 208Y/120V feeder, existing switchgear to Panel TPS | Site — Electric Service Area to existing Treatment Building | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | N | Y | 0 | 3 |  |  | Verified | 6 | E0.2; E1.1; E4.1; E6.1; E6.3 | 26 05 19; 26 05 33 | E0.2; E1.1; E4.1; E6.1; E6.3 | Electrical & Controls
Item | CWP 26 | TPS | Panel TPS, 208Y/120V 3-ph 4-W, 200 A (kept; re-fed) | Existing Treatment Building | Modify / connect | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 | E0.2; E1.1; E4.1; E6.1 |  | E0.2; E1.1; E4.1; E6.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-208V-400A-Distribution-Panel | Existing 208Y/120V 400 A distribution panel (Square-D I-Line), Office Building, re-fed from transformer TS | Existing Office Building | Modify / connect | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Inferred | 6 | E0.2; E1.1; E6.1; E6.3 |  | E0.2; E1.1; E6.1; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-Treatment-Building-Power-Handhole | Electric power handhole at the Treatment Building / IPS panel location | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | N | N | 0 | 0 |  |  | Verified | 6 | E4.1; E10.1 | 26 05 33 | E4.1; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-Treatment-Building-Control-Signal-Handhole | Electric control and signal handhole at the Treatment Building / IPS panel location | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | N | N | 0 | 0 |  |  | Verified | 6 | E4.1; E7.0; E10.1 | 26 05 33 | E4.1; E7.0; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-WAS-Dewatering-Flow-Meter | Dewatering flow meter ("WAS flow meter" on E7.0), Promag W400 with local display, Cat 6 to the IPS panel | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 2 | 3 | PROPOSED-WAS-FLOW-METER (Process & Mechanical) | #43, #184 | Inferred | 6 | E4.1; E6.3; E7.0; E10.2 | 26 80 00 | E4.1; E6.3; E7.0; E10.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-WAS-and-Sludge-Pump-Local-Disconnects | Local motor disconnects for WP-1, WP-2 and SD-1 (3) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | N | 3 | 0 | PROPOSED-SLUDGE-PUMP-LOCAL-PANELS (Process & Mechanical) | #62 | Inferred | 6 | E4.1; E6.1 | 26 28 16 | E4.1; E6.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Treatment-Building-Ventilation-Control-Panel | Ventilation control panel, Treatment Building, NEMA 4X stainless steel | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 3 | 4 |  |  | Unresolved | 6 | E4.1; E6.2; E8.3; E8.4; E9.3 | 26 80 00 | E4.1; E6.2; E8.3; E8.4; E9.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Methane-Sensor | Methane gas sensor, Treatment Building, circuit LP2-4 (500 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 3 | 3 |  |  | Verified-Visual | 6 | E4.1; E6.2; E8.4; E8.5; E9.3 | 26 80 00 | E4.1; E6.2; E8.4; E8.5; E9.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-H2S-Sensor | Hydrogen sulfide (H2S) sensor, Treatment Building, circuit LP2-2 (500 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 3 | 3 |  |  | Verified-Visual | 6 | E4.1; E6.2; E8.4; E8.5; E9.3 | 26 80 00 | E4.1; E6.2; E8.4; E8.5; E9.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Gas-Alarm-Light-and-Horn | Local alarm light and horn for ventilation and gas monitoring, Treatment Building | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 2 | 3 |  |  | Verified-Visual | 6 | E4.1; E8.4 | 26 80 00 | E4.1; E8.4; 26 80 00 | Electrical & Controls
Item | CWP 26 | L2 (Treatment Building) | Light fixture type L2 wall packs on circuit LP2-3 ("wall pack lighting", 500 VA) | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 26-C15 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-03-14 | Y | Y | 4 | 3 |  |  | Inferred | 6 | E4.1; E6.2; E8.1 | 26 51 19 | E4.1; E6.2; E8.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Effluent-Flow-Meter | Effluent magnetic flow meter in vault, Promag W400, remote housing, IP68 Type 6 potted submersible sensor, two 316L grounding rings | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | Y | Y | 1 | 3 | PROPOSED-8in-Effluent-Flow-Meter (Contract & General); PROPOSED-EFFLUENT-FLOW-METER (Process & Mechanical) | #10 | Inferred | 6 | E5.1; E6.3; E7.0; E10.2 | 26 80 00 | E5.1; E6.3; E7.0; E10.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-Effluent-Flow-Meter-Transmitter-Panel | Effluent flow meter transmitter panel: stainless local control panel with the transmitter and instrument terminals, on handrail or rack with SS hardware | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | Y | Y | 1 | 3 |  |  | Verified | 6 | E5.1; E6.3 | 26 80 00 | E5.1; E6.3; 26 80 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-UV-Control-Panel-1 | UV control panel 1 (UV system controller), furnished with the UV system, installed by the contractor | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | Not stated | Not stated | 0 | 0 | PROPOSED-UV-CONTROL-PANELS (Process & Mechanical) | #55 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E5.1; E6.3 |  | E5.1; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-UV-Control-Panel-2 | UV control panel 2 (UV system controller), furnished with the UV system, installed by the contractor | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | Not stated | Not stated | 0 | 0 | PROPOSED-UV-CONTROL-PANELS (Process & Mechanical) | #55 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E5.1; E6.3 |  | E5.1; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-UV-Power-Distribution-1 | UV power distribution 1: stainless splitter panel within 10 ft of the module power end, wiring gutter, J-boxes and (3) duplex GFCI power distribution receptacles (PDRs) with in-use wet-location covers on SS Unistrut; SS conduit and fittings | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | N | Y | 0 | 2 | PROPOSED-UV-CONTROL-PANELS (Process & Mechanical) | #55 | Verified-Visual | 6 | E5.1; E6.2; E6.3 | 26 27 26 | E5.1; E6.2; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-UV-Power-Distribution-2 | UV power distribution 2: stainless splitter panel within 10 ft of the module power end, wiring gutter, J-boxes and (3) duplex GFCI power distribution receptacles (PDRs) with in-use wet-location covers on SS Unistrut; SS conduit and fittings | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | N | Y | 0 | 2 | PROPOSED-UV-CONTROL-PANELS (Process & Mechanical) | #55 | Verified-Visual | 6 | E5.1; E6.2; E6.3 | 26 27 26 | E5.1; E6.2; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-UV-Area-Pole-Light | UV-area pole light: 4-in square aluminum pole 12 ft on a concrete base secured to the basin side, photocell, local on/off switch, WP/GFCI receptacle; Lithonia "#DXS0-LED-P3-30K-T3M-MVOLT-SPA-DNAXD" (as printed) or equal | UV Disinfection Chamber | Install | 26-C16 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber | 2023-03-14 | Y | Y | 2 | 2 |  |  | Unresolved | 6 | E5.1; E6.3 | 26 51 19 | E5.1; E6.3 | Electrical & Controls
Item | CWP 26 | S1–S2 [Aerobic Digester] | Aerobic digester transducer level sensor(s): S1 high alarm 25.55, S2 low alarm 15.30 | UV Disinfection Chamber & Digester | Install | 26-C17 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — UV chamber and digester | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Digester-Level-Transducer (Electrical & Controls) | #58 | Inferred | 1 | C5.3 |  | C5.3 | Process & Mechanical
Item | CWP 26 | PROPOSED-2W-Flow-Meter | 2W flow meter, 1-in Promag W400, 24 VAC/DC, EtherNet/IP, local display, NEMA 4X, in Hot Box #1 | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | Y | 1 | 2 | PROPOSED-2W-FLOW-METER (Process & Mechanical); PROPOSED-Hot Box #1 flow meter (Civil & Site) | #11 | Inferred | 6 | E4.3; E6.3; E7.0; E10.2 | 26 80 00 | E4.3; E6.3; E7.0; E10.2 | Electrical & Controls
Item | CWP 26 | LSH-111 | 2W float F1: high level alarm and redundant valve close at 22.00 (factory float tree) | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | Y | 1 | 2 | F1–F4 [2W Pump Station] (Process & Mechanical) | #46 | Verified-Visual | 6 | E4.3; E7.3 | 26 80 00 | E4.3; E7.3 | Electrical & Controls
Item | CWP 26 | F2 (2W Pump Station) | 2W float F2: valve close at 20.00 (factory float tree) | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | Y | 1 | 2 | F1–F4 [2W Pump Station] (Process & Mechanical) | #46 | Verified-Visual | 6 | E4.3; E7.3 | 26 80 00 | E4.3; E7.3 | Electrical & Controls
Item | CWP 26 | F3 (2W Pump Station) | 2W float F3: valve open at 19.00 (factory float tree) | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | Y | 1 | 2 | F1–F4 [2W Pump Station] (Process & Mechanical) | #46 | Verified-Visual | 6 | E4.3; E7.3 | 26 80 00 | E4.3; E7.3 | Electrical & Controls
Item | CWP 26 | LSL-111 | 2W float F4: low level alarm and pumps off at 15.00 (factory float tree) | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | Y | 1 | 2 | F1–F4 [2W Pump Station] (Process & Mechanical) | #46 | Verified-Visual | 6 | E4.3; E7.3 | 26 80 00 | E4.3; E7.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-2W-Pump-Local-Disconnects | Local motor disconnects for the two 2W pumps (2) | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Y | N | 2 | 0 |  |  | Inferred | 6 | E6.1 | 26 28 16 | E6.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Hot-Box-Heat-Trace | Heat trace on all exposed 2W piping in Hot Boxes #1 and #2: Raychem BTV self-regulating or equal, dedicated 120 V 20 A GFEP circuits (LP1-10, LP1-12), NEMA 4X thermostat, end-of-line kit with indicator light | 2W Pump Station | Install | 26-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #124 | Verified | 6 | E4.3; E6.2; E6.3 |  | E4.3; E6.2; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-Train 2 flow meter | Train 2 flow meter, 8-inch, in Train 2 flow meter vault | Train 2 | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Plant-2-Flow-Meter (Electrical & Controls); PROPOSED-TRAIN-2-FLOW-METER (Process & Mechanical) | #7 | Inferred | 1 | C7.10 (Det. 1) |  | C7.10 | Civil & Site
Item | CWP 26 | PROPOSED-INFLUENT-FLOW-METER | Influent flow meter, 6-inch electromagnetic, 0-880 gpm | Influent Flow Splitter | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Influent-Flow-Meter (Electrical & Controls) | #9 | Inferred | 6 | G0.5; G0.6; G0.7; C3.1 |  | G0.5; G0.6; G0.7; C3.1 | Process & Mechanical
Item | CWP 26 | PROPOSED-TRAIN-2-FLOW-METER | Train 2 influent flow meter, 8-inch electromagnetic, 0-470 gpm | Influent Flow Splitter | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Plant-2-Flow-Meter (Electrical & Controls); PROPOSED-Train 2 flow meter (Civil & Site) | #7 | Inferred | 6 | G0.5; G0.6; G0.7; C3.1 |  | G0.5; G0.6; G0.7; C3.1 | Process & Mechanical
Item | CWP 26 | PROPOSED-TRAIN-3-FLOW-METER | Train 3 influent flow meter, 8-inch electromagnetic, 0-470 gpm | Influent Flow Splitter | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Plant-3-Flow-Meter (Electrical & Controls); PROPOSED-Train 3 flow meter (Civil & Site) | #8 | Inferred | 6 | G0.5; G0.6; G0.7; C3.1 |  | G0.5; G0.6; G0.7; C3.1 | Process & Mechanical
Item | CWP 26 | PROPOSED-PLANT-DRAIN-FLOW-METER ¦ PROPOSED-Plant-Drain-Flow-Meter | Plant drain flow meter, 4-inch electromagnetic, 0-200 gpm ¦ Plant drain magnetic flow meter, Promag W400, remote transmitter at the IPS panel | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 5 |  |  | Inferred | 6 | G0.5; G0.7; E4.1; E6.3; E7.0; E8.1; E10.2 | 26 80 00 | G0.5; G0.7; E4.1; E6.3; E7.0; E8.1; E10.2 | Process & Mechanical; Electrical & Controls
Item | CWP 26 | F1 (Influent Pump Station) | Float switch F1, Eco-Float GP60NONC, non-mercury NO/NC — redundant large lag on at 19.00 (with timer) | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 5 | F1–F4 [Influent Pump Station] (Process & Mechanical) | #40 | Inferred | 6 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | 26 80 00 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | Electrical & Controls
Item | CWP 26 | F2 (Influent Pump Station) | Float switch F2, Eco-Float GP60NONC, non-mercury NO/NC — redundant large lead on at 18.50 | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 5 | F1–F4 [Influent Pump Station] (Process & Mechanical) | #40 | Inferred | 6 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | 26 80 00 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | Electrical & Controls
Item | CWP 26 | F3 (Influent Pump Station) | Float switch F3, Eco-Float GP60NONC, non-mercury NO/NC — redundant small lag on at 18.00 | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 5 | F1–F4 [Influent Pump Station] (Process & Mechanical) | #40 | Inferred | 6 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | 26 80 00 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | Electrical & Controls
Item | CWP 26 | F4 (Influent Pump Station) | Float switch F4, Eco-Float GP60NONC, non-mercury NO/NC — redundant small lead on at 17.50 | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 5 | F1–F4 [Influent Pump Station] (Process & Mechanical) | #40 | Inferred | 6 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | 26 80 00 | E4.1; E4.2; E6.3; E8.1; E8.3; E10.1 | Electrical & Controls
Item | CWP 26 | LT (Influent Pump Station) | Submersible level transducer: WIKA pressure transmitter, 316 SS, 0–15 psi, LevelGuard, 4–20 mA loop powered, vented, NEMA 4X termination enclosure | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 3 | 4 | PROPOSED-IPS-LEVEL-TRANSDUCER (Process & Mechanical) | #39 | Unresolved | 6 | E4.1; E4.2; E6.3; E8.1; E8.5; E10.1 | 26 80 00 | E4.1; E4.2; E6.3; E8.1; E8.5; E10.1 | Electrical & Controls
Item | CWP 26 | IPS | Influent Pump Station control panel, 480 V 3-ph 3-W, NEMA 4X SS: 60 A main, starters for IP-1 to IP-4, T3 and LP2, Allen-Bradley CompactLogix PLC (1768-ENBT), network switch, flow-meter transmitters | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 4 | 5 |  |  | Unresolved | 6 | E4.1; E6.1; E6.3; E7.0; E7.2; E8.1; E8.2; E8.3; E8.4; E8.5; E8.6; E9.1 | 26 80 00 | E4.1; E6.1; E6.3; E7.0; E7.2; E8.1; E8.2; E8.3; E8.4; E8.5; E8.6; E9.1; 26 80 00 | Electrical & Controls
Item | CWP 26 | T3 | Transformer T3, 10 kVA, 480–120/240V (inside IPS panel; feeds LP2) | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | N | 2 | 0 |  |  | Inferred | 6 | E6.1; E8.1 | 26 22 13 | E6.1; E8.1; 26 22 13 | Electrical & Controls
Item | CWP 26 | LP2 | Panel LP2 (Influent Pump Station panel), 120/240 V 1-ph 3-W, 100 A bus, 60 A main breaker, 10,000 AIC, surface mounted | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 4 | 3 |  |  | Inferred | 6 | E4.1; E6.1; E6.2; E8.1 | 26 24 16 | E4.1; E6.1; E6.2; E8.1; 26 24 16 | Electrical & Controls
Item | CWP 26 | PROPOSED-Influent-Pump-Local-Disconnects | Influent pump motor local disconnects (4) on the building wall within sight of the wet well; outdoor enclosures lockable Type 316 SS with drip shields | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | N | 3 | 0 |  |  | Verified-Visual | 6 | E4.1; E6.1 | 26 28 16 | E4.1; E6.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Influent-Wet-Well-Power-Handhole | Influent wet well pump power handhole, precast, traffic rated, solid bottom with sump and drain | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 |  |  | Verified-Visual | 6 | E4.1; E4.2; E10.1 | 26 05 33 | E4.1; E4.2; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-Influent-Wet-Well-Instrument-Handhole | Influent wet well instrumentation handhole, precast, traffic rated, solid bottom with sump and drain | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 |  |  | Verified-Visual | 6 | E4.1; E4.2; E6.3; E10.1 | 26 05 33 | E4.1; E4.2; E6.3; E10.1; 26 05 33 | Electrical & Controls
Item | CWP 26 | PROPOSED-Influent-Flow-Meter | Influent magnetic flow meter, Endress+Hauser Promag W400, Class I Div 2, EtherNet/IP, remote transmitter at the IPS panel, two 316L grounding rings | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 2 | 4 | PROPOSED-INFLUENT-FLOW-METER (Process & Mechanical) | #9 | Inferred | 6 | E4.1; E6.3; E7.0; E8.1; E10.2 | 26 80 00 | E4.1; E6.3; E7.0; E8.1; E10.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-Plant-2-Flow-Meter | Plant 2 magnetic flow meter ("Train #2 flow meter" on E7.0), Promag W400, remote transmitter at the IPS panel | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 2 | 4 | PROPOSED-Train 2 flow meter (Civil & Site); PROPOSED-TRAIN-2-FLOW-METER (Process & Mechanical) | #7 | Inferred | 6 | E4.1; E6.3; E7.0; E8.1; E10.2 | 26 80 00 | E4.1; E6.3; E7.0; E8.1; E10.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-Plant-3-Flow-Meter | Plant 3 magnetic flow meter ("Train #3 flow meter" on E7.0), Promag W400, remote transmitter at the IPS panel | Influent Pump Station | Install | 26-C08 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-03-14 | Y | Y | 2 | 4 | PROPOSED-Train 3 flow meter (Civil & Site); PROPOSED-TRAIN-3-FLOW-METER (Process & Mechanical) | #8 | Inferred | 6 | E4.1; E6.3; E7.0; E8.1; E10.2 | 26 80 00 | E4.1; E6.3; E7.0; E8.1; E10.2 | Electrical & Controls
Item | CWP 26 | PROPOSED-Train 3 flow meter | Train 3 flow meter, 8-inch, in Train 3 flow meter vault | Train 3 | Install | 26-C14 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Train 3 | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Plant-3-Flow-Meter (Electrical & Controls); PROPOSED-TRAIN-3-FLOW-METER (Process & Mechanical) | #8 | Inferred | 1 | C7.10 (Det. 2) |  | C7.10 | Civil & Site
Item | CWP 26 | PROPOSED-Train-3-Local-Disconnects | Local motor disconnects, NEMA 4X Type 316 SS, for the clarifier drive and two mixers (3) | Train No.3 | Install | 26-C14 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Train 3 | 2023-03-14 | Y | N | 2 | 0 |  |  | Inferred | 6 | E3.1 | 26 28 16 | E3.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Train-3-Pole-Light | Platform pole light: 4-in square aluminum pole, 12 ft, receptacle, photocell, local switch; Lithonia "#DXS0-LED-P3-30K-T3M-MVOLT-SPA-DNAXD" (as printed) or equal | Train No.3 | Install | 26-C14 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Train 3 | 2023-03-14 | Y | Y | 3 | 1 |  |  | Verified | 6 | E3.1; E6.3 | 26 51 19 | E3.1; E6.3 | Electrical & Controls
Item | CWP 26 | PROPOSED-Temporary power generator | Temporary back-up power generator | Site | Temporary | 26-C13 | 2023-09-25 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | 2023-03-14 | N | Y | 0 | 1 | PROPOSED-Temporary-Backup-Generator (Electrical & Controls); PROPOSED-Temporary-Back-Up-Generator (Contract & General) | #14, #255 | Unresolved | 18 — Unresolved (see 04) | G0.3 |  | G0.3 | Civil & Site
Item | CWP 26 | PROPOSED-Temporary-Backup-Generator | Temporary back-up generator (rental), connected to the permanent ATS until the permanent generator arrives; example cut sheet MQ Power 120 kW prime diesel | Electric Service Area | Temporary | 26-C13 | 2023-09-25 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | 2023-03-14 | Y | Y | 2 | 2 | PROPOSED-Temporary power generator (Civil & Site); PROPOSED-Temporary-Back-Up-Generator (Contract & General) | #14, #142, #255 | Unresolved | 18 — Unresolved (see 04) | None (Add. 4 and 26 05 00 only) | 26 05 00 | Add. 4 Generator Exhibit; 26 05 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Temporary-Back-Up-Generator | Temporary back-up generator (rental, 480V) | Not stated | Temporary | 26-C13 | 2023-09-25 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | 2023-03-14 | N | Y | 0 | 0 | PROPOSED-Temporary power generator (Civil & Site); PROPOSED-Temporary-Backup-Generator (Electrical & Controls) | #14, #253, #255 | Unresolved | 18 — Unresolved (see 04) |  | 00 31 13 | 00 31 13; 00 41 00 | Contract & General
Item | CWP 26 | PROPOSED-SCADA-Computer-System | SCADA computer system with Cat 6 network junction box, combo network/telephone outlet and SCADA alarm dialer connection | Lab — existing Office/Lab/Shop Building | Install | 26-C09 | 2023-10-04 | 2024-07-26 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — SCADA / PLC programming | 2023-03-14 | Y | Y | 1 | 3 |  |  | Verified-Visual | 6 (extra SCADA/PLC programming, if ordered, is Item 17 — force account; 04) | E0.3; E6.3; E7.0 | 26 80 00 | E0.3; E6.3; E7.0 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-Utility-Transformer-208V | Existing OPALCO pad-mount utility transformer, 208Y/120V 3-ph, 45 kVA | Electric Service Area | Remove | 26-C04 | 2023-10-05 | 2023-10-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 (coordination only) | E0.2; E1.1 | 26 05 00 | E0.2; E1.1 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-CT-Enclosure-and-Meter | Existing current transformer enclosure and OPALCO utility meter | Electric Service Area | Remove | 26-C04 | 2023-10-05 | 2023-10-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 | E0.2 | 26 05 00 | E0.2; 26 05 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-Meter-Base-and-Wall-Raceway | Existing obsolete meter base and raceway on building wall | Electric Service Area | Remove | 26-C04 | 2023-10-05 | 2023-10-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 | E0.2 | 26 05 00 | E0.2; 26 05 00 | Electrical & Controls
Item | CWP 26 | PROPOSED-Existing-200A-Feeder-to-Panel-TPS | Existing 200 A 208Y/120V power feeder to Panel TPS | Site | Remove | 26-C04 | 2023-10-05 | 2023-10-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  |  | Verified | 6 | E0.2; E1.1 |  | E0.2; E1.1 | Electrical & Controls
Item | CWP 26 | GEN | Standby diesel generator, 480Y/277V, 125 kW / 156 kVA, sound-attenuated outdoor enclosure with sub-base diesel fuel tank (permanent) | Electric Service Area | Install | 26-C07 | 2024-03-01 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Permanent standby generator | 2023-03-14 | Y | Y | 3 | 1 | PROPOSED-Generator-on-S2.4 (Structural & Building); PROPOSED-Permanent-Standby-Generator (Contract & General) | #65, #257 | Unresolved | Unresolved — 1 or 6 (see 04, Other bid-item conflicts #1); Equipment Alternate E | E1.1; E6.1; E6.3; E7.3; E10.3 | 26 32 13 | E1.1; E6.1; E6.3; E7.3; E10.3; 26 32 13 | Electrical & Controls
Item | CWP 26 | PROPOSED-Service-Area-Grounding-Electrode-System | Grounding electrode systems at the new service: utility transformer grounding, generator pad rebar bond, separately derived system grounding | Electric Service Area | Install | 26-C07 | 2024-03-01 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Permanent standby generator | 2023-03-14 | N | Y | 0 | 1 |  |  | Inferred | 6 | E1.1; E6.1; E10.1 | 26 05 26 | E1.1; E6.1; E10.1; 26 05 26 | Electrical & Controls
Item | CWP 26 | PROPOSED-Generator-on-S2.4 | Generator shown on the generator slab — "per civil, attachment by others" | Generator Pad | Install | 26-C07 | 2024-03-01 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Permanent standby generator | 2023-03-14 | Not stated | Not stated | 0 | 0 | GEN (Electrical & Controls); PROPOSED-Permanent-Standby-Generator (Contract & General) | #65, #236, #257 | Unresolved | 1 or 6 — Unresolved (see 04) | S2.4 |  | S2.4 | Structural & Building
Item | CWP 26 | PROPOSED-Permanent-Standby-Generator | Permanent 480V standby generator | Not stated | Install | 26-C07 | 2024-03-01 | 2024-04-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Permanent standby generator | 2023-03-14 | Y | Y | 10 | 5 | GEN (Electrical & Controls); PROPOSED-Generator-on-S2.4 (Structural & Building) | #65, #253, #257 | Unresolved | 1 or 6 — Unresolved (see 04); Equipment Alternate E |  | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00 | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00; CQA Plan | Contract & General
Item | CWP 26 | GEN (E) | Existing standby diesel generator, 208Y/120V 3-ph, 30 kW / 37.5 kVA | Electric Service Area | Remove | 26-C03 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #150 | Verified-Visual | 6 | E0.2 | 26 05 00 | E0.2; 26 05 00 | Electrical & Controls
Item | CWP 26 | SES (E) | Existing 300 A service entrance breaker, SUSE rated, NEMA 3R | Electric Service Area | Remove | 26-C03 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #150 | Verified-Visual | 6 | E0.2 | 26 05 00 | E0.2; 26 05 00 | Electrical & Controls
Item | CWP 26 | ATS (E) | Existing automatic transfer switch, 4-wire, 3-pole | Electric Service Area | Remove | 26-C03 | 2024-05-01 | 2024-05-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | 2023-03-14 | Not stated | Not stated | 0 | 0 |  | #150 | Verified-Visual | 6 | E0.2 | 26 05 00 | E0.2; 26 05 00 | Electrical & Controls
Section | CWP 31 | Earthwork, Dewatering & Erosion Control | 19 items · 0 overdue · 0 complete |  |  |  | 2023-03-15 | 2024-10-16 | [5 empty] | 19 | 0% | 0% | 0%
Item | CWP 31 | PROPOSED-Plastic covering for slopes and stockpiles | Plastic covering for slopes and stockpiles (TESC) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Inferred | 4 | C0.4 (Det. 1); C0.3 | 31 32 11 | C0.4; 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Catch basin inserts | Catch basin inserts (inlet protection, TESC) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 2 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Inferred | 4 | C0.4 (Det. 2); C0.2; C0.3 | 31 32 11 | C0.4; C0.2; 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Filter fabric fence | Filter fabric (silt) fence (TESC) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 2 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Unresolved | 4 | C0.4 (Det. 3); C0.2; C0.6; C0.3 | 31 32 11 | C0.4; C0.2; C0.6; 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Stabilized construction entrance | Stabilized construction entrance (quarry spalls on geotextile) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 2 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Unresolved | 4 | C0.4 (Det. 4); C0.2; C0.3 | 31 32 11 | C0.4; C0.2; 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Geotextile encased check dams | Geotextile encased check dams (BMP C208) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Unresolved | 4 | C0.4 (Det. 5); C0.3 | 31 32 11 | C0.4; 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Dewatering system | Contractor dewatering system: pumps, backup pumps, standby generator, wells or well points, discharge treatment | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | Y | 3 | 3 | PROPOSED-Temporary-Construction-Dewatering (Contract & General) | #15, #69 | Inferred | 1 | C0.2 (Element 10) | 31 23 19; 31 20 00 | 31 23 19; 31 20 00; C0.2 | Civil & Site
Item | CWP 31 | PROPOSED-Compost berm | Compost berm (TESC) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Unresolved | 4 | — | 31 32 11 | 31 32 11 | Civil & Site
Item | CWP 31 | PROPOSED-Orange barrier fence | Orange high-visibility barrier fence (TESC / clearing limits) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 | PROPOSED-Erosion-and-Sediment-Control-Measures (Contract & General) | #71 | Unresolved | 4 | C0.4 (Det. 3 note) | 31 32 11 | 31 32 11; C0.4 | Civil & Site
Item | CWP 31 | PROPOSED-Temporary shoring and trench safety systems | Temporary shoring, bracing and trench excavation safety systems (PE-designed where required) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 2 | 0 | PROPOSED-Trench-Safety-System (Contract & General); PROPOSED-Temporary-Excavation-Support (Contract & General) | #70 | Inferred | 2 | G0.3 (Note 7) | 31 40 00; 31 23 33 | 31 40 00; 31 23 33; G0.3 | Civil & Site
Item | CWP 31 | PROPOSED-Emergency access areas | Emergency access areas (west side) — no parking, blocking, stockpiling or staging; vehicle turnaround allowed | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | Y | N | 1 | 0 |  |  | Inferred | 4 | C0.3 (KN 1) | 31 32 11 | C0.3 | Civil & Site
Item | CWP 31 | PROPOSED-Trench-Safety-System | Trench safety system | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary shoring and trench safety systems (Civil & Site) | #70, #250 | Unresolved | 2 |  | 00 24 13; 00 41 00 | 00 24 13; 00 41 00 | Contract & General
Item | CWP 31 | PROPOSED-Erosion-and-Sediment-Control-Measures | Erosion and sediment control measures (SWPPP) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Plastic covering for slopes and stockpiles (Civil & Site); PROPOSED-Catch basin inserts (Civil & Site); PROPOSED-Filter fabric fence (Civil & Site); PROPOSED-Stabilized construction entrance (Civil & Site); PROPOSED-Geotextile encased check dams (Civil & Site); PROPOSED-Compost berm (Civil & Site) (+1 more) | #71, #250 | Inferred | 5 | TESC plans (civil sheets, not numbered in source) | 00 24 13; 00 41 00; 01 50 00 | 00 24 13; 00 41 00; 01 50 00 | Contract & General
Item | CWP 31 | PROPOSED-Temporary-Construction-Dewatering | Temporary construction dewatering (excavations) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Dewatering system (Civil & Site) | #69, #250 | Inferred | 1 |  | 01 11 10; 00 31 13 | 01 11 10; 00 31 13 | Contract & General
Item | CWP 31 | PROPOSED-Temporary-Excavation-Support | Temporary excavation support (shoring, bracing, sheeting, cribbing) | Site | Temporary | 31-C02 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Temporary shoring and trench safety systems (Civil & Site) | #70, #250 | Inferred | 1; 2 (trench safety only) |  | 01 11 10 | 01 11 10 | Contract & General
Item | CWP 31 | PROPOSED-Tracer wire and locater boxes | Tracer wire (#10 AWG insulated), locater boxes, and detectable warning tape on new utilities | Site | Install | 31-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | 2023-03-14 | Y | N | 4 | 0 |  |  | Unresolved | 1 | C7.1 (Det. 6); C7.4 (Det. 2, Note I) | 31 23 33; 33 30 00 | C7.1; C7.4; 31 23 33; 33 30 00 | Civil & Site
Item | CWP 31 | PROPOSED-Influent sample sump | Influent sample sump, 24-in x 6-ft precast well curb (H2 Precast WC-24 or equal) with traffic-rated riser and lid | Site | Install | 31-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | 2023-03-14 | N | N | 0 | 0 | PROPOSED-INFLUENT-SAMPLE-SUMP (Process & Mechanical) | #4 | Inferred | 1 | C7.5 (Det. 4); C7.1 (Det. 3); C1.3; C1.4 | 31 20 00; 33 30 00 | C7.5; C7.1; C1.3; C1.4; 31 20 00; 33 30 00 | Civil & Site
Item | CWP 31 | PROPOSED-Train 2 flow meter vault | Train 2 flow meter vault, precast 4'-2" x 4'-2" x 5'-0" (Utility Vault 506-LA or equal), H-20 hatch Halliday H1R3636, Bilco LadderUp | Train 2 | Install | 31-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-TRAIN-2-FLOW-METER-VAULT (Process & Mechanical); PROPOSED-Plants-2-and-3-Flow-Meter-Vault (Structural & Building) | #5 | Inferred | 1 | C7.10 (Det. 1) | 31 20 00; 33 30 00 | C7.10; 31 20 00; 33 30 00 | Civil & Site
Item | CWP 31 | PROPOSED-INFLUENT-SAMPLE-SUMP | Influent sampling sump | Influent Pump Station | Install | 31-C01 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Influent sample sump (Civil & Site) | #4, #164 | Inferred | 1 | G0.5; G0.6; C4.1 |  | G0.5; G0.6; C4.1 | Process & Mechanical
Item | CWP 31 | PROPOSED-Train 3 flow meter vault | Train 3 flow meter vault, precast 4'-2" x 4'-2" x 5'-0" (Utility Vault 506-LA or equal), H-20 hatch Halliday H1R3636, Bilco LadderUp | Train 3 | Install | 31-C03 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Earthwork, Dewatering & Erosion Control — Train 3 | 2023-03-14 | N | N | 0 | 0 | PROPOSED-TRAIN-3-FLOW-METER-VAULT (Process & Mechanical); PROPOSED-Plants-2-and-3-Flow-Meter-Vault (Structural & Building) | #6 | Inferred | 1 | C7.10 (Det. 2) | 31 20 00; 33 30 00 | C7.10; 31 20 00; 33 30 00 | Civil & Site
Section | CWP 32 | Paving, Fencing, Walls & Landscaping | 12 items · 0 overdue · 0 complete |  |  |  | 2023-03-15 | 2024-10-16 | [5 empty] | 12 | 0% | 0% | 0%
Item | CWP 32 | PROPOSED-Temporary cold-mix patches | Temporary cold-mix (MC-2) asphalt patches at trench crossings, 2 in minimum | Site | Temporary | 32-C03 | 2023-03-15 | 2024-10-16 | [5 empty] | 1 | 0% | 0% | 0% | On track |  | Paving, Fencing, Walls & Landscaping — Temporary facilities and controls | 2023-03-14 | N | N | 0 | 0 |  |  | Inferred | 1 | — | 32 12 16 | 32 12 16 | Civil & Site
Item | CWP 32 | PROPOSED-Parking stall striping | Parking stall striping, including van-accessible stall and signs | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | N | N | 0 | 0 |  | #96 | Unresolved | 1 | C7.1 (Det. 4); C2.6 |  | C7.1 | Civil & Site
Item | CWP 32 | PROPOSED-Concrete walkway | Concrete walkway / pavement, 6-inch minimum, #3 at 12 in each way | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | N | N | 0 | 0 |  | #97 | Inferred | 1 | C7.2 (Det. 1); C7.4 (Det. 4); C2.6 |  | C7.2; C7.4 | Civil & Site
Item | CWP 32 | PROPOSED-HMA pavement | Asphalt concrete pavement, 4-in HMA Class 1/2-in PG 58H-22 over 4-in CSBC and 12-in gravel base, thickened edge | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | Y | Y | 2 | 2 | PROPOSED-Site-Final-Surfacing-and-Pavement (Contract & General) | #73 | Unresolved | 1 | C7.3 (Det. 3); C7.4 (Det. 2); C2.6 | 32 12 16 | C7.3; C7.4; 32 12 16 | Civil & Site
Item | CWP 32 | PROPOSED-Gravel surfacing | Gravel surfacing, 4-in compacted base course over subgrade at 95% | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | N | N | 0 | 0 | PROPOSED-Site-Final-Surfacing-and-Pavement (Contract & General) | #73 | Unresolved | 1 | C7.3 (Det. 5); C2.6 |  | C7.3 | Civil & Site
Item | CWP 32 | PROPOSED-Asphalt wedge curb | Asphalt wedge curb per 4/C7.7 | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | Y | Y | 2 | 1 |  |  | Unresolved | 1 | C2.1 (KN 5) | 32 12 16 (Inferred) | C2.1 | Civil & Site
Item | CWP 32 | PROPOSED-Site-Final-Surfacing-and-Pavement | Final surfacing and pavement (entire site) | Site | Install | 32-C01 | 2024-08-01 | 2024-08-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2023-03-14 | N | Y | 0 | 5 | PROPOSED-HMA pavement (Civil & Site); PROPOSED-Gravel surfacing (Civil & Site) | #73, #250 | Inferred | 1; 8 (extra HMA only) |  | 00 31 13; 00 24 13; 00 41 00; 00 73 00; 01 45 00 | 00 31 13; 00 24 13; 00 41 00; 00 73 00; 01 45 00 | Contract & General
Item | CWP 32 | PROPOSED-Block retaining wall | Block (gravity) retaining wall, STA 0+05.00 to 1+31.00 | Site | Install | 32-C02 | 2024-08-01 | 2024-09-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2023-03-14 | Y | Y | 2 | 3 |  |  | Unresolved | 1 | C2.5; C0.2; C0.5; C2.1 | 32 32 23 | C2.5; C0.5; C0.2; 32 32 23 | Civil & Site
Item | CWP 32 | PROPOSED-Chain link fence 126 LF | Chain link fence along retaining wall, 126 LF, 6-ft fabric with 3-strand barbed wire (7 ft total), connected to existing fence | Site | Install | 32-C02 | 2024-08-01 | 2024-09-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2023-03-14 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.5; C2.1 | 02 83 00 | C2.5; 02 83 00 | Civil & Site
Item | CWP 32 | PROPOSED-Hydroseeded restoration areas | Hydroseeded grass restoration of disturbed areas (topsoil, seed, fertilizer, mulch) | Site | Install | 32-C02 | 2024-08-01 | 2024-09-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2023-03-14 | Y | N | 3 | 0 |  |  | Unresolved | 1 | C7.4 (Det. 2, Notes A, C); C0.2 (Item 22) | 02 92 00 | C7.4; C0.2; 02 92 00 | Civil & Site
Item | CWP 32 | PROPOSED-Retaining wall footing drain | Retaining wall footing drain with drain rock and drainage geotextile | Site | Install | 32-C02 | 2024-08-01 | 2024-09-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2023-03-14 | N | N | 0 | 0 |  |  | Unresolved | 1 | C2.5; C2.1 | 32 32 23; 33 31 00; 31 23 33; 33 41 00; Appendix C | 32 32 23; 33 31 00; 31 23 33; 33 41 00; Appendix C | Civil & Site
Item | CWP 32 | PROPOSED-Bollards | Bollards | Site | Install | 32-C02 | 2024-08-01 | 2024-09-30 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2023-03-14 | N | N | 0 | 0 |  | #131, #250 | Inferred | 3 |  | 00 24 13; 00 41 00 | 00 24 13; 00 41 00 | Contract & General
Section | CWP 33 | Yard Piping & Utilities | 88 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-07-08 | [5 empty] | 88 | 0% | 0% | 0%
Item | CWP 33 | PROPOSED-AERATION-AIR-HEADER | Blower Building aeration air piping: 3-inch SS header (IE 24.26) with 3-inch butterfly valves; 6-inch SS outlets with 6-inch butterfly valves | Blower Building | Install | 33-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Blower Building | 2023-03-31 | N | N | 0 | 0 |  | #231 | Inferred | 1 | C6.4; C6.5 | 33 31 00 (cited on C6.4) | C6.4; C6.5 | Process & Mechanical
Item | CWP 33 | PROPOSED-AIR-TO-TRAIN-3 | 6-inch SS aeration air line, Blower Building to Train 3 (buried, IE 15.90 at drop) | Blower Building; Train 3 | Install | 33-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Blower Building | 2023-03-31 | N | Y | 0 | 2 | Pipe ID 20 (Civil & Site) | #93 | Inferred | 1 | C6.4; C6.5; C3.3; C3.5 | 33 31 00 (cited on C6.4); 46 53 00 | C6.5; C6.4; C3.3; C3.5 | Process & Mechanical
Item | CWP 33 | PROPOSED-AIR-TO-TRAIN-1-STUB | 6-inch air piping to Train #1, terminated with blind flange inside existing metal building | Blower Building | Install | 33-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Blower Building | 2023-03-31 | N | N | 0 | 0 |  | #108 | Inferred | 1 | C6.5 |  | C6.5 | Process & Mechanical
Item | CWP 33 | PROPOSED-AIR-TO-TRAIN-2-STUB | 6-inch air piping to Train #2, terminated with blind flange inside existing metal building | Blower Building | Install | 33-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Blower Building | 2023-03-31 | N | N | 0 | 0 |  | #109 | Inferred | 1 | C6.5 |  | C6.5 | Process & Mechanical
Item | CWP 33 | PROPOSED-Blower-Building-Foundation-Drains | Perimeter foundation drains, 4 in rigid ABS perforated pipe or drain tile in drain rock — Blower Building slab edge | Blower Building | Install | 33-C01 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Blower Building | 2023-03-31 | Y | N | 1 | 0 |  | #128, #239 | Inferred | 1 (Inferred per 04) | S2.3 |  | S2.3 | Structural & Building
Item | CWP 33 | PROPOSED-Interim 8in HDPE effluent pipe | Interim 8-inch HDPE effluent pipe | Site | Temporary | 33-C02 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Temporary bypass and interim effluent piping | 2023-03-31 | Y | Y | 3 | 8 | PROPOSED-Temporary-8in-Effluent-Piping (Contract & General) | #74 | Unresolved | 1 | C0.5 (KN 1, 8); C0.7 (cited) | 33 33 00 | C0.5; 33 33 00; Appendix F | Civil & Site
Item | CWP 33 | PROPOSED-Temporary-8in-Effluent-Piping | Temporary 8-inch effluent piping | Site | Temporary | 33-C02 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Temporary bypass and interim effluent piping | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Interim 8in HDPE effluent pipe (Civil & Site) | #74, #250 | Inferred | 1 |  | 00 31 13 | 00 31 13 | Contract & General
Item | CWP 33 | PROPOSED-EFFLUENT-HEADER-TO-UV | Secondary effluent header through 8-inch effluent flow meter to UV Channels #1 and #2, 8-inch, with 8-inch gate valves (hand wheel) at channel inlets | UV Disinfection Chamber & Digester | Install | 33-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 |  | #105 | Inferred | 1 | G0.5; C5.1; C5.2; C5.3 |  | G0.5; C5.1; C5.2; C5.3 | Process & Mechanical
Item | CWP 33 | PROPOSED-UV-CHAMBER-DRAIN | UV chamber drain, 4-inch, with 4-inch gate valves | UV Disinfection Chamber & Digester | Install | 33-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | Pipe ID 2 (Civil & Site) | #88 | Inferred | 1 | G0.5; C5.1; C5.2; C5.3 |  | G0.5; C5.1; C5.2; C5.3 | Process & Mechanical
Item | CWP 33 | PROPOSED-DIGESTER-AIR-LINES | Aerobic digester air supply lines, 3-inch and 4-inch | UV Disinfection Chamber & Digester | Install | 33-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | Pipe ID 21 (Civil & Site) | #94 | Inferred | 1 | C5.1; C5.2; C5.3; C6.3 |  | C5.1; C5.2; C5.3; C6.3 | Process & Mechanical
Item | CWP 33 | PROPOSED-DIGESTED-SLUDGE-LINE | Digested sludge line, 2-inch SCH 80 PVC, digester to digested sludge pumps | UV Disinfection Chamber & Digester | Install | 33-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | Pipe ID 7 (Civil & Site) | #90 | Unresolved | 1 | G0.5; C5.1; C5.3; C6.2 |  | G0.5; C5.1; C5.3; C6.2 | Process & Mechanical
Item | CWP 33 | PROPOSED-WAS-PUMP-DISCHARGE-TO-DIGESTER | WAS pump discharge to aerobic digester, 3-inch | UV Disinfection Chamber & Digester | Install | 33-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — UV chamber and digester | 2023-03-31 | N | N | 0 | 0 | Pipe ID 19 (Civil & Site) | #91 | Unresolved | 1 | G0.5; C5.1; C5.3; C6.2 |  | G0.5; C5.1; C5.3; C6.2 | Process & Mechanical
Item | CWP 33 | PROPOSED-Water line relocation at storm drain | Existing water line — relocate 1 ft clear below bottom of storm drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 7 |  |  | Inferred | 1 | C0.5 (KN 22) | 33 32 00; 33 30 00 | C0.5; 33 32 00; 33 30 00 | Civil & Site
Item | CWP 33 | Pipe ID 1 | 8-inch existing effluent (DI gravity) | Site | Modify / connect | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 30 00 | C1.3; 33 30 00 | Civil & Site
Item | CWP 33 | Pipe ID 2 | 4-inch UV disinfection drain and digester supernatant (DI gravity), 2% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-UV-CHAMBER-DRAIN (Process & Mechanical) | #88 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 3 | 8-inch influent (DI gravity), 0.4% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-STEP-INFLUENT-CONNECTION (Process & Mechanical) | #87 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 4 | 3-inch influent pump station air vent (SS), outlet 8 ft above finish grade, gooseneck down, fastened to exterior building wall | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 4 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 30 00; 33 05 00 | C1.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 5 | 10-inch UV disinfection effluent (DI gravity), 0.28% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-FINAL-EFFLUENT-LINE (Process & Mechanical) | #92 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 6 | 4-inch building septic (Sch. 80 PVC gravity), 2% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 7 | 2-inch digested sludge (Sch. 80 PVC force main), positive slope throughout | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | PROPOSED-DIGESTED-SLUDGE-LINE (Process & Mechanical) | #90 | Inferred | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 8 | 4-inch vault drain (Sch. 80 PVC gravity), 2.0% | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 5 | 5 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7); C7.10 | 33 31 00; 33 30 00; 33 05 00 | C1.3; C7.10; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 9 | 1-inch 2W water system air vent (SS), outlet 3 ft above grade, gooseneck down | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 4 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 30 00; 33 05 00 | C1.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 10 | 3-inch 2W water line, HDPE (Add. 4; base: 2-inch Sch. 80 PVC force main) | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 7 | 8 | PROPOSED-2W-DISCHARGE-LINE (Process & Mechanical) | #50 | Inferred | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00; 33 33 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00; 33 33 00 | Civil & Site
Item | CWP 33 | Pipe ID 11 | 8-inch Train 3 influent (DI gravity), 0.4% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | INF3 (Process & Mechanical) | #81 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 12 | 2-inch water pipe (Sch. 80 PVC force main) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 7 |  | #191 | Unresolved | 1 | C1.3 (Add. 4 p.7) | 33 32 00; 33 30 00; 33 05 00 | C1.3; 33 32 00; 33 30 00 | Civil & Site
Item | CWP 33 | Pipe ID 13 | 8-inch Train 2 influent (DI gravity), 0.4% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | INF2 (Process & Mechanical) | #80 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 14 | 8-inch Train 1 influent (DI gravity), 0.4% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | INF1 (Process & Mechanical) | #79 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 15 | 2-inch Train 3 WAS (Sch. 80 PVC gravity), positive drainage throughout | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | WAS3 (Process & Mechanical) | #85 | Unresolved | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 16 | 8-inch Train 2 effluent (DI gravity), 0.4% min | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | SE2 (Process & Mechanical) | #83 | Inferred | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 17 | 8-inch Train 3 effluent (DI gravity), 0.4% min | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | SE3 (Process & Mechanical) | #84 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 18 | 6-inch influent to flow splitter (DI force main), positive slope throughout | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-IPS-DISCHARGE-TO-SPLITTER (Process & Mechanical) | #86 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 19 | 2-inch digester WAS influent (Sch. 80 PVC gravity) | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | PROPOSED-WAS-PUMP-DISCHARGE-TO-DIGESTER (Process & Mechanical) | #91 | Unresolved | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 20 | 6-inch Cell 3 air (SS) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-AIR-TO-TRAIN-3 (Process & Mechanical) | #93, #159 | Unresolved | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 21 | 4-inch digester air (SS) | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | PROPOSED-DIGESTER-AIR-LINES (Process & Mechanical) | #94 | Unresolved | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 22 | 1-inch yard hydrants, 3 locations (Add. 4) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 7 | 6 | PROPOSED-YARD-HYDRANTS (Process & Mechanical) | #52, #180 | Unresolved | 1 | C1.3 (Add. 4 p.7); C7.1 (Det. 1); C7.5 (Det. 1) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C7.1; C7.5; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 23 | 1-inch 2W water line, HDPE (Add. 4) | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 7 | 8 | PROPOSED-2W-BLADDER-TANK-SUPPLY (Process & Mechanical) | #51, #146 | Inferred | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00; 33 33 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00; 33 33 00 | Civil & Site
Item | CWP 33 | Pipe ID 24 | 8-inch Train 1 effluent (DI gravity), 0.4% min (Add. 4) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 | SE1 (Process & Mechanical) | #82 | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 25 | 4-inch pressate drain (DI gravity), 2% min (Add. 4) | Site; Existing building (C1.6A) | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 6 | PROPOSED-PLANT-DRAIN-LINE (Process & Mechanical) | #89 | Inferred | 1 | C1.3 (Add. 4 p.7); C1.6A (Add. 4 p.8) | 33 31 00; 33 30 00; 33 05 00 | C1.3; C1.6A; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Pipe ID 26 | 4-inch building floor drain (DI gravity), 2% min (Add. 4) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Inferred | 1 | C1.3 (Add. 4 p.7) | 33 31 00; 33 30 00; 33 05 00 | C1.3; 33 31 00; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 1 | 6-inch gate valve — influent flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  | #177 | Inferred | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 2 | 8-inch gate valve — Train 2 flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 5 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2); C7.10 | 33 30 00; 33 05 00 | C1.4; C7.3; C7.10; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 3 | 8-inch gate valve — Train 3 flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 5 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2); C7.10 | 33 30 00; 33 05 00 | C1.4; C7.3; C7.10; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 4 | 4-inch gate valve — drain flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Inferred | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 5 | 4-inch gate valve — drain flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Inferred | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 6 | 4-inch gate valve — treated effluent outlet box drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 7 | 4-inch gate valve — treated effluent outlet box drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 8 | 4-inch gate valve — UV disinfection drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 9 | 4-inch gate valve — sample sump drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 10 | 4-inch gate valve — pump station clean-out drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 11 | 4-inch gate valve — pump station clean-out drain | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 12 | 8-inch plug valve — effluent flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | Buried Valve ID 13 | 4-inch gate valve — drain flow meter isolation | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 5 |  |  | Unresolved | 1 | C1.4; C7.3 (Det. 2) | 33 30 00; 33 05 00 | C1.4; C7.3; 33 30 00; 33 05 00 | Civil & Site
Item | CWP 33 | SD-1 | Storm drain alignment SD-1, 12-inch, 42 + 19 + 42 LF at 0.5% | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 3 |  | #3, #207 | Unresolved | 1 | C2.2 | 33 30 00; 33 41 00 | C2.2; 33 30 00; 33 41 00 | Civil & Site
Item | CWP 33 | PROPOSED-4in roof drain at SD-1 | 4-inch roof drain connection from SDCB #9 (8 LF and 17 LF at 2.00%) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 5 |  |  | Inferred | 1 | C2.2 | 33 30 00; 33 41 00 | C2.2; C0.5; 33 30 00; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #5 | Storm drain catch basin #5, Type 1, rim 22.94 (STA 0+47.05) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.2; C2.1; C2.3 | 33 41 00 | C2.2; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #8 | Storm drain catch basin #8, Type 1, rim 22.78 (STA 0+67.46) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.2; C2.4; C2.1 | 33 41 00 | C2.2; C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #9 | Storm drain catch basin #9, Type 1, rim 22.75 (STA 1+09.93) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.2; C2.4; C2.1 | 33 41 00 | C2.2; C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #7 | Storm drain catch basin #7, Type 1, rim 23.00 (west trench drain) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #10 | Storm drain catch basin #10, Type 1, rim 23.10 (STA 0+77.60, east trench drain) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #2 | Storm drain catch basin #2, rim 22.65 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #3 | Storm drain catch basin #3, rim 22.70 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #4 | Storm drain catch basin #4, rim 23.15 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB #6 | Storm drain catch basin #6, rim 23.00 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C2.4; C2.1; C2.3 | 33 41 00 | C2.4; 33 41 00 | Civil & Site
Item | CWP 33 | SDCB 1076 | Existing storm drain catch basin 1076 (Type 1) — new 12-inch connection on east side at IE 20.35 | Site | Modify / connect | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C2.2; C0.1 | 33 41 00 | C2.2; C0.1; 33 41 00 | Civil & Site
Item | CWP 33 | PROPOSED-East trench drains | East trench drains, north and south of SDCB #10, rim 23.10 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C2.4; C7.4 (Det. 5) | 33 41 00 | C2.4; C7.4 | Civil & Site
Item | CWP 33 | PROPOSED-West trench drain | West trench drain, about 51 ft, north side of SDCB #7 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C2.4; C7.4 (Det. 5) | 33 41 00 | C2.4; C7.4 | Civil & Site
Item | CWP 33 | PROPOSED-New septic tank | New septic tank (replaces SSMH 1285) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C0.5 (KN 4); C7.1 (Det. 3) | Appendix H | C0.5; Appendix H; C7.1 | Civil & Site
Item | CWP 33 | PROPOSED-Gravity sewer cleanouts | Gravity sewer cleanouts (6-in or 8-in) with cast iron ring and cover in concrete block | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 4 |  |  | Inferred | 1 | C7.1 (Det. 5) | 33 31 00; 33 30 00 | C7.1; 33 31 00; 33 30 00 | Civil & Site
Item | CWP 33 | PROPOSED-Buried valve label markers | Bronze buried valve label markers (Berntsen #C35FB) with cast iron valve boxes and concrete pads | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  | #99 | Unresolved | 1 | C7.3 (Det. 2, 4); C1.4 |  | C7.3; C1.4 | Civil & Site
Item | CWP 33 | PROPOSED-Post hydrant | Post hydrant on 2-inch HDPE supply with buried 2-inch gate valve | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 4 | 2 | PROPOSED-POST-HYDRANTS (Process & Mechanical) | #53 | Unresolved | 1 | C7.5 (Det. 2) | 33 30 00 | C7.5; 33 30 00 | Civil & Site
Item | CWP 33 | PROPOSED-Composite manholes, double manhole condition | Lightweight composite manholes (Morrison Bros. 418LC-3800 AM or equal) in cast-in-place traffic ring | Not stated | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  |  | Unresolved | 1 | C7.5 (Det. 3) | 33 30 00 | C7.5; 33 30 00 | Civil & Site
Item | CWP 33 | SDCB #1 | Storm drain catch basin #1, Type 1L, rim 22.3; 12-in (SE) invert 19.3 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 1 | 0 |  |  | Unresolved | 1 | C0.3; C2.1 (KN 7); C2.3 (SD-3) | 33 41 00 | C2.1; C2.3 | Civil & Site
Item | CWP 33 | SD-2 | Storm drain alignment SD-2: SDCB #5 → #6 → #7 → #10; 48 LF of 12-in and 23 LF of 6-in at 0.5%; 4-in roof drain 21 LF at 2.00% | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 3 |  |  | Inferred | 1 | C2.3 (plan and profile); C2.1 | 33 30 00; 33 41 00 | C2.3 | Civil & Site
Item | CWP 33 | SD-3 | Storm drain alignment SD-3: SDCB #1 → #2 → #3 → #4 → trench drain; 83 LF of 12-in and 28 LF of 6-in at 0.5% | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 3 |  |  | Unresolved | 1 | C2.3 (plan and profile); C2.1 | 33 30 00; 33 41 00 | C2.3 | Civil & Site
Item | CWP 33 | PROPOSED-4in roof drain connections (SD-2, SD-3) | 4-in roof drain connections: SD-2 STA 0+47.16 (21 LF at 2.00%); SD-3 STA 0+26.94 and 0+70.26 | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | Y | Y | 3 | 3 |  |  | Inferred | 1 | C2.3; C2.1 (KN 3) | 33 30 00; 33 41 00 | C2.3; C2.1 | Civil & Site
Item | CWP 33 | SE1 | Train 1 secondary effluent line to effluent flow meter and UV | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | Pipe ID 24 (Civil & Site) | #82 | Inferred | 1 | G0.5 |  | G0.5 | Process & Mechanical
Item | CWP 33 | SE2 | Train 2 secondary effluent line to effluent flow meter and UV | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | Pipe ID 16 (Civil & Site) | #83 | Inferred | 1 | G0.5 |  | G0.5 | Process & Mechanical
Item | CWP 33 | WAS1 | Train 1 waste activated sludge line to WAS pump | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  | #101, #162 | Inferred | 1 | G0.5; C6.2 |  | G0.5; C6.2 | Process & Mechanical
Item | CWP 33 | WAS2 | Train 2 waste activated sludge line to WAS pump | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 |  | #102, #162 | Inferred | 1 | G0.5; C6.2 |  | G0.5; C6.2 | Process & Mechanical
Item | CWP 33 | PROPOSED-FINAL-EFFLUENT-LINE | Final effluent, UV chamber to existing SSMH *1288 and 12-inch outfall, 10-inch | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | Pipe ID 5 (Civil & Site) | #92 | Unresolved | 1 | G0.5; G0.6; C5.2; C5.3 |  | G0.5; G0.6; C5.2; C5.3 | Process & Mechanical
Item | CWP 33 | PROPOSED-8in-Effluent-Piping | 8-inch effluent piping (new) | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | Y | 0 | 3 |  | #105, #250 | Inferred | 1 |  | 00 31 13; 01 45 00 | 00 31 13; 01 45 00 | Contract & General
Item | CWP 33 | PROPOSED-Yard-Piping | Yard piping | Site | Install | 33-C06 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-03-31 | N | Y | 0 | 5 |  | #250 | Inferred | 1 |  | 00 31 13; 00 73 00; 01 45 00 | 00 31 13; 00 73 00; 01 45 00 | Contract & General
Item | CWP 33 | INF1 | Train 1 influent line, flow splitter to existing Train 1, 8-inch | Influent Flow Splitter | Install | 33-C03 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | Pipe ID 14 (Civil & Site) | #79, #162 | Inferred | 1 | G0.5; C3.1; C3.2 |  | G0.5; C3.1; C3.2 | Process & Mechanical
Item | CWP 33 | INF2 | Train 2 influent line, flow splitter to existing Train 2, 8-inch DI | Influent Flow Splitter | Install | 33-C03 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | Pipe ID 13 (Civil & Site) | #80, #162 | Inferred | 1 | G0.5; C3.1; C3.2 |  | G0.5; C3.1; C3.2 | Process & Mechanical
Item | CWP 33 | INF3 | Train 3 influent line, flow splitter to Train 3, 8-inch | Influent Flow Splitter; Train 3 | Install | 33-C03 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | Pipe ID 11 (Civil & Site) | #81, #162 | Inferred | 1 | G0.5; C3.1; C3.2; C3.3; C3.5 |  | G0.5; C3.1; C3.2; C3.3; C3.5 | Process & Mechanical
Item | CWP 33 | PROPOSED-STEP-INFLUENT-CONNECTION | 8-inch STEP influent connection to the new Influent Pump Station, IE 19.50 | Influent Pump Station | Install | 33-C03 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | Pipe ID 3 (Civil & Site) | #87 | Inferred | 1 | G0.5; G0.6; C3.1; C4.1 |  | G0.5; G0.6; C3.1; C4.1 | Process & Mechanical
Item | CWP 33 | PROPOSED-Floor drains | Floor drains, 4-inch stainless steel with 2-inch trap | Not stated (in Train 2 and Train 3 flow meter vaults per C7.10) | Install | 33-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Train 3 | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C7.1 (Det. 2); C7.10 | 33 31 00 | C7.1; C7.10; 33 31 00 | Civil & Site
Item | CWP 33 | SE3 | Train 3 secondary effluent line, 8-inch | Train 3 | Install | 33-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Yard Piping & Utilities — Train 3 | 2023-03-31 | N | N | 0 | 0 | Pipe ID 17 (Civil & Site) | #84 | Inferred | 1 | G0.5; C3.3; C3.5 |  | G0.5; C3.3; C3.5 | Process & Mechanical
Section | CWP 40 | Process Interconnections | 1 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0%
Item | CWP 40 | PROPOSED-DIGESTER-TELESCOPING-VALVE | Aerobic digester telescoping valve, 4-inch rising stem, 48-inch min travel, Waterman TS-2 or equal | UV Disinfection Chamber & Digester | Install | 40-C01 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Process Interconnections — UV chamber and digester | 2023-03-31 | Y | N | 4 | 0 |  |  | Inferred | 1 | G0.6; G0.7; C5.1; C5.3 | 40 05 71 | G0.6; G0.7; C5.1; C5.3; 40 05 71 | Process & Mechanical
Section | CWP 41 | Material Handling (Screw Conveyors) | 2 items · 0 overdue · 0 complete |  |  |  | 2023-11-01 | 2024-02-09 | [5 empty] | 2 | 0% | 0% | 0%
Item | CWP 41 | Receiving Conveyor | Receiving conveyor, horizontal shaftless, 9-in. flight, 6 ft 9 in., 304 SS U-trough, two inlets from rotary press cake chutes, 1 HP | Rotary Fan Press System | Install | 41-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | 2023-10-31 | Y | Y | 2 | 4 |  | #111 | Unresolved | 1; Equipment Alternate C |  | 41 12 13 | 41 12 13; 46 76 26 | Process & Mechanical
Item | CWP 41 | Inclined Conveyor | Inclined conveyor, shafted, 9-in. flight at 5-in. pitch, 17 ft 4 in. at 35 degrees, 304 SS tubular trough, outlet to bin, 5 HP | Rotary Fan Press System | Install | 41-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | 2023-10-31 | Y | Y | 2 | 4 |  | #112 | Unresolved | 1; Equipment Alternate C |  | 41 12 13 | 41 12 13; 46 76 26 | Process & Mechanical
Section | CWP 43 | Blowers & 2W Plant Water System | 31 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-02-09 | [5 empty] | 31 | 0% | 0% | 0%
Item | CWP 43 | ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) | Biological treatment blowers (4), Kaeser Com-paK DB 166 C, 20 HP 460 V, VFD, 315 scfm at 8.9 psig each | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Y | Y | 1 | 1 | BL-2 (Electrical & Controls); BL-3 (Electrical & Controls); BL-4 (Electrical & Controls); PROPOSED-Blowers-Blower-Building (Structural & Building); PROPOSED-Blowers (Contract & General); BL-1 (Electrical & Controls) | #18 | Inferred | 1; 6 | C6.4; C6.5 | 43 11 00 | C6.4; C6.5; 43 11 00 | Process & Mechanical
Item | CWP 43 | PROPOSED-EYE-WASH-STATIONS | Wall-mount eye wash stations (quantity and locations not stated) | Not stated | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Y | N | 1 | 0 |  | #113, #180 | Inferred | 1 |  | 43 22 10 | 43 22 10 | Process & Mechanical
Item | CWP 43 | BL-1 | Aeration Blower No.1 — cell aeration blower, Cell 1, 20 HP, VFD in MCC | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Blowers-Blower-Building (Structural & Building); PROPOSED-Blowers (Contract & General); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical) | #18, #202, #215 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 |  | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 | Electrical & Controls
Item | CWP 43 | BL-2 | Aeration Blower No.2 — cell aeration blower, Cell 2, 20 HP, VFD in MCC | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Blowers-Blower-Building (Structural & Building); PROPOSED-Blowers (Contract & General); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical) | #18 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 |  | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 | Electrical & Controls
Item | CWP 43 | BL-3 | Aeration Blower No.3 — cell aeration blower, Cell 3, 20 HP, VFD in MCC | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Blowers-Blower-Building (Structural & Building); PROPOSED-Blowers (Contract & General); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical) | #18 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 |  | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 | Electrical & Controls
Item | CWP 43 | BL-4 | Aeration Blower No.4 — backup, 20 HP, VFD in MCC | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Blowers-Blower-Building (Structural & Building); PROPOSED-Blowers (Contract & General); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical) | #18, #202, #215 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 |  | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 | Electrical & Controls
Item | CWP 43 | DB | Digester blower, 5 HP, VFD in MCC | Not stated — drawn on E2.1 outside the Blower Building outline, beside a "building interior wall" | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | ESWD WWTP – Aerobic Digester Blower (Process & Mechanical) | #19 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 |  | E2.1; E6.1; E6.3; E7.1; E7.2; E7.3; E7.4; E9.1; E9.2 | Electrical & Controls
Item | CWP 43 | PROPOSED-Blowers-Blower-Building | Blowers (4) on the blower pad | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | BL-2 (Electrical & Controls); BL-3 (Electrical & Controls); BL-4 (Electrical & Controls); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical); BL-1 (Electrical & Controls) | #18, #224 | Inferred | 1 (Inferred per 04) | A1.1; A1.3 |  | A1.1; A1.3 | Structural & Building
Item | CWP 43 | PROPOSED-2W-Bladder-Tank-Assembly | 2W bladder tank assembly — 2 tanks, 24 in diameter | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-2W-DIAPHRAGM-TANKS (Process & Mechanical) | #25, #227 | Inferred | 1 (Inferred per 04) | A1.1 |  | A1.1 | Structural & Building
Item | CWP 43 | PROPOSED-Blowers | Blower equipment (blowers and drives) | Blower Building | Install | 43-C02 | 2023-04-01 | 2023-07-31 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Blower Building | 2023-03-31 | Y | Y | 11 | 4 | BL-2 (Electrical & Controls); BL-3 (Electrical & Controls); BL-4 (Electrical & Controls); PROPOSED-Blowers-Blower-Building (Structural & Building); ESWD WWTP – Biological Treatment System Blowers (Trains 1 – 3) (Process & Mechanical); BL-1 (Electrical & Controls) | #18, #251 | Inferred | 1 |  | 01 91 00; 01 33 00; 01 70 00 | 01 91 00; 01 33 00; 01 70 00; CQA Plan | Contract & General
Item | CWP 43 | ESWD WWTP – Aerobic Digester Blower | Aerobic digester blower (1), Kaeser Com-paK BB 52 C, 5 HP 460 V, VFD, 120 scfm at 4.0 psig, on 3.25 x 2.25 ft pad | Existing Metal Building adjacent to Train #2 (Digester Blower) | Install | 43-C04 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Aerobic digester | 2023-03-31 | Y | Y | 1 | 1 | DB (Electrical & Controls) | #19, #173 | Inferred | 1; 6 | C6.3; C6.4 | 43 11 00 | C6.3; C6.4; 43 11 00 | Process & Mechanical
Item | CWP 43 | Hot Box #1 | 2W water hot box #1 — flow meter and isolation valve (relocated per Add. 4) | Site | Install | 43-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Hot-Box-1 (Electrical & Controls) | #16, #95, #149, #193, #206 | Inferred | 1 | C1.3 (Add. 4 p.7); C7.6 (Det. 1) |  | C1.3; C7.6 | Civil & Site
Item | CWP 43 | Hot Box #2 | 2W water hot box #2 — air gap piping (relocated per Add. 4) | Site | Install | 43-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Hot-Box-2 (Electrical & Controls); PROPOSED-2W-AIR-GAP-ENCLOSURE (Process & Mechanical); PROPOSED-2W-Air-Gap-Water-System (Contract & General) | #17, #169, #183 | Inferred | 1 | C1.3 (Add. 4 p.7); C7.6 (Det. 2–3) |  | C1.3; C7.6 | Civil & Site
Item | CWP 43 | PROPOSED-Hot Box #1 solenoid valve | Solenoid valve, ASCO Redhat 8221, 3/4-inch, slow-closing, normally closed, 120 VAC, NEMA 4X | Site | Install | 43-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | PROPOSED-2W-Isolation-Valve-Solenoid (Electrical & Controls) | #49, #100 | Inferred | 1 | C7.6 (Det. 1) |  | C7.6 | Civil & Site
Item | CWP 43 | PROPOSED-2W-AIR-GAP-ENCLOSURE | 2W air gap system in a fiberglass enclosure ("2W (Air Gap) Water Hot Box") | Site (on C1.3 per Add. 4 p.3) | Install | 43-C05 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-03-31 | Y | N | 2 | 0 | PROPOSED-Hot-Box-2 (Electrical & Controls); Hot Box #2 (Civil & Site); PROPOSED-2W-Air-Gap-Water-System (Contract & General) | #17 | Inferred | 1 |  | 43 22 10 | 43 22 10; C4.2 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-FLOW-METER | Plant water (2W) flow meter, 1-inch electromagnetic, 0-25 gpm, in a fiberglass enclosure (43 22 10 flow meter system) | Not stated (2W system) | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Y | N | 1 | 0 | PROPOSED-Hot Box #1 flow meter (Civil & Site); PROPOSED-2W-Flow-Meter (Electrical & Controls) | #11 | Inferred | 1 | G0.7 | 43 22 10 | G0.7; 43 22 10 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-PUMP-STATION-WET-WELL ¦ PROPOSED-2W-Pump-Station-Wet-Well | 2W plant water pump station wet well, 96-inch precast, floor 10.00, top 21.50, with 30-inch fiberglass access structure, insulated gasketed lid and 38-inch traffic-rated lid and ring ¦ 2W water system pump station wet well | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Y | Y | 4 | 5 | PROPOSED-2W-Pump-Station-Precast-Wet-Well (Structural & Building) | #47, #251, #252 | Inferred | 1 | C4.2 | 43 22 10; 01 45 00; 01 50 00 | C4.2; 43 22 10; 01 45 00; 01 50 00 | Process & Mechanical; Contract & General
Item | CWP 43 | PROPOSED-2W-PUMPS | 2W plant water pumps (2), submersible well pumps, 1 duty and 1 standby, 20-80 gpm | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Y | Y | 2 | 2 | 2W-P1 (Electrical & Controls); 2W-P2 (Electrical & Controls) | #45, #193 | Inferred | 1; 6 | G0.7; C4.2 | 43 22 10 | G0.7; C4.2; 43 22 10 | Process & Mechanical
Item | CWP 43 | F1–F4 [2W Pump Station] | 2W pump station float switches F1-F4 | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | N | N | 0 | 0 | F2 (2W Pump Station) (Electrical & Controls); LSH-111 (Electrical & Controls); F3 (2W Pump Station) (Electrical & Controls); LSL-111 (Electrical & Controls) | #46 | Inferred | 1 | C4.2 | 43 22 10 | C4.2; 43 22 10 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-DIAPHRAGM-TANKS | 2W air diaphragm (bladder) tanks (2), Amtrol Well-X-Trol WX-350D, 119 gal (26 x 62 in.), with manifold, gauge and relief valves | Train #2 Building (per Add. 4 p.6) | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Y | Y | 1 | 2 | PROPOSED-2W-Bladder-Tank-Assembly (Structural & Building) | #25 | Unresolved | 1 | C4.3; C6.4 | 43 22 10 | C4.3; C6.4; 43 22 10 | Process & Mechanical
Item | CWP 43 | PIT-620 | 2W system pressure transducer, 0-150 psi (operating 55-75 psi) | 2W Equipment Layout (room not named on C4.3) | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | N | N | 0 | 0 | PROPOSED-2W-Pressure-Transducer (Electrical & Controls) | #48 | Inferred | 1 | C4.3 | 43 22 10 | C4.3; 43 22 10 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-DISCHARGE-LINE | 2W plant water discharge, 2-inch SCH 80 PVC to 3-inch HDPE | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | N | N | 0 | 0 | Pipe ID 10 (Civil & Site) | #50 | Inferred | 1 | C4.2; C6.3; C6.4 | 43 22 10 | C4.2; C6.3; C6.4; 43 22 10 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-FILL-LINE | 2W water fill from air gap to 2W wet well, 4-inch SCH 80 PVC at 2% slope, inlet IE 19.50 | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | N | N | 0 | 0 |  | #169 | Unresolved | 1 | C4.2 | 43 22 10 | C4.2; 43 22 10 | Process & Mechanical
Item | CWP 43 | PROPOSED-2W-BLADDER-TANK-SUPPLY | 1-inch 2W supply piping to the bladder tanks, routed below existing concrete floor, slab penetration at tank connection | Train #2 Building (per Add. 4 p.6) | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | N | N | 0 | 0 | Pipe ID 23 (Civil & Site) | #51 | Inferred | 1 | C6.4 | 43 22 10 | C6.4; 43 22 10 | Process & Mechanical
Item | CWP 43 | 2W-P1 | 2W Water Pump No.1, 5 HP, VFD in MCC (E4.3 tags it P-2W-1) | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-2W-PUMPS (Process & Mechanical) | #45, #193 | Unresolved | 1 (equipment, Inferred per 04); 6 (power and control) | E4.3; E6.1; E6.3; E7.3; E7.4; E9.1 |  | E4.3; E6.1; E6.3; E7.3; E7.4; E9.1 | Electrical & Controls
Item | CWP 43 | 2W-P2 | 2W Water Pump No.2, 5 HP, VFD in MCC (E4.3 tags it P-2W-2) | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-2W-PUMPS (Process & Mechanical) | #45, #193 | Unresolved | 1 (equipment, Inferred per 04); 6 (power and control) | E4.3; E6.1; E6.3; E7.3; E7.4; E9.1 |  | E4.3; E6.1; E6.3; E7.3; E7.4; E9.1 | Electrical & Controls
Item | CWP 43 | PROPOSED-Hot-Box-1 | Hot Box #1 (2W): houses the 1-in 2W flow meter, isolation valve solenoid, heat trace, GFEP and J-box | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Not stated | Not stated | 0 | 0 | Hot Box #1 (Civil & Site) | #16, #95 | Unresolved | 1 (enclosure, Inferred per 04); 6 (electrical) | E4.3; E6.2; E6.3 |  | E4.3; E6.2; E6.3 | Electrical & Controls
Item | CWP 43 | PROPOSED-Hot-Box-2 | Hot Box #2 (2W): heat trace on exposed piping | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Not stated | Not stated | 0 | 0 | Hot Box #2 (Civil & Site); PROPOSED-2W-AIR-GAP-ENCLOSURE (Process & Mechanical); PROPOSED-2W-Air-Gap-Water-System (Contract & General) | #17 | Unresolved | 1 (enclosure, Inferred per 04); 6 (electrical) | E4.3; E6.2; E6.3 |  | E4.3; E6.2; E6.3 | Electrical & Controls
Item | CWP 43 | PROPOSED-2W-Isolation-Valve-Solenoid | Isolation valve solenoid in Hot Box #1 (2W line) | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Hot Box #1 solenoid valve (Civil & Site) | #49, #100 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.3; E6.3; E7.4 |  | E4.3; E6.3; E7.4 | Electrical & Controls
Item | CWP 43 | PROPOSED-2W-Air-Gap-Water-System | 2W air gap water system | 2W Pump Station | Install | 43-C01 | 2023-05-01 | 2023-10-18 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — 2W air gap water system | 2023-03-31 | Y | Y | 11 | 4 | PROPOSED-Hot-Box-2 (Electrical & Controls); Hot Box #2 (Civil & Site); PROPOSED-2W-AIR-GAP-ENCLOSURE (Process & Mechanical) | #17, #251 | Inferred | 1 |  | 00 31 13; 01 33 00; 01 70 00; 01 91 00 | 00 31 13; 01 33 00; 01 70 00; 01 91 00; CQA Plan | Contract & General
Item | CWP 43 | PROPOSED-2W-SUPPLY-TO-PRESS | 2W water supply to rotary fan press, 2-inch | Rotary Fan Press System | Install | 43-C03 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Blowers & 2W Plant Water System — Sludge dewatering (rotary fan press) | 2023-03-31 | N | N | 0 | 0 |  |  | Inferred | 1 | C6.1 | 43 22 10; 46 76 26 | C6.1; 43 22 10; 46 76 26 | Process & Mechanical
Section | CWP 45 | Process Valves | 4 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2023-11-01 | [5 empty] | 4 | 0% | 0% | 0%
Item | CWP 45 | PROPOSED-AIR-BUTTERFLY-VALVES | Aeration air butterfly valves: 3-inch and 6-inch at the biological blowers, 4-inch at the digester blower; Bray Series 31 lug or Dezurik or equal | Blower Building; Digester Blower | Install | 45-C01 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Process Valves — Aerobic digester | 2023-03-31 | Y | Y | 3 | 2 |  |  | Inferred | 1 | C6.3; C6.5 | 45 05 00 | C6.3; C6.5; 45 05 00 | Process & Mechanical
Item | CWP 45 | PROPOSED-SLUDGE-MANIFOLD-PIPING | Sludge pump and valving area manifold: 2-inch SCH 80 PVC with 2-inch PVC ball valves and unions; 4-inch SCH 80 PVC digested sludge header; 4x2 reducer; 2x3 expansion to press | Sludge Pump and Valving Area | Install | 45-C03 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Process Valves — Sludge pumps and valving | 2023-03-31 | N | N | 0 | 0 |  |  | Unresolved | 1 | C6.2 | 45 05 00 | C6.2; 45 05 00 | Process & Mechanical
Item | CWP 45 | PROPOSED-IPS-CHECK-VALVES | Influent Pump Station discharge check valves, 4-inch and 6-inch FxF, swing check with external lever, spring and limit switch (MH 259-02ALS) | Influent Pump Station | Install | 45-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Process Valves — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 4 | 2 |  |  | Inferred | 1 | C4.1 | 45 05 00 | C4.1; 45 05 00 | Process & Mechanical
Item | CWP 45 | PROPOSED-IPS-GATE-VALVES | Influent Pump Station gate valves: 4-inch and 6-inch FxF in the valve vaults; 4-inch and 6-inch buried gate valves FLxMJ with valve boxes | Influent Pump Station | Install | 45-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Process Valves — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 4 | 2 |  |  | Inferred | 1 | C4.1 | 45 05 00 | C4.1; 45 05 00 | Process & Mechanical
Section | CWP 46 | Treatment Equipment | 60 items · 0 overdue · 0 complete |  |  |  | 2023-04-01 | 2024-07-08 | [5 empty] | 60 | 0% | 0% | 0%
Item | CWP 46 | PROPOSED-WAS-SOLENOID-VALVES | WAS inlet solenoid valves (3, on WAS #1-#3), ASCO Redhat 8221G013, 2-inch, normally closed, 120 V coil, NEMA 4X | Sludge Pump and Valving Area | Install | 46-C03 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge pumps and valving | 2023-03-31 | N | N | 0 | 0 | PROPOSED-WAS-Solenoid-Valves (Electrical & Controls) | #12, #107, #172 | Inferred | 1 | C6.2 |  | C6.2 | Process & Mechanical
Item | CWP 46 | DW-1 | Dewatering skid with skid control panel DW-1: pre-wired and factory tested, UL/ETL labeled per WA L&I, 15 HP, 480 V 3-ph; skid PLC, operator interface and network switch | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 46-C05 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Dewatering-System (Contract & General); PROPOSED-RFP-CONTROL-PANEL (Process & Mechanical); PROPOSED-ROTARY-FAN-PRESS (Process & Mechanical) | #63, #207 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.1; E6.3; E7.0; E9.1 |  | E4.1; E6.1; E6.3; E7.0; E9.1 | Electrical & Controls
Item | CWP 46 | PROPOSED-WAS-Solenoid-Valves | WAS solenoid valves (3), WAS #1 to #3, 120 V from the IPS panel | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 46-C05 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-WAS-SOLENOID-VALVES (Process & Mechanical) | #12, #107 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.3; E8.4 |  | E4.1; E6.3; E8.4 | Electrical & Controls
Item | CWP 46 | PROPOSED-Polymer-Feed-Pump | Polymer feed pump at the dewatering skid; 120 V GFCI receptacle LP2-6 and 4–20 mA flow pace | Treatment Building (existing; E4.1 key note 3 calls it "Dewatering Building" — see Issues) | Install | 46-C05 | 2023-04-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Existing dewatering / treatment building | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-POLYMER-SYSTEM (Process & Mechanical) | #64 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E4.1; E6.2; E6.3; E8.6; E10.2 |  | E4.1; E6.2; E6.3; E8.6; E10.2 | Electrical & Controls
Item | CWP 46 | PROPOSED-UV-TRANSMISSIVITY-ANALYZER | UV transmissivity analyzer, Hach DR 1900 (1) | Not stated | Install | 46-C06 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber | 2023-03-31 | Y | Y | 1 | 1 |  | #115 | Inferred | 1 |  | 46 66 10 | 46 66 10 | Process & Mechanical
Item | CWP 46 | UV1 | UV disinfection unit No.1 (UV modules on 10-ft cords, 2 per PDR) | UV Disinfection Chamber | Install | 46-C06 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-UV-Disinfection-System (Contract & General); PROPOSED-UV-SYSTEM (Process & Mechanical) | #54 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E5.1; E6.2; E6.3; E7.3; E7.5 |  | E5.1; E6.2; E6.3; E7.3; E7.5; 26 80 00 | Electrical & Controls
Item | CWP 46 | UV2 | UV disinfection unit No.2 (UV modules on 10-ft cords, 2 per PDR) | UV Disinfection Chamber | Install | 46-C06 | 2023-04-01 | 2023-10-11 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-UV-Disinfection-System (Contract & General); PROPOSED-UV-SYSTEM (Process & Mechanical) | #54 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E5.1; E6.2; E6.3; E7.3; E7.5 |  | E5.1; E6.2; E6.3; E7.3; E7.5; 26 80 00 | Electrical & Controls
Item | CWP 46 | PROPOSED-UV-SYSTEM | UV disinfection system, Trojan UV3000 PTP or equal: 2 open-channel systems (UV Channels #1 and #2), 6 modules per bank, 4 lamps per module, 48 lamps, stainless channels with level control weirs | UV Disinfection Chamber & Digester | Install | 46-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber and digester | 2023-03-31 | Y | Y | 10 | 6 | PROPOSED-UV-Disinfection-System (Contract & General); UV1 (Electrical & Controls); UV2 (Electrical & Controls) | #54 | Unresolved | 1; Equipment Alternate D | G0.5; G0.6; G0.7; C5.1; C5.2; C5.3; C5.4 | 46 66 00 | G0.5; G0.6; G0.7; C5.1; C5.2; C5.3; C5.4; 46 66 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-UV-CONTROL-PANELS | UV control panels on chamber walls (2 on C5.1): splitter panel, power distribution receptacles and wall-mounted system monitor per UV unit (C5.4) | UV Disinfection Chamber & Digester | Install | 46-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber and digester | 2023-03-31 | Y | Y | 8 | 4 | PROPOSED-UV-Control-Panel-1 (Electrical & Controls); PROPOSED-UV-Control-Panel-2 (Electrical & Controls); PROPOSED-UV-Power-Distribution-1 (Electrical & Controls); PROPOSED-UV-Power-Distribution-2 (Electrical & Controls) | #55 | Unresolved | 1; Equipment Alternate D | C5.1; C5.2; C5.3; C5.4 | 46 66 00 | C5.1; C5.4; 46 66 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-DIGESTER-DIFFUSERS | Aerobic digester coarse bubble diffusers, 24-in. 316 SS, open bottom with rubber inlet check valve (G0.7: 6 at 20 cfm) | UV Disinfection Chamber & Digester | Install | 46-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber and digester | 2023-03-31 | Y | N | 4 | 0 |  |  | Inferred | 1 | G0.7; C5.1; C5.2; C5.3 | 46 51 21 | G0.7; C5.1; C5.2; C5.3; 46 51 21 | Process & Mechanical
Item | CWP 46 | PROPOSED-UV-INTENSITY-SENSORS | UV intensity sensors (2, one per bank), submersible, with low-UV alarm contact | UV Disinfection Chamber & Digester | Install | 46-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber and digester | 2023-03-31 | Y | Y | 5 | 2 |  | #114 | Inferred | 1; Equipment Alternate D |  | 46 66 00 | 46 66 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-UV-Disinfection-System | UV disinfection system equipment | UV Disinfection Chamber & Digester | Install | 46-C07 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — UV chamber and digester | 2023-03-31 | Y | Y | 12 | 6 | PROPOSED-UV-SYSTEM (Process & Mechanical); UV1 (Electrical & Controls); UV2 (Electrical & Controls) | #54, #251 | Inferred | 1; Equipment Alternate D |  | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00; 01 91 00 | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00; 01 91 00; CQA Plan | Contract & General
Item | CWP 46 | PROPOSED-PLANT-DRAIN-LINE | Filtrate, pressate and digester supernatant drain line to Influent Pump Station, 4-inch (IE 13.40 at wet well) | Site | Install | 46-C08 | 2023-04-01 | 2023-11-01 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Yard piping, vaults and site utilities | 2023-03-31 | N | N | 0 | 0 | Pipe ID 25 (Civil & Site) | #89 | Inferred | 1 | G0.5; G0.6; C4.1; C5.1; C5.3; C6.1 | 46 76 26 | G0.5; G0.6; C4.1; C5.1; C5.3; C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-FLOW-SPLITTER-BOX | Influent flow splitter box, prefabricated 316 SS, 4 equal chambers with adjustable weirs, removable cover | Influent Flow Splitter | Install | 46-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Influent pump station and flow splitter | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Influent-Flow-Splitter (Contract & General); PROPOSED-Flow-Splitter (Structural & Building) | #75, #103 | Inferred | 1 | G0.5; G0.6; C3.1; C3.2 |  | G0.5; G0.6; C3.1; C3.2 | Process & Mechanical
Item | CWP 46 | PROPOSED-Influent-Sampler | Influent sampler (Owner-furnished, contractor-installed); 120 V GFCI receptacle LP2-8 and 4–20 mA flow pace | Influent Pump Station | Install | 46-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 |  | #13, #122, #251 | Verified-Visual | 6 (installation, receptacle, flow-pace signal); sampler Owner-furnished | E4.1; E6.2; E6.3; E8.6 |  | E4.1; E6.2; E6.3; E8.6; 26 80 00 | Electrical & Controls
Item | CWP 46 | PROPOSED-Flow-Splitter | Flow splitter — per civil, attachment by others | Flow Splitter | Install | 46-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Influent pump station and flow splitter | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Influent-Flow-Splitter (Contract & General); PROPOSED-FLOW-SPLITTER-BOX (Process & Mechanical) | #75, #103, #237 | Inferred | 1 (Inferred per 04) | S2.4 |  | S2.4 | Structural & Building
Item | CWP 46 | PROPOSED-Influent-Flow-Splitter | Influent flow splitter | Influent Flow Splitter | Install | 46-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Influent pump station and flow splitter | 2023-03-31 | N | Y | 0 | 6 | PROPOSED-Flow-Splitter (Structural & Building); PROPOSED-FLOW-SPLITTER-BOX (Process & Mechanical) | #75, #103, #251 | Inferred | 1 |  | 00 31 13; 00 73 00; 01 45 00; 01 50 00 | 00 31 13; 00 73 00; 01 45 00; 01 50 00; CQA Plan | Contract & General
Item | CWP 46 | PROPOSED-Influent-Sampler | Influent sampler | Not stated | Install | 46-C02 | 2023-06-01 | 2023-10-25 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Influent pump station and flow splitter | 2023-03-31 | Y | Y | 9 | 3 |  | #13, #122, #251 | Inferred | Not stated |  | 00 31 13; 01 33 00; 01 70 00 | 00 31 13; 01 33 00; 01 70 00 | Contract & General
Item | CWP 46 | WAS3 | Train 3 WAS / clarifier drain line to WAS pump manifold, 2-inch | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | N | 0 | 0 | Pipe ID 15 (Civil & Site) | #85, #162 | Inferred | 1 | G0.5; C3.3; C3.4; C6.2 | 46 53 00 | G0.5; C3.3; C3.4; 46 53 00; C6.2 | Process & Mechanical
Item | CWP 46 | DO #1 ¦ DO-1 | Dissolved oxygen / pH sensor, Train 3 Aeration Zone #1 ¦ Dissolved oxygen sensor and transmitter, Zone 1 (Hach LDO probe, SC200 transmitter, 24 VDC) | Train 3 ¦ Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 4 | 3 | PROPOSED-Train-3-pH-Sensors (Contract & General); PROPOSED-Train-3-Dissolved-Oxygen-Sensors (Contract & General) | #1, #35, #160, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B ¦ 6 | C3.3; E3.1; E7.6 | 46 53 00; 26 80 00 | C3.3; 46 53 00; E3.1; E7.6; 26 80 00 | Process & Mechanical; Electrical & Controls
Item | CWP 46 | DO #2 ¦ DO-2 | Dissolved oxygen / pH sensor, Train 3 Aeration Zone #2 ¦ Dissolved oxygen sensor and transmitter, second monitor (Hach LDO/SC200) | Train 3 ¦ Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 4 | 3 | PROPOSED-Train-3-pH-Sensors (Contract & General); PROPOSED-Train-3-Dissolved-Oxygen-Sensors (Contract & General) | #2, #35, #160, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B ¦ 6 | C3.3; E3.1; E6.3; E7.6 | 46 53 00; 26 80 00 | C3.3; 46 53 00; E3.1; E6.3; E7.6; 26 80 00 | Process & Mechanical; Electrical & Controls
Item | CWP 46 | PROPOSED-TRAIN-3-TANK | Train 3 tank, reinforced concrete bullseye tank, 32-ft ID, 34-ft OD, 12-inch walls | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | N | 0 | 0 | PROPOSED-Train-3-Concrete-Tank (Structural & Building) | #29, #158, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.5; G0.6; G0.7; C3.3; C3.4; C3.5 | 46 53 00 | G0.5; G0.6; G0.7; C3.3; C3.4; C3.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-TREATMENT-SYSTEM | Train 3 biological treatment system package, Smith & Loveless Model R Oxigest (basis of design) or approved equal | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 4 | 3 | PROPOSED-Train-3-Biological-Treatment-Equipment (Contract & General) | #30, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.5; G0.6; G0.7; C3.3; C3.4; C3.5 | 46 53 00 | 46 53 00; C3.3; C3.4; C3.5 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-INNER-WALLS | Train 3 steel inner walls and zone partition walls, structural steel plate 1/4-inch minimum | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | N | 2 | 0 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | C3.3 | 46 53 00 | C3.3; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-CLARIFIER-MECHANISM | Train 3 clarifier mechanism, 18-ft dia.: center drive, feed well, rake arms, skimmer, scum baffle, effluent trough and weirs, scum airlift | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 2 | 1 | PROPOSED-Train-3-Clarifier-Drive-Motor (Electrical & Controls); PROPOSED-Clarifier (Contract & General) | #33, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | C3.3; C3.4; C3.5 | 46 53 00 | C3.3; C3.4; C3.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-WALKWAYS-AND-LADDER | Train 3 access walkway (3-ft clarifier bridge), 2-ft peripheral service walkway, aluminum grating and handrail, aluminum ladder with concrete pad | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | N | 2 | 0 | PROPOSED-Handrails (Contract & General); PROPOSED-Train-3-Guardrail-and-Ladders (Structural & Building) | #34, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | C3.3; C3.4; C3.5 | 46 53 00 | C3.3; C3.4; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-AERATION-DIFFUSERS | Train 3 aeration system: air header, drop pipes with unions and air control valves, medium bubble (plenum) diffusers, 8 in Aeration Zone 1 and 2 in Aeration Zone 2 | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 2 | 2 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.7; C3.3; C3.4; C3.5 | 46 53 00 | G0.7; C3.3; C3.4; C3.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-ANOXIC-MIXERS | Train 3 submersible mixers (2), 5 HP, 460 V 3-phase, one per anoxic zone | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 4 | 3 | PROPOSED-Train-3-Submersible-Mixer-A (Electrical & Controls); PROPOSED-Train-3-Submersible-Mixer-B (Electrical & Controls) | #32, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.7; C3.3; C3.4 | 46 53 00; 46 41 23 | G0.7; C3.3; C3.4; 46 53 00; 46 41 23 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-DAVIT-CRANES | Portable lifting davits (2) for the Train 3 mixers, stainless, manual brake winch, on top mast brackets | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | N | 2 | 0 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | C3.3; C3.4 | 46 41 23 | C3.3; C3.4; 46 41 23 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-RAS-AIRLIFT | RAS airlift pump, 3-inch steel riser with flow division (weir) box, 51 gpm at 15 cfm max | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 3 | 2 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.5; G0.7; C3.3; C3.5 | 46 53 00 | G0.5; G0.7; C3.3; C3.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-MLR-AIRLIFT | Nitrate (mixed liquor) recycle airlift pump(s), 6-inch steel riser, Liqui-Lift weir box, 6-inch MLR pipe | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 3 | 2 |  | #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.5; G0.7; C3.3; C3.4; C3.5 | 46 53 00 | G0.5; G0.7; C3.3; C3.4; C3.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-CARBON-FEED-PUMPS | Carbon feed peristaltic metering pumps (2: 1 duty, 1 standby), Stenner Model S3V02AA302N | Not stated (feeds Train 3 Anoxic 2 per G0.5) | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 3 | 1 |  | #161, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B | G0.5 | 46 53 00 | G0.5; 46 53 00 | Process & Mechanical
Item | CWP 46 | PROPOSED-TRAIN-3-CONTROL-PANEL | Treatment system control panel, NEMA 4X 316 SS, 460 V 3-phase input, UL listed | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 2 | 1 | TCP-3 (Electrical & Controls) | #31, #161, #255 | Unresolved | 1; 18 — Unresolved (see 04); 19; Equipment Alternate B |  | 46 53 00 | 46 53 00 | Process & Mechanical
Item | CWP 46 | TCP-3 | Train No.3 control panel TCP-3 (by treatment system provider), 480 V 3-ph input, NEMA 4X Type 316 SS | Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-TRAIN-3-CONTROL-PANEL (Process & Mechanical) | #31, #161 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E3.1; E6.1; E6.3; E7.3; E9.1 |  | E3.1; E6.1; E6.3; E7.3; E9.1 | Electrical & Controls
Item | CWP 46 | PROPOSED-Train-3-Clarifier-Drive-Motor | Train No.3 clarifier drive motor | Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-Clarifier (Contract & General); PROPOSED-TRAIN-3-CLARIFIER-MECHANISM (Process & Mechanical) | #33 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E3.1; E6.3 |  | E3.1; E6.3 | Electrical & Controls
Item | CWP 46 | PROPOSED-Train-3-Submersible-Mixer-A | Train No.3 submersible mixer A | Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-TRAIN-3-ANOXIC-MIXERS (Process & Mechanical) | #32 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E3.1; E6.3 |  | E3.1; E6.3 | Electrical & Controls
Item | CWP 46 | PROPOSED-Train-3-Submersible-Mixer-B | Train No.3 submersible mixer B | Train No.3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 | PROPOSED-TRAIN-3-ANOXIC-MIXERS (Process & Mechanical) | #32 | Inferred | 1 (equipment, Inferred per 04); 6 (power and control) | E3.1; E6.3 |  | E3.1; E6.3 | Electrical & Controls
Item | CWP 46 | PROPOSED-Hypochlorite-Feed-Pump | Hypochlorite feed pump; 120 V GFCI receptacle on LP1-16 and 4–20 mA flow pace | Not stated (drawn on E4.1) | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 |  | #121 | Verified-Visual | 1 (equipment, Inferred per 04); 6 (power and control) | E2.2; E4.1; E6.2; E6.3; E7.7; E10.2 |  | E2.2; E4.1; E6.2; E6.3; E7.7; E10.2 | Electrical & Controls
Item | CWP 46 | PROPOSED-Effluent-Sampler | Effluent sampler (Owner-furnished, contractor-installed); 120 V GFCI receptacle on LP1-14 and 4–20 mA flow pace | Not stated (drawn on E4.1) | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Not stated | Not stated | 0 | 0 |  | #123 | Verified-Visual | 6 (installation, receptacle, flow-pace signal); sampler Owner-furnished | E2.2; E4.1; E6.2; E6.3; E7.7 |  | E2.2; E4.1; E6.2; E6.3; E7.7; 26 80 00 | Electrical & Controls
Item | CWP 46 | PROPOSED-Train-3 | Train 3 (third treatment train) | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | Y | 0 | 6 |  | #251, #253 | Inferred | 1 |  | 00 31 13; 00 24 13; 00 73 00; 01 45 00; 01 50 00 | 00 31 13; 00 24 13; 00 73 00; 01 45 00; 01 50 00; CQA Plan | Contract & General
Item | CWP 46 | PROPOSED-Train-3-Biological-Treatment-Equipment | Train 3 biological treatment system equipment | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 12 | 7 | PROPOSED-TRAIN-3-TREATMENT-SYSTEM (Process & Mechanical) | #30, #251, #255 | Unresolved | 1; Equipment Alternate B; 18 — Unresolved (see 04); 19 |  | 00 24 13; 00 41 00; 01 33 00; 01 70 00; 01 91 00; 01 45 00 | 00 24 13; 00 41 00; 01 33 00; 01 70 00; 01 91 00; 01 45 00 | Contract & General
Item | CWP 46 | PROPOSED-Aeration-Basins | Aeration basins (Train 3) | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | Y | 0 | 4 |  | #251, #252 | Inferred | 1 |  | 01 45 00; 01 50 00 | 01 45 00; 01 50 00 | Contract & General
Item | CWP 46 | PROPOSED-Anoxic-Basins | Anoxic basins (Train 3) | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | Y | 0 | 4 |  | #251, #252 | Inferred | 1 |  | 01 45 00; 01 50 00 | 01 45 00; 01 50 00 | Contract & General
Item | CWP 46 | PROPOSED-Clarifier | Clarifier (Train 3) | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | Y | 0 | 5 | PROPOSED-Train-3-Clarifier-Drive-Motor (Electrical & Controls); PROPOSED-TRAIN-3-CLARIFIER-MECHANISM (Process & Mechanical) | #33, #251, #252 | Inferred | 1 |  | 01 45 00; 01 50 00; 01 91 00 | 01 45 00; 01 50 00; 01 91 00 | Contract & General
Item | CWP 46 | PROPOSED-Train-3-Dissolved-Oxygen-Sensors | Dissolved oxygen (DO) sensors, Train 3 | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 11 | 4 | DO #1 (Process & Mechanical); DO-1 (Process & Mechanical); DO #2 (Process & Mechanical); DO-2 (Process & Mechanical) | #35, #251, #253 | Inferred | 1; Equipment Alternate B (package — Inferred) |  | 01 91 00; 01 33 00; 01 70 00 | 01 91 00; 01 33 00; 01 70 00 | Contract & General
Item | CWP 46 | PROPOSED-Train-3-pH-Sensors | pH sensors, Train 3 | Train 3 | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | Y | Y | 11 | 4 | DO #1 (Process & Mechanical); DO-1 (Process & Mechanical); DO #2 (Process & Mechanical); DO-2 (Process & Mechanical) | #35, #251, #253 | Inferred | 1; Equipment Alternate B (package — Inferred) |  | 01 91 00; 01 33 00; 01 70 00 | 01 91 00; 01 33 00; 01 70 00 | Contract & General
Item | CWP 46 | PROPOSED-Handrails | Handrails | Not stated | Install | 46-C04 | 2023-08-01 | 2024-07-08 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Train 3 | 2023-03-31 | N | N | 0 | 0 | PROPOSED-TRAIN-3-WALKWAYS-AND-LADDER (Process & Mechanical); PROPOSED-Train-3-Guardrail-and-Ladders (Structural & Building) | #34, #252 | Inferred | 1 |  | 01 70 00 | 01 70 00 | Contract & General
Item | CWP 46 | PROPOSED-DIGESTED-SLUDGE-FLOW-METER | Rotary press sludge flowmeter, 3-inch electromagnetic (E+H 10W), 24-800 gpm, at the flocculator inlet (G0.5 digested sludge FM) | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 2 | 0 |  | #172 | Unresolved | 1; Equipment Alternate C | G0.5; C6.2 | 46 76 26 | G0.5; C6.2; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-ROTARY-FAN-PRESS | Rotary fan press (rotary press model), steel, 1 unit | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 3 | 5 | PROPOSED-Dewatering-System (Contract & General); DW-1 (Electrical & Controls) | #63 | Inferred | 1; Equipment Alternate C | G0.5; G0.6; G0.7; C6.1 | 46 76 26 | C6.1; G0.7; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-FLOCCULATOR | Rotary fan press flocculator, steel, 1 | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 1 | 3 |  |  | Inferred | 1; Equipment Alternate C | C6.1 | 46 76 26 | C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-SLUDGE-MANIFOLD | Rotary fan press sludge manifold and piping, 316 SS, 1 | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 1 | 3 |  |  | Inferred | 1; Equipment Alternate C | C6.1 | 46 76 26 | C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-CAKE-CHUTE | Rotary fan press cake chute, LLDPE, 1 | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 1 | 0 |  |  | Inferred | 1; Equipment Alternate C | C6.1 | 46 76 26 | C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-AIR-COMPRESSOR | Rotary fan press air compressor, material not listed, 1 | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 1 | 0 |  |  | Inferred | 1; Equipment Alternate C | C6.1 | 46 76 26 | C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-CONTROL-PANEL | Rotary fan press control panel with operator interface, 1 | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 1 | 3 | PROPOSED-Dewatering-System (Contract & General); DW-1 (Electrical & Controls) | #63 | Unresolved | 1; Equipment Alternate C | C6.1 | 46 76 26 | C6.1; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-POLYMER-SYSTEM | Emulsion (liquid) polymer make-up system, Fournier frame with Watson-Marlow peristaltic dosing pump; C6.1 plan labels a dry polymer mix unit | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 2 | 0 | PROPOSED-Polymer-Feed-Pump (Electrical & Controls) | #64 | Unresolved | 1; Equipment Alternate C | C6.1 | 46 33 33 | C6.1; 46 33 33; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-SCREW-CONVEYOR | Screw conveyor system, stainless steel, dewatered cake to mobile dumpster/bin (system row; components below) | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 3 | 5 |  |  | Unresolved | 1; Equipment Alternate C | C6.1 | 46 12 13 (as printed on C6.1; not in the spec); 41 12 13 | C6.1; 41 12 13; 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-DIGESTED-SLUDGE-FEED-TO-PRESS | Digested sludge feed to rotary fan press, 3-inch | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | N | N | 0 | 0 |  | #106 | Inferred | 1 | G0.5; C6.1; C6.2 |  | G0.5; C6.1; C6.2 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-POLYMER-FLOWMETER | Rotary press polymer (dilution) flowmeter, 1-inch electromagnetic (E+H 10P), 5-80 gpm, at the flocculator inlet | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 2 | 0 |  | #116 | Inferred | 1; Equipment Alternate C |  | 46 76 26; 46 33 33 | 46 76 26; 46 33 33 | Process & Mechanical
Item | CWP 46 | PROPOSED-RFP-INLET-PRESSURE-TRANSMITTER | Flocculator inlet pressure transmitter, E+H PMC71, 0-30 psi, HART | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | N | 1 | 0 |  | #117 | Inferred | 1; Equipment Alternate C |  | 46 76 26 | 46 76 26 | Process & Mechanical
Item | CWP 46 | PROPOSED-Dewatering-System | Sludge dewatering system (rotary fan press) | Rotary Fan Press System | Install | 46-C01 | 2023-11-01 | 2024-02-09 | [5 empty] | 1 | 0% | 0% | 0% | Not started |  | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-03-31 | Y | Y | 12 | 6 | PROPOSED-RFP-CONTROL-PANEL (Process & Mechanical); PROPOSED-ROTARY-FAN-PRESS (Process & Mechanical); DW-1 (Electrical & Controls) | #15, #63, #251 | Unresolved | 1; Equipment Alternate C |  | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00; 01 91 00 | 00 31 13; 00 41 00; 00 73 00; 01 33 00; 01 70 00; 01 91 00; CQA Plan | Contract & General
Formulas:
Planned start = MIN([Planned start, row below]:H17)
Planned start = IFERROR(INDEX(Schedule!$E2:E147,MATCH([Schedule activity ID],Schedule!$A2:A147,0)),"")
Planned finish = MAX([Planned finish, row below]:I17)
Planned finish = IFERROR(INDEX(Schedule!$F2:F147,MATCH([Schedule activity ID],Schedule!$A2:A147,0)),"")

## Rules of Credit
Rules of credit — % earned when each step is done
Edit the yellow cells. Each row should total 100. Where the Ledger says Submittal Req = N or Testing/Startup Req = N, that step drops out and the rest scale to 100%. "Not stated" keeps the step (conservative).
Work type | Submittal approved | On site / ready | Installed / removed | Tested / inspected | Turned over / closed | Total (formula)
Install | 5 | 15 | 50 | 20 | 10 | 100
Remove | 0 | 10 | 80 | 0 | 10 | 100
Temporary | 5 | 15 | 40 | 20 | 20 | 100
Modify / connect | 5 | 10 | 55 | 20 | 10 | 100
Step meanings by work type:
Install — submittal approved; material on site; set / installed; tested or inspected per the ITP; turned over.
Remove — area isolated and ready; removed; closed out (disposal, patch, restore).
Temporary — as Install; "Turned over / closed" = removed at the end of use.
Modify / connect (existing items kept) — as Install, for the modification or connection work.
Weights are generic placeholders (no project estimate or material takeoff in this sample). Replace with the project's rules of credit.

## Schedule
ID | Type | CWP | Activity | Start | Finish
MS01 | Milestone | Milestone | Bids opened | 2023-02-08 | 2023-02-08
MS02 | Milestone | Milestone | Contract award | 2023-02-15 | 2023-02-15
MS03 | Milestone | Milestone | CPM schedule due (10 days after award) | 2023-02-25 | 2023-02-25
MS04 | Milestone | Milestone | Preconstruction meeting and Notice to Proceed | 2023-03-15 | 2023-03-15
MS05 | Milestone | Milestone | 480V service, MCC and PLC panel complete | 2023-10-04 | 2023-10-04
MS06 | Milestone | Milestone | UV system complete | 2023-10-07 | 2023-10-07
MS07 | Milestone | Milestone | UV on line; effluent switched to new 8-in piping | 2023-10-11 | 2023-10-11
MS08 | Milestone | Milestone | 2W air gap water system complete | 2023-10-18 | 2023-10-18
MS09 | Milestone | Milestone | Influent pump station, flow splitter and sampler on line | 2023-10-25 | 2023-10-25
MS10 | Milestone | Milestone | Major piping complete; aerobic digester complete | 2023-11-01 | 2023-11-01
MS11 | Milestone | Milestone | Dewatering system complete | 2024-02-09 | 2024-02-09
MS12 | Milestone | Milestone | Permanent generator on line; rental removed | 2024-04-30 | 2024-04-30
MS13 | Milestone | Milestone | Train 3 complete | 2024-07-08 | 2024-07-08
MS14 | Milestone | Milestone | Substantial Completion | 2024-07-26 | 2024-07-26
MS15 | Milestone | Milestone | Final Completion | 2024-10-16 | 2024-10-16
01-C01 | Construction | CWP 01 | General Requirements & Temporary Works — Temporary bypass and interim effluent piping | 2023-04-01 | 2023-10-11
01-C02 | Construction | CWP 01 | General Requirements & Temporary Works — Temporary facilities and controls | 2023-03-15 | 2024-10-16
02-C01 | Construction | CWP 02 | Demolition & Existing Conditions — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31
02-C02 | Construction | CWP 02 | Demolition & Existing Conditions — Site demolition ahead of new work | 2023-04-01 | 2023-05-31
02-C03 | Construction | CWP 02 | Demolition & Existing Conditions — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
03-C01 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — 2W air gap water system | 2023-05-01 | 2023-10-18
03-C02 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Blower Building | 2023-04-01 | 2023-07-31
03-C03 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Permanent standby generator | 2024-03-01 | 2024-04-30
03-C04 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
03-C05 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Sludge pumps and valving | 2023-04-01 | 2023-11-01
03-C06 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Train 3 | 2023-08-01 | 2024-07-08
03-C07 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — UV chamber and digester | 2023-04-01 | 2023-11-01
03-C08 | Construction | CWP 03 | Concrete (Cast-in-Place & Precast) — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
05-C01 | Construction | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — Train 3 | 2023-08-01 | 2024-07-08
05-C02 | Construction | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — UV chamber and digester | 2023-04-01 | 2023-11-01
08-C01 | Construction | CWP 08 | Doors, Frames & Hardware — Blower Building | 2023-04-01 | 2023-07-31
09-C01 | Construction | CWP 09 | Painting & Coatings — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
10-C01 | Construction | CWP 10 | Specialties — Blower Building | 2023-04-01 | 2023-07-31
10-C02 | Construction | CWP 10 | Specialties — Train 3 | 2023-08-01 | 2024-07-08
10-C03 | Construction | CWP 10 | Specialties — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
13-C01 | Construction | CWP 13 | Pre-Engineered Metal Building — Blower Building | 2023-04-01 | 2023-07-31
13-C02 | Construction | CWP 13 | Pre-Engineered Metal Building — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31
13-C03 | Construction | CWP 13 | Pre-Engineered Metal Building — Site demolition ahead of new work | 2023-04-01 | 2023-05-31
13-C04 | Construction | CWP 13 | Pre-Engineered Metal Building — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09
22-C01 | Construction | CWP 22 | Plumbing & Process Pumps — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
22-C02 | Construction | CWP 22 | Plumbing & Process Pumps — Sludge pumps and valving | 2023-04-01 | 2023-11-01
22-C03 | Construction | CWP 22 | Plumbing & Process Pumps — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09
22-C04 | Construction | CWP 22 | Plumbing & Process Pumps — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
23-C01 | Construction | CWP 23 | HVAC & Ventilation — Blower Building | 2023-04-01 | 2023-07-31
23-C02 | Construction | CWP 23 | HVAC & Ventilation — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09
26-C01 | Construction | CWP 26 | Electrical, Instrumentation & Controls — 2W air gap water system | 2023-05-01 | 2023-10-18
26-C02 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Blower Building | 2023-04-01 | 2023-07-31
26-C03 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing generator, switchgear and fuel tank removal | 2024-05-01 | 2024-05-31
26-C04 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing service equipment removal | 2023-10-05 | 2023-10-31
26-C05 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Aerobic digester | 2023-04-01 | 2023-11-01
26-C06 | Not scheduled | CWP 26 | Electrical, Instrumentation & Controls — Future provisions — not scheduled
26-C07 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Permanent standby generator | 2024-03-01 | 2024-04-30
26-C08 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
26-C09 | Construction | CWP 26 | Electrical, Instrumentation & Controls — SCADA / PLC programming | 2023-10-04 | 2024-07-26
26-C10 | Construction | CWP 26 | Electrical, Instrumentation & Controls — 480V service, MCC and PLC panel | 2023-04-01 | 2023-10-04
26-C11 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Sludge pumps and valving | 2023-04-01 | 2023-11-01
26-C12 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Temporary facilities and controls | 2023-03-15 | 2024-10-16
26-C13 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Temporary back-up generator (rental) | 2023-09-25 | 2024-04-30
26-C14 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Train 3 | 2023-08-01 | 2024-07-08
26-C15 | Construction | CWP 26 | Electrical, Instrumentation & Controls — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09
26-C16 | Construction | CWP 26 | Electrical, Instrumentation & Controls — UV chamber | 2023-04-01 | 2023-10-11
26-C17 | Construction | CWP 26 | Electrical, Instrumentation & Controls — UV chamber and digester | 2023-04-01 | 2023-11-01
31-C01 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
31-C02 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Temporary facilities and controls | 2023-03-15 | 2024-10-16
31-C03 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Train 3 | 2023-08-01 | 2024-07-08
31-C04 | Construction | CWP 31 | Earthwork, Dewatering & Erosion Control — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
32-C01 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Final surfacing and pavement | 2024-08-01 | 2024-08-31
32-C02 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Site finish work (fencing, walls, landscaping, bollards) | 2024-08-01 | 2024-09-30
32-C03 | Construction | CWP 32 | Paving, Fencing, Walls & Landscaping — Temporary facilities and controls | 2023-03-15 | 2024-10-16
33-C01 | Construction | CWP 33 | Yard Piping & Utilities — Blower Building | 2023-04-01 | 2023-07-31
33-C02 | Construction | CWP 33 | Yard Piping & Utilities — Temporary bypass and interim effluent piping | 2023-04-01 | 2023-10-11
33-C03 | Construction | CWP 33 | Yard Piping & Utilities — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
33-C04 | Construction | CWP 33 | Yard Piping & Utilities — Train 3 | 2023-08-01 | 2024-07-08
33-C05 | Construction | CWP 33 | Yard Piping & Utilities — UV chamber and digester | 2023-04-01 | 2023-11-01
33-C06 | Construction | CWP 33 | Yard Piping & Utilities — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
40-C01 | Construction | CWP 40 | Process Interconnections — UV chamber and digester | 2023-04-01 | 2023-11-01
41-C01 | Construction | CWP 41 | Material Handling (Screw Conveyors) — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09
43-C01 | Construction | CWP 43 | Blowers & 2W Plant Water System — 2W air gap water system | 2023-05-01 | 2023-10-18
43-C02 | Construction | CWP 43 | Blowers & 2W Plant Water System — Blower Building | 2023-04-01 | 2023-07-31
43-C03 | Construction | CWP 43 | Blowers & 2W Plant Water System — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09
43-C04 | Construction | CWP 43 | Blowers & 2W Plant Water System — Aerobic digester | 2023-04-01 | 2023-11-01
43-C05 | Construction | CWP 43 | Blowers & 2W Plant Water System — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
45-C01 | Construction | CWP 45 | Process Valves — Aerobic digester | 2023-04-01 | 2023-11-01
45-C02 | Construction | CWP 45 | Process Valves — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
45-C03 | Construction | CWP 45 | Process Valves — Sludge pumps and valving | 2023-04-01 | 2023-11-01
46-C01 | Construction | CWP 46 | Treatment Equipment — Sludge dewatering (rotary fan press) | 2023-11-01 | 2024-02-09
46-C02 | Construction | CWP 46 | Treatment Equipment — Influent pump station and flow splitter | 2023-06-01 | 2023-10-25
46-C03 | Construction | CWP 46 | Treatment Equipment — Sludge pumps and valving | 2023-04-01 | 2023-11-01
46-C04 | Construction | CWP 46 | Treatment Equipment — Train 3 | 2023-08-01 | 2024-07-08
46-C05 | Construction | CWP 46 | Treatment Equipment — Existing dewatering / treatment building | 2023-04-01 | 2024-02-09
46-C06 | Construction | CWP 46 | Treatment Equipment — UV chamber | 2023-04-01 | 2023-10-11
46-C07 | Construction | CWP 46 | Treatment Equipment — UV chamber and digester | 2023-04-01 | 2023-11-01
46-C08 | Construction | CWP 46 | Treatment Equipment — Yard piping, vaults and site utilities | 2023-04-01 | 2023-11-01
01-P01 | Submittals & procurement | CWP 01 | General Requirements & Temporary Works — submittals and procurement (20 register lines) | 2023-02-15 | 2023-03-14
01-T01 | Inspection & test | CWP 01 | General Requirements & Temporary Works — inspections and tests during the work (11 ITP lines) | 2023-03-15 | 2024-10-16
02-P01 | Submittals & procurement | CWP 02 | Demolition & Existing Conditions — submittals and procurement (0 register lines) | 2023-02-15 | 2023-03-31
02-T01 | Inspection & test | CWP 02 | Demolition & Existing Conditions — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2024-05-31
03-P01 | Submittals & procurement | CWP 03 | Concrete (Cast-in-Place & Precast) — submittals and procurement (8 register lines) | 2023-02-15 | 2023-03-31
03-T01 | Inspection & test | CWP 03 | Concrete (Cast-in-Place & Precast) — inspections and tests during the work (4 ITP lines) | 2023-04-01 | 2024-07-08
05-P01 | Submittals & procurement | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — submittals and procurement (7 register lines) | 2023-02-15 | 2023-03-31
05-T01 | Inspection & test | CWP 05 | Metals (Grating, Railings, Ladders, Stairs) — inspections and tests during the work (1 ITP lines) | 2023-04-01 | 2024-07-08
08-P01 | Submittals & procurement | CWP 08 | Doors, Frames & Hardware — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31
08-T01 | Inspection & test | CWP 08 | Doors, Frames & Hardware — inspections and tests during the work (2 ITP lines) | 2023-04-01 | 2023-07-31
09-P01 | Submittals & procurement | CWP 09 | Painting & Coatings — submittals and procurement (4 register lines) | 2023-02-15 | 2023-05-31
09-T01 | Inspection & test | CWP 09 | Painting & Coatings — inspections and tests during the work (3 ITP lines) | 2023-06-01 | 2023-10-25
10-P01 | Submittals & procurement | CWP 10 | Specialties — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31
10-T01 | Inspection & test | CWP 10 | Specialties — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-07-08
13-P01 | Submittals & procurement | CWP 13 | Pre-Engineered Metal Building — submittals and procurement (5 register lines) | 2023-02-15 | 2023-03-31
13-T01 | Inspection & test | CWP 13 | Pre-Engineered Metal Building — inspections and tests during the work (1 ITP lines) | 2023-04-01 | 2024-05-31
22-P01 | Submittals & procurement | CWP 22 | Plumbing & Process Pumps — submittals and procurement (6 register lines) | 2023-02-15 | 2023-03-31
22-T01 | Inspection & test | CWP 22 | Plumbing & Process Pumps — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-02-09
23-P01 | Submittals & procurement | CWP 23 | HVAC & Ventilation — submittals and procurement (1 register lines) | 2023-02-15 | 2023-03-31
23-T01 | Inspection & test | CWP 23 | HVAC & Ventilation — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2024-02-09
26-P01 | Submittals & procurement | CWP 26 | Electrical, Instrumentation & Controls — submittals and procurement (26 register lines) | 2023-02-15 | 2023-03-14
26-T01 | Inspection & test | CWP 26 | Electrical, Instrumentation & Controls — inspections and tests during the work (23 ITP lines) | 2023-03-15 | 2024-10-16
31-P01 | Submittals & procurement | CWP 31 | Earthwork, Dewatering & Erosion Control — submittals and procurement (11 register lines) | 2023-02-15 | 2023-03-14
31-T01 | Inspection & test | CWP 31 | Earthwork, Dewatering & Erosion Control — inspections and tests during the work (9 ITP lines) | 2023-03-15 | 2024-10-16
32-P01 | Submittals & procurement | CWP 32 | Paving, Fencing, Walls & Landscaping — submittals and procurement (6 register lines) | 2023-02-15 | 2023-03-14
32-T01 | Inspection & test | CWP 32 | Paving, Fencing, Walls & Landscaping — inspections and tests during the work (2 ITP lines) | 2023-03-15 | 2024-10-16
33-P01 | Submittals & procurement | CWP 33 | Yard Piping & Utilities — submittals and procurement (14 register lines) | 2023-02-15 | 2023-03-31
33-T01 | Inspection & test | CWP 33 | Yard Piping & Utilities — inspections and tests during the work (21 ITP lines) | 2023-04-01 | 2024-07-08
40-P01 | Submittals & procurement | CWP 40 | Process Interconnections — submittals and procurement (1 register lines) | 2023-02-15 | 2023-03-31
40-T01 | Inspection & test | CWP 40 | Process Interconnections — inspections and tests during the work (0 ITP lines) | 2023-04-01 | 2023-11-01
41-P01 | Submittals & procurement | CWP 41 | Material Handling (Screw Conveyors) — submittals and procurement (1 register lines) | 2023-02-15 | 2023-10-31
41-T01 | Inspection & test | CWP 41 | Material Handling (Screw Conveyors) — inspections and tests during the work (1 ITP lines) | 2023-11-01 | 2024-02-09
43-P01 | Submittals & procurement | CWP 43 | Blowers & 2W Plant Water System — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31
43-T01 | Inspection & test | CWP 43 | Blowers & 2W Plant Water System — inspections and tests during the work (3 ITP lines) | 2023-04-01 | 2024-02-09
45-P01 | Submittals & procurement | CWP 45 | Process Valves — submittals and procurement (3 register lines) | 2023-02-15 | 2023-03-31
45-T01 | Inspection & test | CWP 45 | Process Valves — inspections and tests during the work (2 ITP lines) | 2023-04-01 | 2023-11-01
46-P01 | Submittals & procurement | CWP 46 | Treatment Equipment — submittals and procurement (19 register lines) | 2023-02-15 | 2023-03-31
46-T01 | Inspection & test | CWP 46 | Treatment Equipment — inspections and tests during the work (13 ITP lines) | 2023-04-01 | 2024-07-08
03-S01 | Test / start-up | CWP 03 | Clean-water leakage test — UV chamber | 2023-09-27 | 2023-10-10
03-S02 | Test / start-up | CWP 03 | Clean-water leakage test — 2W wet well | 2023-10-04 | 2023-10-17
03-S03 | Test / start-up | CWP 03 | Clean-water leakage test — influent pump station wet well and flow splitter | 2023-10-11 | 2023-10-24
03-S04 | Test / start-up | CWP 03 | Clean-water leakage test — aerobic digester | 2023-10-18 | 2023-10-31
03-S05 | Test / start-up | CWP 03 | Clean-water leakage test — Train 3 aeration and anoxic basins and clarifier | 2024-06-24 | 2024-07-07
33-S06 | Test / start-up | CWP 33 | Pipe pressure testing, witnessed (48-hour notice) | 2023-10-01 | 2023-10-31
26-S07 | Test / start-up | CWP 26 | Temporary generator connection and automatic load transfer test (Add. 4 Clarification 5) | 2023-09-25 | 2023-10-04
26-S08 | Test / start-up | CWP 26 | 480V service, MCC and PLC testing and energization | 2023-09-20 | 2023-10-04
26-S09 | Test / start-up | CWP 26 | Permanent generator load bank test, 2 hours at full load (26 32 13) | 2024-04-15 | 2024-04-30
46-S10 | Test / start-up | CWP 46 | UV system start-up and field testing (46 66 00: 2 days start-up, 1 day training) | 2023-10-07 | 2023-10-11
43-S11 | Test / start-up | CWP 43 | 2W system start-up (01 91 00 ¶1.10: hold 60–90 psi, 0–50 gpm) | 2023-10-11 | 2023-10-18
22-S12 | Test / start-up | CWP 22 | Influent pumps and flow splitter start-up | 2023-10-18 | 2023-10-25
43-S13 | Test / start-up | CWP 43 | Blower start-up (01 91 00) | 2023-10-18 | 2023-11-01
46-S14 | Test / start-up | CWP 46 | Dewatering system start-up (01 91 00 ¶1.07.A) | 2024-02-01 | 2024-02-09
46-S15 | Test / start-up | CWP 46 | Train 3 start-up and seeding, 10,000 gal activated sludge | 2024-07-08 | 2024-07-12

## Legend
How to use the tracker
Edit | Tracker Summary C3 (yellow): status date. Tracker, blue cells: Work type (drop-down), the five step dates (date, or N/A if the step does not apply), Weight, Remarks. Rules of Credit (yellow): step weights. Schedule tab (blue dates): re-plan an activity and every linked item follows.
Do not edit | All other Tracker columns are formulas or Ledger reference data.
Earned % | Sum of the weights of completed steps ÷ sum of the weights that apply. The submittal step drops out only when the Ledger says Submittal Req = N, the test step only when Testing/Startup Req = N; "Not stated" keeps the step, so progress is not overstated.
Planned % | Straight line from planned start to planned finish at the status date.
Flag | Complete (100%) · Overdue (past planned finish, not complete) · Behind (earned more than 10 points below planned) · Not started (nothing earned, start still ahead) · On track (everything else).
Sections | Each CWP starts with a colored section row showing its item count, overdue and complete counts, planned window, and weighted planned / earned %.
Duplicates | Some physical items sit on more than one Ledger row (different lanes, different tags). "Also tracked as" names the other rows — update one and mark the others N/A or weight 0 until the tag crosswalk is done.
Weight | Defaults to 1 per item (no material takeoff or estimate in this sample). Replace with hours or quantities when available.
Example (not part of the tracker data): an Install item needing a submittal and a test
Work type | Submittal approved | On site / ready | Installed / removed | Tested / inspected | Turned over / closed | Submittal req | Testing req | Earned % (formula)
Install | 2023-03-10 | 2023-06-15 | 2023-07-20 |  |  | Y | Y | 70%
→ 5 + 15 + 50 of 100 = 70% until the test and turnover dates are entered.